request for project preparation grant (PPG)

Project Type:

the GEF Trust Fund

Submission date:  01/12/2010

GEF Project ID:

GEF Agency  Project ID:

Country(ies): Tunisia

Project Title: Tunisia Ecotourism and Conservation of Desert Biodiversity

GEF Agency(ies): , ,

Other Executing partner(s):

GEF Focal Area(s): Biodiversity and Land Degradation

GEF-4 Strategic program(s): BD1 and BD2; LD-SP1 and LD-SP3 (see preparation guidelines section on exactly what to write)

name of parent/program/umbrella project (if applicable):

a.   Project preparation Timeframe

| Start date of PPG | March 2010 |
| --- | --- |
| Completion date of PPG | March 2011 |

- Past project preparation activities ($)

| ### List of Past Project Preparation Activities | ### Output of the Activities | Project Preparation Amount (a) | Co-financing (b) In-kind | Total c = a + b |
| --- | --- | --- | --- | --- |
| Total Project Preparation Financing |  |  |  |  |

C.  proposed project preparation activities ($)

| ##### Describe the PPG activities and justifications: ##### The goal of the Project is to help develop sustainable nature-based tourism (or ecotourism) as a means to promote environmental, financial, and social sustainabiltiy in Tunisia. It aims to reduce and reverse the degradation of Tunisia’s natural capital by integrating conservation of desert biodiversity and desert lands at all levels of ecotourism development. ##### The preparatory phase, for which the PPG is being requested, will complete the design of the full Project, including: collection of baseline information; identifying gaps in information; gathering key data/information for the design of the components; identifying and confirming the lead entities and implementation arrangements for each component; developing indicators for monitoring and evaluation both at the component and overall project level; and identifying and securing partnerships and other sources of financing and co-financing. It will also develop synergies with on-going projects, especially with the Project on Integrated NRM in the Middle East and the North Africa Region (MENARID), which is co-financing the Project, and the planned work on M&E and KM under one of MENARID's MSPs. The preparatory phase will also identify and assess the insitutional capacity required for project implementation. The PPG grant would finance the costs for national and international consultants and provide logistic support for the activities listed and described in more detail below. ##### The project preparation process will provide opportunities: ( i) for the key Government ministries and other stakeholders to share concerns and knowledge and thus deepen the understanding of nature tourism, biodiversity and land degradation challenges and possible solutions; (ii) to help identify related information needs and collect and analyze the available or gathered data; (iii) to discuss an institutional mechanisms so that concerns and agreed actions can be included in development planning and strategies by the relevant institutions on a regular basis; and (iv) to contribute to the project design and preparation based on participation and consultations. ##### The proposed PPG work includes 5 planned Activities: ##### Activity 1: Setting up of a Steering Committee; holding an inception workshop; preparing TORs for studies. In addition to the Steering Committee, an interdisciplinary working group with personnel from the project partners will be set up to collaborate with the project planning and preparation work. The management structure for project preparation work would be designed so that the work can efficiently be carried out, while appropriately involving different stakeholders. This activity would also include the development of the Terms of Reference and the hiring of the Project Coordinator and support staff. The initital Steering Committee (PSC) may later be restructured, if necessary, based on the stakeholder analysis and consultations. During the inception workshop various key issus would be discussed and considered by key ministries/agencies and other stakeholders, including institutional approaches, ecotourism, biodiversity conservation, land degradation, water conservation, and institutional and planning aspects. The inception workshop would help finalize the TORs for the planned studies, provide guidance, help with data gathering, and prioritize analytical work. ##### Activity 2: Studies. Studies will be undertaken as a basis for developing each proposed project components. Thus, studies are planned on: ##### (a) The development and implementation of institutional, incentive and legal framework for ecotourism at the central government, provincial, and local levels, including promotion, provision of training, sensitization, inter-ministerial coordination, changes in laws and regulations, creation of a soft loan window for community-based and other private sector investments, etc. This will support the institutional development component; ##### (b) The preparation and implementation of Management Plans for selected protected areas/reserves, while leveraging general support to strengthen management in new and existing protected areas and reserves. This will support the protected area management component; ##### (c) Integrated natural resources management (INRM) including sustainable land management (SLM) best practices in the productive agricultural and rangeland management systems in the main arid Provinces to achieve inceased sustainability, resilience, and agro-biodiversity. This will support the INRM Component; ##### (d) Investing in public infrastructure improvements, including access roads, visitor centers, lodges, signage, vista points, educational materials, etc., in order to make nature more accessible to visitors at selected protected areas/agro-biodiversity sites, while at the same time keeping the ecological footprint to a minimum. This study will support the public nature tourism investment component; ##### (e) Establishing joint ventures between local communities, NGOs, and the public/private sector at the selected sites/protected areas, and encouraging such ventures nation-wide. This study would support the community and private sector development component. ##### Each study would be prepared under specific terms of reference that would describe the main issues in each area, identify data sources, summarize available data, taking stock of existing knowledge and current and planned actions, analyze data, and review development strategies, where relevant. Each study would then propose a specific set of actions/activities to be undertaken during the project, along with initial costing, outputs and outcomes, and ways for monitoring and evalution, who would carry out the work, etc. These will subsequently form the basis for preliminary discussions with government agencies and other key stakeholders and then be discussed at workshops (Activity 3). ##### Activity 3: Workshops and stakeholder consultations. Workshops would be held back-to-back to discuss each draft study, concluding with a workshop on the overall project design. The project preparation team will carry out local meetings with institutions, organizations, and community groups to ensure that stakeholder input is incorporated into the project; both to promote involvement in the project formulation process and to collect necessary information. This process will also help identify local capabilities and awareness to develop project activities. The results from this process will be written up and discussed at the workshops, where applicable. ##### Activity 4: Revisions/finalization of preliminary studies, and preparation of overall draft project report. The revisions of the preliminary studies would be based on feedback received from the consultations and specific worshops. Further, based on the consultations and workshops a draft of an overall Project Appraisal Document (PAD) would be prepared. It would summarize and integrate the main preliminary findings and recommendations and, on that basis, would design the project and its components. The project proposal would include preliminary detailed cost estimates and specifications for project implementation, procurement specifications for project activities, financial arrangements, and a financing and investment plan needed to implement the project. The draft will include incremental cost analysis to identify expenditures that would be financed by GEF, and through sources of co-financing to support other portions and "non-incremental" aspects of the project. ##### Activity 5. Concluding Project Preparation Workshop and Finalization of Project Design and Implementation Arrangements. This workshop would discuss the overall findings and recommendations and in particular seek to arrive at a consensus among government agencies and other stakeholders about the specifics of the proposed Project as contained in the overall draft PAD. On the basis of the workshop the project document would be finalized, including a logframe with outputs and outcomes, a monitoring plan, procurement plan, implementation arrangements, etc. ##### Justification. The proposed project fits both within the strategic direction of the Government of Tunisia as well as those of the GEF. It is an innovative project whose approach and lessons would likely be beneficial to other MNA countries with large desert ecosystems, land degradation and biodiversity challenges, and an interest in developing nature tourism. While the Ministry of Tourism and the Ministry of Agriculture are interested in developing nature tourism, in combatting land degradation, and in conserving valuable desert biodiversity, more detailed work is needed to prepare a project that can be funded by the GEF, which is why the grant is being requested. |  |  |  |  |
| --- | --- | --- | --- | --- |
| ### List of Proposed Project Preparation Activities | ### Output of the PPG Activities | Project Preparation Amount (a) | Co-financing (b) | Total c = a + b |
| 1. Setting up Steering Committee; holding inception workshop; preparing TORs for studies. | Report institutional set-up for project preparation phase; workshop report; TORs (French and English) | 10,000 | 10,000 | 20,000 |
| 2. Studies | ##### Drafts of five studies | 80,000 | 40,000 | 120,000 |
| 3. Workshops and stakeholder consultations | Stakeholder consultation report | 50,000 | 20,000 | 70,000 |
| 4. Revisions/finalization of draft studies and preparation of draft Project Appraisal Document | Finalized studies and draft Project Appraisal Document incl. final institutional arrangements, costing of activities, procurement plan, logframe, M&E plan, financial management arrangements (French and English) | 40,000 | 20,000 | 60,000 |
| 5. Concluding Project Preparation Workshop and Finalization of Project Design and Implementation Arrangements | Final PAD incl. relevant annexes (English and French) | 20,000 | 10,000 | 30,000 |
| Total Project Preparation Financing |  | 200,000 | 100,000 | 300,000 |

D.  Financing plan summary for project preparation grant: ($)

|  | Project Preparation | Agency Fee |
| --- | --- | --- |
| GEF financing | 200,000 | 20,000 |
| Co-financing | 100,000 |  |
| Total | 300,000 | 20,000 |

E.  PPG  requested by agency(ies), focal area(s) and country(ies) 1

| GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| World Bank | Biodiversity | Tunisia | 130,000 | 13,000 | 143,000 |
| World Bank | Land Degradation | Tunisia | 70,000 | 7,000 | 77,000 |
| Total PPG Requested |  |  | 200,000 | 20,000 | 220,000 |

F.   PPG Budget Request

| ### Cost Items | ### Total Estimated Person Weeks for GEF Grant (PW) | GEF ($) | ### Co-financing ($) in-kind | ### Total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants * | 45 | 45,000 | 40,000 | 85,000 |
| ### International consultants* | 42 | 105,000 |  | 105,000 |
| Travel |  | 50,000 |  | 50,000 |
| Workshop facilities and translation |  |  | 60,000 | 60,000 |
| Total PPG Budget |  | 200,000 | 100,000 | 300,000 |

* Annex A for Consultant cost details should be prepared first before completing this table.  See notes on Annex A for the 
     required detailed information.  This table is the sum of all local and international consultants presented in Annex A.

G.   GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation.

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Steve Gorman |  | January 14, 2010 | Kanta Kumari Rigaud | 202-473-4269 | kkumari@worldbank.org |

Annex A

Consultants Financed by the Project Preparation Grant (PPG)

| Position / Titles | $/ Person Week1 | Estimated PWs2 | Tasks to be performed |
| --- | --- | --- | --- |
| Local |  |  |  |
| Institutional Specialist | 1,000 | 8 | Collaborate with international consultant on institutional work (Activity 1 and study 2(a) |
| Protected Area Specialist | 1,000 | 8 | Collaborate with international consultant on protected area work [studies 2 (b) and 2 (d)] |
| INRM Specialist | 1,000 | 5 | Collaborate with INRM and SLM and water management work [study 2 (c)] |
| Community Development Specialist with PSD knowledge | 1,000 | 8 | Collaborate on study 2 (e) and facilitate stakeholder consultations |
| Project Design and Management Specialist | 1,000 | 12 | Collaborate with international consultant on project preparation and design |
| Safeguard Specialist | 1,000 | 4 | Collaborate with international consultant on Environmental Management Plan |
| International |  |  |  |
| Institutional Specialist | 2,500 | 8 | Carry out institutional work [Activity 1 and study 2(a)] with local consultant |
| Protected Area Specialist | 2,500 | 8 | Undertake protected area work [Study 2 (b) and 2 (d)] in collaboration with local consultant |
| INRM Specialist | 2,500 | 5 | Undertake INRM and SLM and water management work [study 2 (c)] |
| Community Development Specialist with PSD knowledge | 2,500 | 5 | Undertake study 2 (e) |
| Project Design and Management Specialist; small subcontracts may be needed for procurement plan, FM Plan, etc. | 2,500 | 12 | Prepare project document in collaboration with local consultant |
| Safeguard Specialist | 2,500 | 4 | Prepare Environmental Management Plan in collaboration with local consultant |

1  Provide dollar amount per person week.

2   Provide person weeks needed to carry out the task and corresponds to the dollar amount per person week in the previous column.

Project ID number will be assigned by GEFSEC.  If PIF has already been submitted, please use the same ID number as PIF.