United Nations Development Programme

Country: Viet Nam

PROJECT DOCUMENT

Project Title: Enhancing Capacity for Implementing Rio Conventions

UNDAF Outcome(s): The Project contributes directly to the current United Nations One Plan in Viet Nam. It notably contributes to Outcome 1.4: by 2016, key national and sub-national agencies, in partnership with the private sector and communities, implement and monitor laws, policies and programmes for more efficient use of natural resources and environmental management, and implement commitments under international conventions. More specifically, under Outcome 1.4, the project will directly contribute to the following outputs under the One UN Plan: UN One Plan Output: Output 1.4.2: A set of coherent policies and plans are prepared or updated to strengthen (1) management of protected areas and biodiversity conservation, and (2) environment management at national and community levels.

Executing Entity/Implementing Partner: Institute of Strategy and Policy on Natural Resources and Environment (ISPONRE) of the Ministry of Natural Resources and Environment (MONRE)

Implementing Entity/Responsible Partners: United Nations Development Programme

Brief Description: Viet Nam has taken many measures to protect its natural resources and environment, notably developing its legislative, regulatory and legal framework. The emphasis in the baseline for the coming years is on operationalizing this framework, mostly through the use of dedicated tools/instruments and through building national and provincial implementation capacity. However, in this baseline, most attention is paid to local sustainable development and environmental issues, overlooking important global environmental benefits. This GEF supported project will complement this baseline, providing necessary incremental support to activities in order to mainstream attention global environment factors into the impressive baseline. The National Capacity Self-Assessment set out the barriers to implementing the Rio Conventions and the capacity needs. This project builds directly on the NCSA findings and recommendations, addressing many of the important capacity needs identified therein. Capacity development, notably at the provincial level, will be a key force running through all Outputs in this Project. GEF support, working closely with a range of national, international, governmental and NGO partners, will notably: - Develop a set of indicators for monitoring the Rio Conventions and their implementation; - Develop a methodology for natural resource accounting that is optimally applicable to global environmental factors; - Support activities to develop Environmental Performance Indices; - Support the development of strategic environmental assessment, notably with the use of the indicators from (i); - Support the development of an integrated land-use planning that generates global environmental benefits; - Institutionalize all above outputs by designing and lobbying for a Government formal Decision, as necessary.

Total resources required   		2,579,646USD

Total allocated resources:		2,579,646USD

- Regular

- Other

- GEF			975,000 USD

- UNDP		725,000 USD

- ISPONRE 		440,000 USD

- Other 		179,646 USD

In –kind contributions;

- ISPONRE 		150,000 USD

- Other 		110,000 USD

Programme Period:		2014 -2017

Atlas Award ID:		00079893

Project ID:			00089760

PIMS #				5099

Start date:	2014

End Date:	2017

Management Arrangements:	NIM

PAC Meeting Date: To be conducted after GEF Secretariat approval

Agreed by Ministry of Environment & Natural Resources of Viet Nam (MONRE):

Date/Month/Year

Agreed by UNDP Viet Nam:

Date/Month/Year

Table of Contents

Acronyms and Abbreviations	4

PART I - PROJECT	5

A Project Summary	5

A.1	Project Rationale, Objectives, Outcomes/Outputs, and Activities	5

A.2	Key Indicators	6

B	Country Ownership	7

B.1	Country Eligibility	7

B.2	Country Drivenness	7

B.2.a	National Capacity Self-Assessment	8

B.2.b	Sustainable Development Context	8

B.2.c	Policy and Legislative Context	11

B.2.d	Institutional Context	13

B.2.e	Barriers to Achieving Global Environmental Objectives	16

C.	Programme and policy conformity	18

C.1	GEF Programme Designation and Conformity	18

C.1.a	Guidance from the Rio Conventions	20

C.2  Project Design	21

C.2a The Baseline	21

C.2b The GEF Alternative	22

C.2c Project Objective and Outcomes	23

C.2d Project Outputs and Activities	23

C.3	Sustainability and Replicability	35

C.3.a	Sustainability	35

C.3.b	Replicability and Lessons Learned	36

C.3.c	Risks and Mitigation Measures	37

C.4	Stakeholder Involvement	39

C.5	Monitoring and Evaluation	41

D.	Financing	44

D.1	Financing Plan	44

D.2	Cost Effectiveness	45

D.3	Co-financing	46

E.	Institutional Coordination and Support	46

E.1	Core Commitments and Linkages	46

E.1.a	Linkages to other activities and programmes	46

E.2	Implementation and Execution Arrangements	48

PART II:	ANNEXES	51

Annex 1:	(Draft) Law on Environmental Protection	51

Annex 2: 	List of laws, policies and decisions related to biodiversity, climate change and land degradation, POPS and international waters	51

Annex 3: 	Additional Information on Environmental Indicators	51

Annex 4: 	List of Strategies, Master Plans and Spatial Plans Which Require a Detailed SEA	51

Annex 5:	Capacity Development Scorecard	52

Annex 6:	Logical Framework	53

Annex 7:	Outcome Budget (GEF Contribution and Co-financing)	54

Annex 8:	Provisional Work Plan	55

Annex 9:	Terms of References	56

Annex 10:	Environmental and Social Review Criteria	57

Annex 11:	PDF/PPG Status Report	58

Annex 12:	Standard letter of agreement between UNDP and the Government of Vietnam	59

PART III:	GEF Letters of Endorsement and Co-Financing	60

# Acronyms and Abbreviations

ADB 	Asian Development Bank

APR	Annual Project Reports

CBD 	Convention on Biological Diversity

CCCD 	Cross-Cutting Capacity Development

CGPRS 	Comprehensive Growth and Poverty Reduction Strategy

CO2eq	Is the amount of CO2 that would have an equivalent global warming effect

CRES 	Centre for Natural Resources and Environmental Studies under the Vietnam National University

DARD 	Provincial Department for Agriculture and Rural Development

DONRE 	Provincial Department for natural resources and environment

EPA 	Environmental Performance Assessment

EPI 	Environmental performance indices

GDLM 	General Department of Land Management

GGS 	Green Growth Strategy

GHG	Green House Gas

GiZ	German technical implementing agency

ISPONRE 	Institute of Strategy and Policy on Natural Resources and Environment

LUP 	land-use planning

MARD 	Ministry of Agriculture and Rural Development

MONRE	Ministry of Natural Resources and Environment

NAP 	National Action Plan on land degradation

NBSAP 	National Biodiversity Strategic Action Plan

NCCS 	National Climate Change Strategy

NCSA	Viet Nam’s National Capacity Self-Assessment

NPD 	National Project Director

NPM 	National Project Manager

NRE	Natural resources and environment

NTP 	National Target Programme

NTP-RCC 	National Target Programme to Respond to Climate Change

PCC 	Party Central Committee

PIRs 	Project Implementation Reviews

PMU 	Project Management Unit

POPS 	Persistent Organic Pollutants

PPTA 	Project Preparatory Technical Assistance of the ADB

PSC	Project Steering Committee

RCSI 	Set of Indicators for the Rio Conventions

RCU 	Regional Coordination Unit (of UNDP/GEF)

SEA 	Strategic Environmental Assessment

SEDP	Socio-Economic Development Plans

UNCCD 	The United Nations Convention to Combat Desertification and Drought

UNFCCC 	United Nations Framework Convention on Climate Change

VAF	Viet Nam Administration of Forestry

VEA 	Viet Nam Environment Administration

# PART I - PROJECT

# A Project Summary

## A.1	Project Rationale, Objectives, Outcomes/Outputs, and Activities

- In recent years the Government of Viet Nam has paid great attention to formulating an institutional, policy and legislative framework to protect environmental resources. This includes many institutional, policy and legislative measures that are directly related to the global environment. Allied to this, the Government of Viet Nam has taken steps to mainstream the protection of environmental resources into national, sectoral and regional socio-economic development processes. This has notably been achieved through the development of an EIA process, an SEA process and integrated land-use planning (LUP) processes.

- In the baseline, the above processes will continue and environmental resources will receive increasing protection. The Government is developing dedicated tools to support the implementation of the institutional, policy and legislative framework - including an indicator framework, economic valuation techniques, and environmental performance indicators. The Government is also further developing its approaches to SEA and to LUP.

- The baseline contains several weaknesses. In terms of the Rio Conventions, a weakness in the baseline is the focus on sustainable development and local environmental protection. The global environment – biodiversity, climate change and land degradation – will not be adequately accounted for. To overcome this weakness, GEF support will be used to mainstream biodiversity, climate change and land degradation into the baseline initiatives.

- Two Outcomes will be delivered:

Outcome 1: Viet Nam has environmental management tools that fully address global environment concerns.

- Output 1.1A set of indicators to monitor environmental status and pressure developed.Building on baseline initiatives to develop systems of indicators to monitor environmental status and pressure, GEF supportwill ensure that there are indicators covering biodiversity, climate change and land degradation. These will cover status, trends, threats and performance. This will be based on best practices from across the region and internationally. The project will support analysis, training, developing methods for researchers and testing indicators - possibly through modeling.

- Output 1.2Economicvaluation of environmental and natural resources, and capacity to undertake this valuation.Building on baseline initiatives to develop capacity for economic valuation of environmental and natural resources, GEF support will ensure that economic valuation of biodiversity, biodiversity loss, climate change mitigation, climate change adaptation and land degradation can be undertaken. The project will support determining best practices from across the region and it will support training and developing methods for Viet Nam, thereby helping build core capacity for economic valuation.

- Output 1.3 Environmental performance indices (EPI) developed and monitored, in line with international standards. Building on the baseline to develop an EPI, GEF support will ensure that the EPI fully integrates biodiversity, climate change and land degradation. This will involve analysis, training, developing protocols and coefficients, and on-line databases. It will also involve developing the communication tools to disseminate the EPI. This Output is mostly covered by co-financing from UNDP.

- Once developed and implemented, Output 1.1, 1.2 and 1.3 will serve as permanent tools for future environmental monitoring and management in Viet Nam. They will also feed into the Outputs under Outcome 2.

Outcome 2: Viet Nam is integrating global enviroment concerns into its national strategic planning and development processes.

- Output 2.1 Increased capacity to undertake Strategic Environmental Assessment (SEA) at provincial level. Viet Nam, with support from international partners, has already taken major steps to operationalize and institutionalize an SEA process and to develop the capacity required to implement SEA. Building on this, GEF support will develop capacity at provincial level to further ensure these processes account for the global environment. Provincial case studies will be developed and the case studies will involve an analysis of the present procedures, and the determination of entry points for biodiversity, climate change mitigation, climate change adaptation, and land degradations at provincial authorities. It will most notably involve the use of the tools from Outcome 1- especially the indicator system – to strengthen the SEA process. This will enable a quantitative assessment of the impacts on the global environment of Strategies and key Plans at provincial level. The findings and experiences from the provincial case studies will be and shared with leading national authorities and stakeholders working with SEA.

- Output 2.2Increased capacity to undertake integrated land-use planning (LUP).GEF support will develop capacity and tools to integrate global environment and global environment benefits into the ongoing strengthening of integrated land-use planning in Viet Nam. This integration will involve an analysis of the present procedures, the determination of entry points, and training for key personnel on the use of the tools from Outcome 1. It will also support the first steps in the process to introduce ecological function zones.

- Output 2.3 Formal institutionalized commitment in the form of a Government Decision to SEA and integrated land-use planning. This Output is the formal institutionalization of Outputs 1.1 – 2.2. It ensures that each of the five previous Outputs are enshrined into the Vietnamese legal and regulatory framework.

## A.2	Key Indicators, Assumptions and Risks

- The following table summarizes the indicators to be used to manage and monitor the Project. Full details of the baseline values, the end-of-project targets and the sources of the data are provided in the Logical Framework in Annex 6.

| Objective/outcome | Indicator | Risks/Assumption |
| --- | --- | --- |
| Objective: To enhance the capacity for implementing the Rio Conventions by developing and applying tools that will lead to global environmental benefits. | 1. Government Decision on integrating a set of indicators for the Rio Conventions (RCSI) into SEA and land-use planning process. |  |
|  | 2. Capacity Development Scorecard. |  |
|  | 3. Effectiveness of coordination/collaboration amongst three Rio focal points on data collection, reporting and monitoring. |  |
| Outcome 1: Vietnam has the environmental management tools that fully address global environmental concerns. | 1.1Set of indicators covering the Rio Conventions (RCSI). |  |
|  | 1.2 Number of successful government run training courses on use of the indicators. |  |
|  | 1.3 Number of provincial professional gaining knowledge on how to conduct economic valuation of natural resources. |  |
|  | 1.4 Number of provincial level professionals successfully trained on the use of EPI. |  |
| Outcome 2: Vietnam is integrating global environmental concerns into its national strategic planning and development processes. | 2.1 Guidelines to integrate RCSI into the official SEA process at provincial level |  |
|  | 2.2 Number of trained provincial level professionals on the use the Guidelines to integrate RCSI into the official SEA process. |  |
|  | 2.3 Guidelines to integrate RCSI into the official land-use planning process. |  |
|  | 2.4 Number of trained professionals on the use the Guidelines to integrate RCSI into the official land-use planning process. |  |

- There is a series of risks and assumptions associate with each Objective and Output. The key ones are summarized in the following table

| Product | Risk |
| --- | --- |
| Objective |  |
| Output 1.1 | There may be gaps on the availability and quality of information; Basic capacity may be low in some provinces. |
| Output 1.2 | Availability of adequate data/information (quality and quantity). |
| Output 1.3 | There is a risk that the work supported through the co-financed projects will face delays. |
| Output 2.1 | The knowledge of the staff, especially at provincial level, is too limited to apply the Guidelines. |
| Output 2.2 | Complications may arise when applying the tools in diverse local conditions |
| Output 2.3 | The time required to promote and approve legislation may be too long to be completed within the time frame of the project. |

# B	Country Ownership

## B.1	Country Eligibility

- Viet Nam is eligible to receive technical assistance from UNDP, and is thus eligible for support under the Global Environment Facility (GEF). Viet Nam ratified the Convention on Biological Diversity (CBD) in November 1994,theUnited Nations Convention to Combat Desertification and Drought (UNCCD) in August 1998 and the United Nations Framework Convention on Climate Change(UNFCCC) in November 1994. Viet Nam also ratified important protocols under the Rio Conventions in later years, namely:

- Stockholm Convention on Persistent Organic Pollutants (POPS) in July 2002;

- The Cartagena Protocol on Biological Safety (acceded in January 2004) to protect biodiversity from the potential risks posed by genetically modified organisms that are the product of biotechnology; and

- The Kyoto Protocol in September 2002, committing to stabilize greenhouse gas emissions for the period 2008-2012 at the 1990 level.

- Fit with the GEF-5 CCCD Strategy:  This project has been conceived and designed to contribute to the GEF Cross-Cutting Capacity Development (CCCD) Strategy.

- This project will contribute to the second CCCD objective (CCCD 2), “generate, access and use of information and knowledge”. It will do this by developing environmental management tools that generate information and knowledge on the state of the environment, on the economic value of the environment, and on the performance to manage and improve the environment.

- This project will also contribute to the third CCCD objective (CCCD 3), “strengthened capacities for policy, and legislation development for achieving global benefits”. It will do this by developing mechanisms to integrate global environmental concerns into decision-making. It will develop SEA and land-use planning, so that these mechanisms play an important role in protecting the global environment during Viet Nam’s socio-economic development.

## B.2	Country Drivenness

- The Project is designed to support implementation of many key recent strategic policy developments in Viet Nam, of which the most notable are:

- The National Action Plan on land degradation (NAP), 2006. This Plan emphasizes the need to strengthen the legal framework on natural resources and sustainable management. It also addresses the need for a monitoring and evaluation network of the desertification process; and the need to build up criteria, indicators and methodologies to assess land degradation;

- Law on Biodiversity, 2008. This sets out the need for a National Master Plan for Biodiversity Conservation;

- The National Strategy on Biodiversity to 2020, vision to 2030 (Decision 1250/QD-TTg of the Prime Minister, July 2013);

- Vietnam Sustainable Development Strategy 2011-2020. This outline the strategies and approaches to achieving sustainability during the current decade;

- National Target Programme to Respond to Climate Change (NTP-RCC, 2008). This outlines the measures to respond to climate change for all sectors/areas and localities and maps out the approach to respond;

- The National Climate Change Strategy (NCCS), 2011. Amongst many other approaches, this includes the need for a monitoring network for climate related parameters as a strategic task; and

- The Green Growth Strategy (GGS), 2012, includes a number of related objectives, especially on enriching natural capital, and greening existing economic sectors for sustainable development and environmental management.

- The Project also contributes directly to the current One United Nations Plan in Vietnam. It notably contributes to Outcome 1.4: by 2016, key national and sub-national agencies, in partnership with the private sector and communities, implement and monitor laws, policies and programmes for more efficient use of natural resources and environmental management, and implement commitments under international conventions.

- More specifically, under Outcome 1.4, the project will directly contribute to the following outputs under the One UN Plan:

- Output 1.4.2:  A set of coherent policies and plans are prepared or updated to strengthen (1) management of protected areas and biodiversity conservation, and (2) environment management at national and community levels.

### B.2.a	National Capacity Self-Assessment

- This project builds on the Viet Nam’s National Capacity Self-Assessment (NCSA), completed in 2006. The NCSA identified 18 capacity needs. This project will make a direct contribution to meeting six of those needs, as follows:

- Develop, pilot and disseminate the models of economic development taking into account environmental protection activities;

- Integrate environmental issues and requirements(such as climate change, biodiversity conservation and prevention of land degradation) into the master plans and programmes to develop the national economy, at the same time, improving technology and technical abilities for implementing the programmes;

- Develop skills for policy planners and policy analyzers;

- Develop monitoring and evaluation plans for the performance of three Conventions;

- Develop the system of environmental indicators for reports of environmental state and systematizing them by providing guidance on the implementation thereof from central to local levels; and,

- Enhance capacity for related stakeholder on monitoring and performance evaluation.

- Several of the capacity needs identified in the NCSA have already been addressed and met by the Government of Viet Nam and other partners, including through some GEF projects, since 2006.  However, the approach of those initiatives was often sectoral and did not fully address the cross-cutting nature of climate change, biodiversity and land degradation. An interrelated and cross-cutting approach is vital to efficiently meet obligations under the three Rio Conventions in Viet Nam.

### B.2.b	Sustainable Development Context

- Viet Nam is located in Southeast Asia and borders the Gulf of Thailand, the Gulf of Tonkin, and the South China Sea. It has land borders with Cambodia, China and Laos. The geography consists mainly of hills and forested mountains in the northwest. Flat land is mostly restricted to the two large river deltas (i.e. the Red River in the North and the Mekong River in the South). The latest official census (2009) recorded the population of Viet Nam to be approximately 85.8 million, having grown quickly from an estimated 52.7 million in 1979. In 2009, the majority ethnic group, the Kinh, constituted nearly 73.6 million people, or 85.8% of the population. Viet Nam is also home to 54 ethnic minority groups, for example the Hmong, Dao, Tay, Thai, and Nùng.

- Because of the range of latitude from north to south Viet Nam, and because of the marked topographical relief, the climate tends to vary considerably from place to place. The average annual temperature is generally higher in the plains than in the mountains, and higher in the south than in the north. Temperatures vary less in the southern plains around Ho Chi Minh City and the Mekong Delta, ranging between 21 and 28 °C (69.8 and 82.4 °F) over the course of the year. Seasonal variations in the mountains and plateaus and in the north are much more dramatic, with temperatures varying from 5 °C (41.0 °F) in December and January to 37 °C (98.6 °F) in July and August.

- Viet Nam is considered one of the five countries the most vulnerable to the adverse effects of climate change. Viet Nam already suffers from typhoons, floods, droughts, landslides, etc, and climate change threatens to exacerbate these, with the potential for extensive economic damage and loss of life, affecting coastal, mountainous and urban areas.

- Since the adoption of market-oriented reforms almost two decades ago, and the opening of its economy to international trade, Viet Nam has taken great strides to overcoming economic and human poverty. It is now well on its way to achieving middle-income status. For example, the national poverty rate declined from 58% in 1993 to 16% in 2008, and rural poverty declined from 64% to 20% over the same period. Yet, despite these overall achievements in overcoming poverty, poverty remains persistently entrenched in some areas: rural areas have far more poverty than urban areas; and areas with a large ethnic minority population often have high poverty levels

- Vietnam’s efforts to overcome these socio-economic challenges are focused on the implementation of national policies and plans, notably the Comprehensive Growth and Poverty Reduction Strategy (CGPRS) and the five-yearly Five Year Socio-Economic Development Plans (SEDP). Notably, both the previous SEDP and the present SEDP focus on poverty reduction.

Global Environment

- Biodiversity: Viet Nam stretches over 1,650 km from North to South. 75% of the country’s 331,688 km2 of land is mountainous. There are two large deltas formed by two major rivers - the Red River in the North and Mekong River in the South. Viet Nam’s marine territory is more than three times larger than its land area. Due to its geographical position, its climate and the variety of its terrain, Viet Nam has high levels of biodiversity, with many diverse ecosystems, species and genetic resources.

- Ecosystem diversity. There are many different kinds of ecosystem in Viet Nam including inland ecosystems, wetland ecosystems and marine ecosystems. The diverse types of inland ecosystems include forest, mountain, limestone, and hill ecosystems. There are many wetland ecosystems - based on the Ramsar classification system there are 30 types of natural wetlands in Viet Nam of which 11 are coastal and 19 are inland. The coastal tidal wetlands, wetland forest (mangrove), salty or brackish water lagoons, and peat lands are considered to have the highest diversity, as well as to be of international importance. With over 3,300 km of coastline and a marine economic zone of over 1 million km2, including over 3,000 large and small islands, Viet Nam’s marine ecosystems are particularly rich.

- Species Diversity. Viet Nam has a recorded 11,458 species of fauna, 21,017 species of flora, and about 3,000 species of micro-organisms. Viet Nam is ranked fourth globally in terms of number of primate species and hosts four of the 25 most endangered primate species in the world. In recent years, many new species of fauna and flora have been scientifically observed for the first time in Viet Nam. This includes: five new species of mammal, and, for flora: two new families, 19 branches, and over 70 new species.

- Genetic diversity. Viet Nam is one of 12 global centers of domesticated plant diversity and is also a well-known centre of animal domestication. The main crop plants include 802 species from 81 families that are being cultivated throughout the country, of which 41 species provide starch and 95 species are used for food. For example, there are 20 varieties of swine, of which 14 are domesticated. There are 27 varieties of fowl, of which 16 are domesticated. There are 14 main species of cattle among the many domesticated animals.

- Threats to biodiversity in Viet Nam include population growth and consequent consumption growth, overexploitation of natural resources, characterized by illegal exploitation of timber and non-forest timber products, unsustainable fishing and illegal wildlife hunting and trade. Other threats include changes in land use, characterized by massive infrastructure development, extension of land for agricultural and industrial plantations, introduction of alien species and climate change. Land use changes have reduced natural areas, increased ecological fragmentation and damaged wildlife habitats. Agricultural land increased from 6.7 million hectares in 1990 to 9.4 million hectares in 2002. Illegal logging remains a key issue, with all forest types being targeted. Road construction for transporting wood has in fact facilitated hunting and the exploitation of non-forest timber products, placing additional pressures on wildlife populations.

- Regarding freshwater ecosystems, overexploitation and mega infrastructure projects (e.g. construction of dams for irrigation and hydropower) have led to the loss of habitats of many aquatic species and to dysfunctional ecological processes in lagoons, resulting in changes in water circulation and facilitating saltwater intrusion into rivers. Most of the marine ecosystems are degrading seriously as a result of severe pollution from waste and oil spills. An increase in consumption, together with unsustainable fisheries management, has led to the overexploitation of aquatic products in many regions. Destructive fishing techniques, such as the use of explosives, poison and electricity, are commonly used in both inland and coastal areas, and considered a severe threat to more than 80% of Vietnam’s coral reefs.

- Land degradation. There is more than two million hectares of degraded land scattered all over Viet Nam - mainly in the northern mountainous areas. In addition, there may be as many as seven million hectares of barren land – that is former forest land that has been cleared and with very limited re-growth. In general, soil fertility has declined seriously over large areas. The natural forests have been seriously depleted. The main periods of deforestation were during 1960-1970 and 1976-1990. In recent years, forest coverage has been increasing.

- The first national report of Viet Nam to the UNCCD reports that Viet Nam has several long and narrow deserts. These yellow and white sand areas are located along the central coastal areas (400,000 ha) and in the Cuu Long River Delta (43,000 ha). A significant desertification has been ongoing in Viet Nam since the 1960’s. Every year, 10-20 ha of agricultural land is lost due to encroachment by sand dunes. Likewise, land cracking and soil erosion have become more and more serious in the Cuu Long river delta - a survey recorded 51 cracking points, with 350 ha of land lost every year.  The report estimated that the total land lost by cracking and erosion would ultimately reach 10,000 ha.

- Finally, ground water has deteriorated in quantity as well as in quality, for example due to water exploitation for coffee production in the Central Highlands and pollution by the chemicals industry. It is forecast that lack of water will become a serious problem in the next decade. Droughts have been more frequent and more intense during recent years, throughout the whole country but especially in the central region.

- Greenhouse gas emissions and climate change. Viet Nam is considered one of the countries the most vulnerable to climate change, in particular in its coastal and northern mountainous regions. This is in part due to the predicted increases in natural disasters. Notably, if the sea level were to rise one meter (which it is forecasted to do by 2100), 37.8% of the land in the Mekong River Delta will be under sea water, and around 20 million people will be affected.

- Viet Nam also emits GHG and therefore contributes to the global warming. However, as a developing country, Viet Nam’s total GHG emissions remain rather low. The total GHG emissions in 2000 are estimated at 150,899.7 thousand tons of CO2eq. In Viet Nam, in 2000, the agricultural sector was the largest emission source, followed by energy (see Table below).

Table: GHG Emissions in Viet Nam (2000)

| Sector | CO2 | CH4 | N20 | CO2eq | %age |
| --- | --- | --- | --- | --- | --- |
| Energy | 45,900.00 | 308 | 1.27 | 52,773.46 | 35.0 |
| Industrial processes | 10,005.72 | 0 | 0 | 10,005.72 | 6.6 |
| Agriculture | 0 | 2,383 | 48.49 | 65,090.65 | 43.1 |
| LULUCF | 11.860.19 | 140.33 | 0.96 | 15,104.72 | 10.0 |
| Waste | 0 | 331.48 | 3.11 | 7,925.18 | 5.3 |
| Total | 67,765.01 | 3,164.12 | 53.83 | 150,889.73 | 100 |

- However, Viet Nam’s economic growth and industrialization suggest GHG emissions could have grown rapidly since 2000 and could continue to grow rapidly in the near future. According to the Second National Communication, emissions were forecasted to rise to 169.2 million CO2eq by 2010 (a rise of 12% in one decade, by when the energy sector was expected to be the largest source), and to 300.4 million CO2eq by 2020, and to 515.8 million CO2eq in 2030.

### B.2.c	Policy and Legislative Context

- Viet Nam has issued a comprehensive set of policies, programmes, laws and decisions in recent years related to sustainable development and environmental protection. Some of the more important of these include:

- National Strategy on Environmental Protection until 2020 and Vision to 2030 (2012);

- The Strategic Orientation for Sustainable Development in Viet Nam (Viet Nam Agenda 21) (2004) and the Strategy on Sustainable Development in Viet Nam – Period (2011 – 2020);

- The Environmental Protection Law (2005); and,

- The Five-year Plans for the Natural Resources and Environment Sector (issued every five years).

- These instruments establish the overall aims and approaches to environmental protection. They provide a guidance framework for sectoral instruments and for actions in all sectors and sub-sectors. In addition, a series of key specific initiatives related to biodiversity, climate change and land degradation has been issues, and is listed below:

Biodiversity

- Viet Nam ratified the Convention on Biological Diversity (CBD) in 1993 and the Cartagena Protocol on Bio-safety in 2004. Biodiversity protection is one of the top priorities of the Vietnamese Government and the Government’s policies on biodiversity are quite comprehensive. Some of the main legislative and administrative steps taken are:

- Decision on the Management of the Viet Nam Protected Area System to 2010 (issued in 2003);

- Decree on Conservation and Sustainable Utilization of Wetlands (2003);

- Decision on the National Action Plan on Improvement of Control on Wildlife Trade to 2010 (2004);

- Forest Protection and Development Law (2004);

- The National Action Plan on Biodiversity up to 2010 and orientations towards 2020 (2007);

- The Biodiversity Law (2008) and the National Strategy on Biodiversity to 2020, vision to 2030 (2013);and,

- The Land Law (2003) with modification of Article 126 on Residential land in (2009).

Climate Change

- Viet Nam ratified the UN Framework Convention on Climate Change (UNFCCC) in 1994. Since, a large range of legislative and administrative measures that are relevant to climate change have been issued - mostly relevant to reducing the emissions of GHGs. The National Strategy for environmental protection until 2010 and vision toward 2020 (issued in 2003) emphasizes the use of clean energy as one of the measures to reduce emissions and pollution. The objectives of this strategy include increasing the rate of clean energy use to 5% of total energy consumption by 2010. Furthermore, the Environmental Protection Law (2005) promotes the development of clean energy, renewable energy and environment-friendly products. According to this law, clean energy and renewable energy are to be exploited from wind, solar, geothermal sources, water, biomass and other renewable sources.

- More recently, the National Target Programme to Respond to Climate Change (NTP-RCC, 2008) and the National Climate Change Strategy (NCCS, 2011) both provide important measures to respond to climate change. The former outlines the measures to respond to climate change for sectors/areas and localities and maps out the approach to respond. The latter addresses the need for a monitoring network for climate related parameters as a strategic task.

- Most specific legislation relevant to climate change focuses on the sectors that produce GHG emissions, such as energy, agriculture and forestry. In most cases, despite the fact that these laws will have major impact on emissions, there are few references to climate change or to GHG. The focus is on increasing efficiency in the sector, contributing to development of the economy and promoting investments. Some of the more important include: National Strategy for development of electricity sector in period 2004-2010 and vision toward to 2020; The National Strategy for Energy Development until 2020 and vision toward 2050; and, The Electricity Law (2004).

- Viet Nam submitted its First National Communication to the UNFCCC in 2003 and the Second National Communication in 2010.

Land Degradation

- Viet Nam ratified the United Nations Convention to Combat Desertification (UNCCD) in 1998. The Viet Nam’s National Action Plan (NAP) to combat desertification was approved in 2006. It identified a number of short, medium and longer-term actions for addressing land degradation. The NAP also identified four priority geographical areas, and three priority programs.

- Viet Nam has developed a broad array of legal and administrative measures to oversee land-use and land-management, many of which are related to agriculture or forestry. Two of the key legal implementation instruments are: The Land Law (2003) and the Forest Protection and Development Law (2004).

- A complete list of laws, policies and decisions related to biodiversity, climate change and land degradation, POPS and international waters is provided in Annex 2.

- The following ongoing legislative initiatives are also very pertinent to the implementation of the Rio Conventions and to this present project.

- Communist Central Party Resolution Number 24-NQ/TW, Active Response to Climate Change and Improving the Management of Natural Resources and Environmental Protection (June 2013). This Resolution provides clear guidance on the need to protect the environment, giving renewed impetus to all efforts and all tools supporting sustainable development. The Ministry of Natural Resources and Environment (MONRE) is currently preparing the detailed implementation plan for this resolution;

- Draft “Law on Environmental Protection” - currently under review by the National Assembly. This Law is a major amendment of the 2005 Law. The latest draft of this law has a section on the importance and approach to environmental indicators. It also has an entire chapter devoted to strategic environmental assessment and environmental impact assessment;

- Draft “Law on the Land” - currently under review by the National Assembly. This Law will provide a comprehensive overview of the previous Land Law (2005). This Law has sections on the importance and approach to land-use planning.

### B.2.d	Institutional Context

Key Government Agencies

- The lead agency in the implementation of the Rio Conventions is the Ministry of Natural Resource and Environment (MONRE). MONRE takes the lead in all issues related to environmental protection, and takes a lead coordinating role in all issues related to sustainable development. MONRE includes the following departments and institutes:

- Institute of Strategy and Policy on Natural Resources and Environment (ISPONRE);

- Department of Meteorology, Hydrology, and Climate Change (UNFCCC focal point);

- Viet Nam Environment Administration (VEA). The VEA also includes the Biodiversity Conservation Agency, which is the CBD focal point, and;

- General Department of Land Management (GDLM).

- MONRE has a strong role to play in addressing climate change issues across all sectors. MONRE is the standing Vice Chair of the National Steering Committee for the National Target Programme to Respond to Climate Change (NTP-RCC), and is Chair of the Executive Board of NTP-RCC, and hosts the office of the Standing Office of the NTP-RCC.

- ISPONRE was established by the Prime Minister under MONRE as the advisory body on legal, policy and strategy issues. ISPONRE’s primary functions relate to:

- Providing long term planning for sustainable solutions that balance socio-economic development and environmental protection;

- Proposing and developing strategies and policies within the areas of MONRE’s mandate;

- Conducting economic analysis of, and strategic planning for, natural resources management; and

- Evaluating and assessing international natural resource and environmental management strategies and their adaptability to the Vietnamese context, and advancing adjusted and innovative strategies.

- The Ministry of Agriculture and Rural Development (MARD) is the government agency performing state management functions in the fields of agriculture, forestry, salt production, fishery, irrigation/water services and rural development nationwide, including state management functions with regard to delivery of public service in accordance with legal documents. MARD has the responsibility for the adaptation of the agricultural sector and rural areas to climate change. MARD is also the focal point for the UNCCD.

- Governance and administration in Viet Nam is through a matrix of decision-making and technical support agencies. This consists of economic and regulatory sectors on the one hand (Ministries, central committees, etc) and local government agencies (province, district, etc) on the other hand. In general, each line ministry has a department responsible for science, technology and environment, which has responsibilities related to environmental protection and climate change in the concerned sector.

Local Government

- There is a total of 63 provinces in Vietnam. The provinces are divided into districts, provincial cities and county-level towns, which are further sub-divided into commune-level towns or communes. The municipalities are divided into rural districts and urban districts, which are subdivided into wards.

- The national government agencies (including ministries such as MONRE and MARD) are represented at provincial and district and lower levels by departments or sub-departments. Each Province has a Department for natural resources and environment (DONRE), which has responsibilities related to environmental protection and climate change adaptation in the province, and a Department for Agriculture and Rural Development (DARD). However, Vietnamese provinces (and districts) are under the supervision of provincial (district) People's Council, which are elected by the inhabitants. The People's Council appoints a People's Committee, which acts as the executive arm of the provincial (district) government. Provincial governments are expected to be subordinate to the central government, but in many ways exhibit autonomy on some decision-making and fiscal issues.

- With respect to environmental protection, the provincial and district DONRE are responsible for supervising, advising and monitoring environment in their concerned jurisdiction.

Coordination Mechanisms

- The National Council on Sustainable Development was established by the Prime Minister’s in September 2005. In 2009, the Prime Minister adjusted the functions, tasks and organizational structure of this Council. The Council advises the Prime Minister, and helps the Prime Minister guide the nationwide implementation of the Strategic Orientation for Sustainable Development, and to monitor and assess the implementation of sustainable development objectives in Viet Nam in line with the Strategic Orientation for Sustainable Development.

- The National Council on Sustainable Development is chaired by a Deputy Prime Minister and is composed of 30 members who represent National Assembly Government bodies, Ministries, Agencies, social and professional organizations, businesses, and the mass media.

- Cross-sectoral committees have been established for each of the three Rio Conventions (CBD, UNFCCC and UNCCD). Notably, the National Council on Climate Change was established by the Prime Minister in 2012. This is chaired by Prime Minister, and the Minister of MONRE is one of the vice-Chairs.

Participation

- In Viet Nam, Civil society organizations’ participation in sustainable development is mobilized through the following forms:

- They are expected to formulate, innovate and implement institutions and policies so as to further promote people’s initiatives and ownership. Civil society organizations play an extremely important role in ensuring sustainability in economic and social development and environmental protection in each and every locality.

- They disseminate information, they educate and raise awareness for the people on sustainable development through civil society organizations and community activities. They provide community-based education on the protection of natural resources and the environment through, for example, the formulation of a village code of conduct and launching of knowledge contests and campaign-like activities. These have proved to be a very effective in reality.

- They launch mass movements covering sustainable development contents through individual social groups, localities and at the national scale, with a view to generating more employment, developing production, reducing poverty, maintaining a good living environment, protecting the local natural resources and environment, and raising awareness of the population on issues relating to sustainable development.

- They support and facilitate civil society organizations and residential communities in all aspects in order for them to succeed in achieving objectives set for movements aimed at sustainable development.

- They forge typical examples in sustainable development communities, in systems of self-governance over natural resources and environmental protection, and replicate such examples.

- In Viet Nam, civil society organizations include socio-political organizations, socio-professional organizations, and non-governmental organizations. These include major social groupings such as trade unions (e.g. the Viet Nam Confederation of Labor), ‘Front’ organization (the Central Committee of the Viet Nam Fatherland Front), women organizations (the Viet Nam Women’s Union), young people (the Ho Chi Minh Communist Youth Union, the Ho Chi Minh Vanguard Pioneers Union), farmers (the Viet Nam Farmer’s Union); people of ethnic minorities (the Committee on Ethnic Minorities), intelligentsia (the Viet Nam Union of Science and Technology Association) and non-governmental organizations (NGO). All have been involved in sustainable development activities according to their respective competence, structure, features and advantages. In Viet Nam, enjoying extensive development, close-knit structures and rich experience, these organizations operate to unite the population and mobilize the latter’s participation. Each social grouping has its own organization through which the activities of individual members are coordinated to become broad-based movements. Mobilization of all-people participation represents an important factor determining the success of Vietnam’s process to sustainable development.

- The key governmental and certain non-governmental agencies, and their roles related to this project, are listed in the Table. (See section C4 for a table displaying the role of the agencies in this proposed project).

Table: Summary of Key Players and Roles in Environmental Management

| Organization | Role |
| --- | --- |
| Ministry of Natural Resources and Environment (MONRE) | Environmental protection and implementation of multi-lateral environmental agreements. Focal point for CBD, UNFCCC and GEF |
| Institute of Strategy and Policy on Natural Resources and Environment (ISPONRE). ISPONRE is an agency under MONRE | Strategy and policy analysis and development for MONRE. |
| Ministry of Agriculture and Rural Development | Sustainable development of agriculture. Adapting agriculture to climate change. Focal point for UNCCD. |
| Ministry of Foreign Affairs | Coordination with regards to reporting on and implementing international agreements. |
| Ministry of Planning and Investment | Coordinating the implementation of government plans and programmes across ministries and down through the levels of government. |
| Ministry of Finance | Coordinating the preparation and execution of the national budget. Key role in fiscal issues and national accounting. |
| Viet Nam Environment Administration | Provide technical support to environmental protection. |
| Viet Nam Forestry Administration | Provide technical support to sustainable forest development. |
| Meteorology, Hydrology and Climate Change Department | Provide technical support on many issues related to climate change and climate change adaptation. |
| Academic or Research Institutes |  |
| National Economic University | Provide technical support on a wide range of issues. |
| Centre for Natural Resources and Environmental Studies under the Vietnam National University (CRES) | To conduct multi- and inter-disciplinary research on biodiversity and environmental issues for decision making and sustainable development; To promote human resources development through formal education, training courses, workshops and seminars for professionals, administrative managers, decision makers and the public; To provide advice, support and services in related areas; To promote networking, partnership and linkages through enhanced cooperation among VNU’s related institutions as well as with other national and international institutions and communities. |
| Other |  |
| WWF | WWF Vietnam is part of the WWF Greater Mekong Programme, which works on environmental and conservation issues across Thailand, Cambodia, Lao PDR and Vietnam. WWF Vietnam finances and technical supports a range of national and local projects related to environmental protection. |
| CSOs in Viet Nam | Financing and technical supporting a range of national and local projects related to environmental protection. |

- Currently, the coordination arrangements across the three Rio Conventions are not fully effective. There are no strong effective mechanisms to ensure coordination and collaboration across implementation of the three Rio Conventions. Collaboration does exist frequently, typically amongst colleagues and departments, but there are no formalized, multi-sectoral mechanisms.

### B.2.e	Barriers to Achieving Global Environmental Objectives

- The main barriers identified during the NCSA process are listed in the Table.

Table: Capacity Barriers to Protecting the Global Environment

| Capacity Development Operational Principle | Project Conformity |
| --- | --- |
| Ensure national ownership and leadership | The project is designed to support and improve ongoing national initiatives. Decision-making lies in MONRE and ISPONRE. Design was led by MONRE and ISPONRE. A cross-sectoral and multi-agency project support mechanism is to be established. |
| Ensure multi-stakeholder consultations and decision-making | Several rounds of consultations have been held during project development. The multi-stakeholder mechanisms that exist for the three Rio Conventions will be actively consulted during project implementation. |
| Base capacity building efforts in self-needs assessment | The project design draws fully from the NCSA and the findings/recommendations of the NCSA. It is also based on further design work related to capacity assessments. |
| Adopt a holistic approach to capacity building | The project addresses individual, institutional and systemic levels of capacity, based on NCSA, and full involvement of all stakeholders. |
| Integrate capacity building in wider sustainable development efforts | The project is fully aligned to support MONRE in ongoing initiatives. Notably it is responsive to recent policy and legislative developments (e.g. the Communist party resolution 24-NQ/TW, and the (draft) revised LEP) |
| Promote partnerships | The project is designed to develop operational partnerships across partners in the three Rio Conventions, and to promote partnerships between governmental and non-governmental (institutes, private sector and NGO) partners and at different levels. |
| Accommodate the dynamic nature of capacity building | The project recognizes the dynamic and evolving process in Viet Nam to implement Rio Conventions. Notably, the baseline has evolved significantly since the NCSA was completed. The project is designed to adapt to recent policy and legislative developments |
| Adopt a learning-by-doing approach | The Project Management Unit (PMU – see later) will emphasize participatory monitoring and learning by doing. One PMU staff member will be assigned these tasks as part of her/his ToR. |
| Combine programmatic and project-based approaches | This is a project contributing to several broader initiatives implemented by MONRE and other partners. MONRE will use the project inputs to strengthen its overall approach to environmental management. For example, IPSONRE is currently implementing initiatives supported by World Bank, ADB, GiZ and UNDP. This project takes place integrally within ISPONRE’s overall programme. This is a good example of how specific international collaboration can make a difference to national initiatives. |
| Combine process as well as product-based approaches | The project is designed to support processes – it will support existing, long-term processes to develop indicators, to build valuation techniques, and to establish SEA and integrated LUP. These processes are firmly implanted in the Vietnamese context. However, the project will also lead to concrete products (i.e. lists of indicators, new techniques, guidelines, trained staff, etc). |
| Promote regional approaches | Lessons will be shared with other countries in southeast Asia. Through the UNDP network, lessons from other countries on capacity development will also be introduced into this Viet Nam project. |

- Since the NCSA was completed in 2006, and as can be seen in earlier sections of this document, Viet Nam has continued the process to establishing a comprehensive policy, institutional and legal framework for achieving environmental goals and generating global environmental benefits. Viet Nam has also moved to remove some of the barriers and key capacity weaknesses listed in the above table.

- The feasibility and needs assessment undertaken in the design/preparation of this project document identified three key areas restricting implementation of the Rio Conventions.

- Lack of instruments for the complete implementation of policies – and in particular to ensure that they fully cover the issues covered by the Rio Conventions. The array of laws, policies and plans is considered adequate, and the individual laws are each considered appropriate. However, implementation of the laws and policies requires a series of practical tools and instruments. Experience shows that these tools could include good environmental indicator systems, environmental performance indices, economic valuation, strategic environmental assessment and integrated land-use planning. Whereas Viet Nam has made progress on developing each of these tools, they are not yet ready for full application (more details are provided below in section C2). More focused work is needed to develop these and to adapt them to the Vietnamese context.

- Weak local capacity. Once the appropriate implementation instruments have been developed and adapted to the Vietnamese context, capacity will be needed by the individuals and departments responsible for their use. This exists already at national level and in some provinces, however this is lacking in most provinces.

- Coordination. In order to achieve synergies and increase effectiveness, experience from other countries shows that a strong and regular coordination and collaboration across the three Convention implementation structures is necessary, including with and across the three focal points. Currently, in Viet Nam, as in many countries, despite a commitment to coordination, this has not yet been operationalized, and the required constructive mechanisms have not yet been created.

# C.	Programme and policy conformity

## C.1	GEF Programme Designation and Conformity

- This project has been conceived and designed to contribute to the GEF Cross-Cutting Capacity Development (CCCD) Strategy.

- This project will contribute to the second CCCD objective (CCCD 2), “generate, access and use of information and knowledge”. It will do this by developing environmental management tools that generate information and knowledge on the state of the environment, on the economic value of the environment, and on performance to manage and improve the environment.

- This project will also contribute to the third CCCD objective (CCCD 3), “strengthened capacities for policy, and legislation development for achieving global benefits”. It will do this by developing mechanisms to integrate global environmental concerns into decision-making. It will contribute to further strengthening of the SEA and land-use planning processes at provincial level in Viet Nam, so that these mechanisms play an important role in protecting the global environment during Viet Nam’s socio-economic development.

- The following table illustrates how this project contributes to implementation of the CCCD Strategy.

Table: Project Alignment to CCCD Strategies

| CCCD Strategy Outcome/Output | Pertinent Project Output | Contribution |
| --- | --- | --- |
| CD2: Generate, access and use of information and knowledge; |  |  |
| 2.1 Institutions and stakeholders have skills and knowledge to research, acquire and apply information collective actions | 1.1 A set of indicators to monitor environmental status and pressure; 1.2 Economic valuation of environmental and natural resources; 1.3 Environmental performance indices developed and monitored; | The project is developing the skills and tools that will be used by institutions and stakeholders in Viet Nam to understand, plan, research and better respond to challenges to the global environment. It is notably building capacity related to indicators, valuation and performance monitoring. This capacity will be both in government and non-government agencies. A particular focus will be provincial level government agencies. |
| 2.2 Increased capacity of stakeholders to diagnose, understand and transform complex dynamic nature of global environmental problems | 1.1 A set of indicators to monitor environmental; 1.2 Economic valuation of environmental and natural resources; 1.3 Environmental performance indices developed and monitored; | The tools and skills developed by the project through Outputs 1.1. – 1.3 will help stakeholders to diagnose and understand the complex and dynamic nature of global environmental problems, and initiate necessary transformations. Through the project, government and non-government, at national and local levels, will have increased ability to use indicator systems, monitoring systems, valuation methods and EPI, and to apply these tools to the complex global environmental problems in Vietnam. |
| CD3: strengthened capacities for policy, and legislation development for achieving global benefits |  |  |
| 3.1 Enhanced institutional capacities to plan, develop policies and legislative frameworks for effective implementation of global conventions | 2.1 Increased capacity to undertake SEA at provincial level; 2.2 Increased capacity to undertake integrated land-use planning; 2.3 Formal institutionalised commitment. | By supporting institutional tools (SEA capacity, integrated LUP) this project will directly increase the capacity of institutions to plan, develop policies and legislative frameworks for effective implementation of global conventions |

- The GEF Cross-Cutting Capacity Development is a programme that does not lend itself readily to programme indicators, such as the reduction of greenhouse gas emissions over a baseline average for the years 1990 to 1995, or the percentage increase of protected areas containing endangered endemic species.  Instead, CCCD projects are measured by output, process, and performance indicators that are proxy indicators of improved capacities for the global environment. To this end, CCCD projects look to strengthen cross-cutting capacities in the five major areas of: (i) stakeholder engagement; (ii) information and knowledge; (iii) policy and legislation development; (iv) management and implementation; and (v) monitoring and evaluation. A specific tool for monitoring the capacity developed under this project is provided in Annex 5.

- This project will implement capacity development activities through an adaptive collaborative management approach to engage stakeholders as collaborators in the design and implementation of project activities. This is designed to take into account unintended consequences arising from policy interventions.

- The project is also consistent with the programmatic objectives of the three GEF thematic focal areas of biodiversity, climate change and land degradation, the achievement and sustainability of which is dependent on the critical development of capacities (individual, organizational and systemic). The successful implementation of this project will directly develop capacities related to biodiversity, climate change and land degradation. Indirectly, this will have an impact on the implementation of the three concerned Conventions and achievement of global environmental benefits.

- This Project fully conforms to the operational principles of capacity development as identified in the GEF Strategic Approach to Capacity Building. The following table summarizes the project's conformity with the 11 operational principles.

Table: Project Conformity to CCCD Principles

| Capacity Development Operational Principle | Project Conformity |
| --- | --- |
| Ensure national ownership and leadership | The project is designed to support and improve ongoing national initiatives. Decision-making lies in MONRE and ISPONRE. Design was led by MONRE and ISPONRE. A cross-sectoral and multi-agency project support mechanism is to be established. |
| Ensure multi-stakeholder consultations and decision-making | Several rounds of consultations have been held during project development. The multi-stakeholder mechanisms that exist for the three Rio Conventions will be actively consulted during project implementation. |
| Base capacity building efforts in self-needs assessment | The project design draws fully from the NCSA and the findings/recommendations of the NCSA. It is also based on further design work related to capacity assessments. |
| Adopt a holistic approach to capacity building | The project addresses individual, institutional and systemic levels of capacity, based on NCSA, and full involvement of all stakeholders. |
| Integrate capacity building in wider sustainable development efforts | The project is fully aligned to support MONRE in ongoing initiatives. Notably it is responsive to recent policy and legislative developments (e.g. the Communist party resolution 24-NQ/TW, and the (draft) revised LEP). |
| Promote partnerships | The project is designed to develop operational partnerships across partners in the three Rio Conventions, and to promote partnerships between governmental and non-governmental (institutes, private sector and NGO) partners. |
| Accommodate the dynamic nature of capacity building | The project recognizes the dynamic and evolving process in Viet Nam to implement Rio Conventions. Notably, the baseline has evolved significantly since the NCSA was completed. The project is designed to adapt to recent policy and legislative developments |
| Adopt a learning-by-doing approach | The Project Management Unit (PMU – see later) will emphasize participatory monitoring and learning by doing. One PMU staff member will be assigned these tasks as part of her/his ToR. |
| Combine programmatic and project-based approaches | This is a project contributing to several broader initiatives implemented by MONRE and other partners. MONRE will use the project inputs to strengthen its overall approach to environmental management. For example, IPSONRE is currently implementing initiatives supported by World Bank, ADB, GiZ and UNDP. This project takes place integrally within ISPONRE’s overall programme. This is a good example of how specific international collaboration can make a difference to national initiatives. |
| Combine process as well as product-based approaches | The project is designed to support processes – it will support existing, long-term processes to develop indicators, to build valuation techniques, and to establish SEA and integrated LUP. These processes are firmly implanted in the Vietnamese context. However, the project will also lead to concrete products (i.e. lists of indicators, new techniques, guidelines, trained staff, etc). |
| Promote regional approaches | Lessons will be shared with other countries in southeast Asia. Through the UNDP network, lessons from other countries on capacity development will also be introduced into this Viet Nam project. |

### C.1.a	Guidance from the Rio Conventions

- The project contributes to the overall capacity development needs outlined in the Rio Conventions. Notably, the project contributes, in Viet Nam, to strengthening stakeholder engagement, developing organizational capacities, improving information availability and building environmental governance. This contributes to the Convention articles as set out in the following Table.

Table:  Capacity Development Requirements of the Rio Conventions

| Type of Capacity | Convention Requirements | UNFCCC | CBD | UNCCD |
| --- | --- | --- | --- | --- |
| Stakeholder Engagement | Capacities of relevant individuals and organizations (resource users, owners, consumers, community and political leaders, private and public sector managers and experts) to engage proactively and constructively with one another to manage a global environmental issue. | Article 4 Article 6 | Article 10 Article 13 | Article 5 Article 9 Article 10 Article 19 |
| Organizational Capacities | Capacities of individuals and organizations to plan and develop effective environmental policy and legislation, related strategies, and plans based on informed decision-making processes for global environmental management. | Article 4 Article 6 | Article 8 Article 9 Article 16 Article 17 | Article 4 Article 5 Article 13 Article 17 Article 18 Article 19 |
| Environmental Governance | Capacities of individuals and organizations to enact environmental policies or regulatory decisions, as well as plan and execute relevant sustainable global environmental management actions and solutions. | Article 4 | Article 6 Article 14 Article 19 Article 22 | Article 4 Article 5 Article 8 Article 9 Article 10 |

- More specifically, the project’s outcomes are designed to contribute to various substantive articles and sub-articles under the three Conventions. These contributes are set out in the following Table.

Table: Capacity Development Requirements of the Rio Conventions

| Project Outcomes | CBD | UNCCD | UNFCCC |
| --- | --- | --- | --- |
| 1. Viet Nam has environmental management tools that fully address global environment. | Article 7 (identification and monitoring). Article 10 (sustainable use of component s of biological diversity). Article 11 (incentive measures). | Article 16, information collection, analysis and exchange. | Article 12 (Communication of information related to implementation) |
| 2. Viet Nam uses environmental management in its strategic planning and development processes. | Article 6 (general measures for conservation and sustainable use). Article 10 (sustainable use of component of biological diversity). | General Provisions, Article 5 (b) and (e). | Article 4, 1 (f, h and j). Commitments. |

- Viet Nam has already greatly developed national level skills, capacities and processes. In order to implement Rio Convention, it now needs to decentralize capacity and develop skills, capacities and processes at provincial and district level. This project will contribute to that approach, in particular by building capacity in provincial level agencies.

## C.2  Project Design

### C.2a The Baseline

- As seen from the previous sections, over the past fifteen years the Government of Viet Nam has paid great attention to the formulation of an institutional, policy and legislative framework to protect environmental resources. This includes many institutional, policy and legislative measures that are directly related to global environment. These are described in detail in section B2 and more information is provided in Annexes 1 and 2.

- Allied to this, the Government of Viet Nam has taken steps to mainstream the protection of environmental resources into national and sectoral socio-economic development. Measures have been taken to mainstream environment into national, sectoral and sub-national policy development, planning, programmes and investment decision-making. This has notably been achieved through the development of an EIA process, a SEA process and integrated land-use planning processes.

- In the baseline, the above processes will continue and environmental resources will receive increasing protection. The baseline with regards to each output is summarized in the following table, and the details are described in section C2d below.

| Output | Baseline initiatives |
| --- | --- |
| 1.1: A set of indicators to monitor environmental status and pressure developed | ISPONRE and GSO have developed indicators systems and are continuing training and data collection. |
| 1.2: Economic valuation of environmental and natural resources, and capacity to undertake this valuation | ISPONRE and many other actors (WB, CRES, WWF, GiZ) have undertaken economic valuation of specific ecosystems or in specific regions. |
| 1.3: Environmental performance indices developed and monitored, in line with international standards | ISPONRE and UNDP developing this system and these capacities. |
| 2.1: Increased capacity to undertake SEA | A large scale programme to develop SEA processes and capacity has been supported by ADB, and capacity building (including regulatory development) continues. |
| 2.2: Increased capacity to undertake integrated land-use planning | New Land Law under review. UNDP also supports MARD on related initiatives. UN-REDD also supporting some related initiatives. |

- Notably, the Government is developing dedicated tools to support the implementation of the institutional, policy and legislative framework. These tools include an indicator framework, economic valuation techniques, and environmental performance indicators. The government is also further developing its approaches to SEA and integrated land-use planning processes, notably through the amended Law on Environmental Protection and Law on the Land (both currently in draft form and being appraised by the national legislature).

- As explained in the previous sections, in the baseline there are two major weaknesses. The first is that the focus of the measures is sustainable development and local environmental protection – in the baseline the global environment (biodiversity, climate change and land degradation) will not be adequately accounted for. Second, there is a lack of capacity to utilize the new tools and measures. This capacity shortage is most acute at provincial level - although many of the larger provinces now have significant capacity.

Baseline

Developing the environmental indicator framework

Developing economic valuation of environmental resources environmental indicator framework

Developing environmental performance indices

Strengthening SEA operational capacity

Strengthening operational capacity for integ’t’d land-use planning

Focus on local environment and sustainable development

Figure 1: environmental protection measures in the baseline

- The specific baseline with regards to each Output is described in C2d below.

### C.2bTheGEF Alternative

- The GEF support will be used to mainstream biodiversity, climate change and land degradation into the above baseline initiatives. Notably, GEF support will focus on: (i) improve indicator systems and their use; (ii) improve valuation techniques of environmental resources; (iii) operationalize environmental performance indices; (iv) analyze and increase operational capacity for SEA by two case studies at selected provinces; and (v) increase operational capacity for land-use planning (see Figure 2).

Baseline and

GEF Support

Developing the environmental indicator framework

Developing economic valuation of environmental resources environmental indicator framework

Developing environmental performance indices

Strengthening SEA operational capacity

Strengthening operational capacity for integ’t’d land-use planning

Includes coverage of biodiversity, climate change and land degradation

Figure 2: Global and local environmental protection measures in the alternative

- The details of the GEF alternative for each of these are described in C.2.d below. Likewise, the GEF incremental approach and the role of partner institutions are summarized in section C.2.d.

### C.2cProject Objective and Outcomes

- The NCSA has the overall Goal of helping Viet Nam to fulfill all its obligations under the multi-Environmental Agreement (MEAs). This Project contributes to the implementation of the action plan prepared through the NCSA.

- More specifically, the NCSA was formulated with the Objective of “strengthening the systemic, institutional and individual capacities of Vietnam for effective implementation of the Rio Convention obligations consistent with national circumstances and needs for sustainable development”.

- Within that broader context, the specific Objective of this project is ‘to enhance the capacity for implementing the Rio Conventions by developing and applying tools that will lead to global environmental benefits”. At the end of the project, activities will have resulted in a set of improved capacities to meet and to sustain Rio Convention objectives. This will be achieved through the following two Outcomes:

- Viet Nam has the environmental management tools that fully address global environmental concerns;

- Viet Nam is integrating global environmental concerns into its national strategic planning and development processes.

### C.2dProject Outputs and Activities

Outcome 1: Viet Nam has the environmental management tools that fully address global environmental concerns

Output 1.1 A set of indicators to monitor environmental status and pressure developed

Baseline

- Two of the main sets of environmental indicators currently in use in Viet Nam are:

- National Environment Indicators for Air, Fresh Water and Coastal Water  (NEI/A-FW-CW / MONRE) issued by the Ministry of Natural Resources and Environment (MONRE) in the Circular Number 10/2009/ TT-BTNMT dated 11 August 2009. These entered into force on 25 September 2009. They include 177 primary indicators and 66 secondary indicators;

- The Environmental Indicators in the National Statistical Index System (EI/NSIS/GSO) issued at the Decision number 43/2010/QD-TTg dated 2nd June 2010 by the Prime Minister. Overall there are 21 groups with 350 indicators in the NSIS. The Environmental indicators (Group 21) has 24 indicators. These also cover indicators used in the Rio+20 reporting process (see Box).

Box: Rio + 20 Indicator Set Viet Nam recently reported on implementation of sustainable development to the Rio+20 conference (Vietnam’s Report to the United Nations Conference on Sustainable Development, 2012). This report provides information on progress related to many indicators, mostly aligned to the MDGs. For example, four indicators are provided for MDG 7 (i.e. environmental sustainability), namely forest coverage; proportion of rural population with access to safe drinking water; rural households with sanitary latrines; and households with temporary shelters). The report also provides information on seven indicators for natural resources and environment, each with targets for 2015 and 2020. These are: - Forest coverage; - Protected land, where biodiversity is preserved; - Degraded land; - Underground and surface water decreasing rate; - Rate of days when noxious substance density in atmosphere surpasses allowable levels; - Rate of cities, industrial parks, export processing zones, industrial clusters with solid and liquid waste treatment systems meeting corresponding; - Rate of solid waste collection and treatment. Broadly speaking, these indicators are drawn from the environmental indicators in the National Statistical Index System (i.e. from: EI/NSIS/GSO).

- Of the above two sets of indicators, the NEI/A-FW-CW indicators are far more detailed. See Annex 3 for more detailed information on NEI/A-FW-CW.

- MoNRE and other government agencies (notably MARD and GSO) have ongoing activities to develop these indicator and their use. This includes notably: training of provincial and district government agencies; preparation of the National Environment Report and Provincial Environmental Reports (prepared by the provincial DONRE). These reports have been published annually since 2006, with each year’s report focusing on a specific theme (e.g. the NRE focused on biodiversity in 2005, water in three basins in 2006, and urban air in 2007).

- The baseline also includes the project ‘Development of National Biodiversity Database System in Vietnam’ (supported by JICA, and implemented through the Biodiversity Conservation Agency). This project is helping to develop a database on biodiversity of Viet Nam - a starting point for the development of indicators for long-term monitoring of biodiversity.

- Currently, MONRE is in charge of monitoring environmental status at national level, and the DONRE are in charge of monitoring environment condition at provincial level.

- A significant gap in the baseline situation is that the indicator sets do not provide adequate information on global environmental issues. They do not have adequate parameters associated with monitoring biodiversity, biodiversity conservation, greenhouse gas emissions trends and factors, climate change adaptation measures and land degradation. They are not of use when preparing reports to the Rio Conventions. There is no agreed set of indicators covering the Rio Conventions and useful in preparing reports to the Rio Conventions. Other gaps include (i) compatibility across the sets of indicators, in particularly the two (NEI/A-FW-CW / MONRE and EI/NSIS/GSO) described above; (ii) limited capacity at national level to guidance provincial level managers on indicators; and (iii) limited capacity at provincial level to collect data related to the indicators.

- Overall, there is limited understanding of the existing indicators and in particular of how to apply them to monitor global and national environmental benefits. There is limited understanding on how to monitor environmental change (i.e. biodiversity, climate change and Land degradation) overtime by using these indicators.

- The Project partner, WWF, is working on the project “Annamites Carbon Sinks and Biodiversity”, and through this project it is undertaking research related work on forest and species monitoring indicators.

Alternative and Activities

- With GEF Support, an appropriate set of indicators for monitoring the national and global environment related to the Rio Conventions (RCSI) will be developed. The capacity of the Convention Focal Points to use the indicators to monitor environmental changes in term of BD, CC and LD will be enhanced, as will their increased understanding of the state and pressures of environmental change. Other key governmental and non-governmental stakeholders at national level will receive training in indicator sets and using indicators for environmental management.

- In turn, the information generated from using the RCSI will support the development of actions and policies that will lead to a reduction in the drivers of negative national and global environmental change. With GEF support, the nationally approved indicator framework will appropriately cover global environmental issues. There will be indicators of biodiversity, biodiversity conservation, biodiversity trends, GHG emissions, GHG mitigation measures, land degradation status, land degradation trends, measures to stop and reverse degradation, etc.

- Key activities supported by GEF are:

1.1.1 Review the present sets of indicators to monitor environmental status and pressure and identify the gaps in terms of coverage of all global environment issues;

1.1.2Review indicator sets for the three Rio Conventions used in other countries to determine best practices and how gender issues are included in the indicator sets;

1.1.3Develop a comprehensive set of indicators for monitoring the national and global environment related to the Rio Conventions (RCSI). The following will be clarified for each indicator:

- The objectives of the indicator;

- The definition of each indicator;

- The users of the indicator;

- The methods and kinds of usage;

- The method to identify each indicator;

- The inputs and how to collect the information (sources, quality requirements, quality control and quality assurance …);

- User guide for applying the indicator to monitor environmental status and pressure; and

- Baseline value (in 2010).

1.1.4 Training for Convention focal points and associated governmental and non-governmental partners on the use of the RCSI and on related reporting.

Risks

- There are high training needs related to collecting and storing and reporting on the information – in particular at provincial level;

- There may be gaps on the availability and quality of information;

- There may be gaps in local capacity conditions (such as the requirement of computers, copyright of software, IT knowledge).

Output 1.2. Economic valuation of environmental and natural resources, and capacity to undertake this valuation

Baseline

- Communist Central Party Resolution Number 24-NQ/TW, Active Response to Climate Change and Improving the Management of Natural Resources and Environmental Protection highlighted the significance of natural capital for the development of Viet Nam and stressed that one of major tasks would be the identification and assessment of natural resource values and the development of a natural resource accounting system.

- This Resolution follows on the issuance of several legislative measures, as follows: Decree no 188/2004/ND-CP on the methodology to determine the land use price and the framework for land use prices; Decree no. 123/2007/ND-CP on amending and supplementing a number of articles of Decree 188/2004/ND-CP; Law No. 11/2012/QH13 on Prices (articles no. 19 and 22); and Decree no. 89/2013/ND-CP detailing implementation of a number of articles of the Pricing Law. Moreover, in the forestry sector, there is the Decree 99/2010/ND-CP on determining payment for forest environmental services (article 8, 9) and Decree 48/2007/ND-CP on the principals and methods of forest prices in Viet Nam.

- There are also several regulations related to economic valuation available in specific laws on environmental and natural resources, such as the Law on Natural Resource Tax 2010 (article 6 on price for taxation of natural resources) and the Law on Environmental Protection 2005 (article 113 on environmental protection fee).

- Hence the baseline includes a significant regulatory and legislative basis. Moreover, in the baseline, there has been, and continue to be, a number of related operational initiatives, mostly undertaken by expert groups. The most notable are:

- The ongoing UNEP project to develop tools to demonstrate trade-offs and supply-response functions of mangrove ecosystems in Ca Mau, aiming at integrating ecosystem assessment, scenario development and economic valuation of ecosystem services for sustainable development planning;

- Mai Trong Nhuan and others (2000) applied market-value approach for the estimation of a range of wetland values in Viet Nam;

- Do Nam Thang and Jeff Benet (2005) also used market prices for the valuation of mangrove forests in Ca Mau;

- The same approach has been applied by Le Thu Hoa et al. (2006) for the calculation of direct use values of Giao Thuy National Park, Xuan Thuy district, Nam Dinh provice;

- Market-based values have also been estimated in a study of Vu Tan Phuong and Tran Thi Thu Ha on forest ecosystem services;

- Environmental loss and damage values of Thua Thien Hue after natural disaster (using the real market methods);

- Valuation of ecosystem damage caused by pollution from oil spills in the marine protected area Cu Lao Cham, Quang Nam (using habitat equivalency analysis); and,

- The World Bank (financed by the Netherlands Government) currently supports the ‘Valuing Ecosystem Services in the Economies of Viet Nam and Lao PDR’.

- The Project partner and co-financer CRES is implementing a key related project “Sustainable Use of Cam Thanh Nypa Wetlands, Hoi An city, Quang Nam Province”. The project focuses on raising awareness and capacity on sustainable use of Nypa wetlands of stakeholders and developing a model of community based ecotourism for Cam Thanh Commune, Hoi An city, Quang Nam province. This is directly related to the development of capacity for natural resource accounting.

- There are many weaknesses and gaps in the baseline situation, some related to environment in general, some related to the global environment specifically. First, most of the above work involves only a limited number of experts. In general, the above activities and outputs are not linked to decision-making – they remain somewhat academic or research-oriented. Economic valuation of natural resources still has a low impact on the policy making and decision-making processes in Viet Nam.

- There are many forms and types of ecological services. The Millennium Ecosystem Assessment classified ecosystem services into: supporting services, provisioning services, regulating services and cultural services. In Viet Nam, the focus has been on provisioning services. This has tended to undermine values related to biodiversity and climate change.

- Third, there is a lack of capacity to undertake economic valuation. Experts with high qualification and experience are limited at both national and sub-national levels. There is a lack of knowledge on the systematic assessment and scientific methods of economic valuation in Viet Nam. The establishment of high quality databases is an important precondition to conduct economic valuation, and it will affect the valuation results directly. However, available environmental data merely focuses on selected natural resources such as: land, forests, etc, while for important aspects of ecosystems, such as biodiversity and ecosystem services, the data base remains very scarce.

- Fourth, although the LEP (2005) formulates the requirement to identify and assess the loss and damage caused by environmental pollution within Environmental Impact Assessments (EIA), there are no specific methods defined on how to assess economic values of loss and damage. Legislative documents do not provide the principals and methods for natural resources and environment valuation accounting.

- Fifth, in Viet Nam, the measures of Net Present Value (NPV) and Internal Rate of Return (IRR) are applied to define the performance of social-economic investment projects. The analyses are still limited to the calculation of direct net benefits and costs, using market price methods. Hence indirect-use, option and non-use values are greatly undervalued, leading to an incomplete picture of the opportunity costs for social-economic investment projects and programs. This has tended to undermine values related to biodiversity and climate change.

- Also, the valuation of some natural resources and environment is limited due to coordination and ownership in natural resources and environment (e.g. land belongs to the State while forest is owned by households, provincial people committee).There are overlapping mandates of line ministries on natural resources and environmental management (i.e. MONRE has the mandate of biodiversity conservation and land administration while MARD has the mandate of forest management). The weak cooperation between the line ministries is also contributes to the limited data availability.

- Finally, as of yet, there are no regulations on economic valuation within the current Law on Water Resources, Minerals Law and Law on Biodiversity. Moreover, there is still lack of regulations on the identification of economic values of land resources;

Alternative and Activities

- As seen above, much can be done regarding economic valuation. This project cannot address all these weaknesses, and parallel projects and government initiatives will address most of them. This GEF project will support the overall process, focusing on weaknesses related to biodiversity, climate change and land degradation. The activities include:

1.2.1Prepare guidelines on conducting economic valuation of regulating services (these are the benefits obtained from the regulation of ecosystem processes, including air quality regulation, climate regulation, water regulation, erosion regulation, water purification, disease regulation, pest regulation, pollination, natural hazard regulation). The guidelines will also clarify how social economic benefits are affected, notably gender;

1.2.2 Provide training and guidance for national level decision makers on how to understand and utilize the economic value of ecological regulating services and integrate these values into their decision making processes;

1.2.3 Provide training on economic valuation of ecosystem services for a number of provinces for better recognition of regulation services (i.e. carbon sequestration, biodiversity and habitat). The training will include social economic dimensions of the regulation services, including gender aspects;

1.2.4 Develop a document capturing best practices on using economic valuation of ecosystem services to support policy and decision-making;

1.2.5 Establish a policy dialogue/forum to inform policy makers on the application of valuation results in the planning process.

Risks

- Availability of adequate data/information (quality and quantity);

- High need for technical capacity.

Output 1.3: Environmental performance indices developed and monitored, in line with international standards

Baseline

- Viet Nam started work on environmental performance assessment in 2005, notably with the support of the ADB through two initiatives:

- An Environmental Performance Assessment (EPA) was completed in 2005, within the Greater Mekong Sub-region initiative. In 2006, ADB and others supported the Core Environment Program - Biodiversity Conservation Corridor Initiative, which included an EPA Component. In the framework of this program, with the support of ADB Environmental Operations Center (EOC), ISPONRE undertook a national EPA study to assess the country's environmental protection activities over the period 2006-2010. This covered: surface water, urban air quality, solid waste; climate change and biodiversity;

- In 2010, the Center for Environmental Monitoring of the VEA undertook research on the environmental sustainability index (ESI) ranking, with 15 test indicators in 5 categories developed. The work led to 31 Provincial Directives, and to environmental ratings applicable to 8 provinces. However, this did not go into a comprehensive assessment of management policies or of environmental protection.

- Environmental Performance Assessment as a tool is most pertinent to programmes and projects. At the national or provincial level, Environmental Performance Indices (EPI) is a more appropriate tool for ranking the performance of countries/provinces, using performance indicators across policy categories and including both environmental public health and ecosystems. EPI therefore provide a gauge of a country’s performance toward policy goals (although the EPI is primarily applied at the country-level, its flexible framework and methodology can also be adapted for a variety of purposes at different scales).

- Many of the skills developed for EPA in the past are applicable to EPI. However, many are not, and a series of skills, data and tools are required in order to undertake EPI in Viet Nam. Notably, in the baseline, Viet Nam faces technical, financial and institutional challenges in developing and using EPI. Further, in the baseline, as Viet Nam prioritizes the use of its scarce resources, EPI will focus on local environmental issues such as air pollution, health impacts and sustainable development.

Alternative

- The alternative is mostly funded by the Project partners – UNDP and ISPONRE. GEF funds are used to ensure linkages and coordination with the five other Outputs, and to provide some additional training to pilot and roll out an EPI that fully addresses global environmental issues.

- The alternative consists of the development of an EPI as a method of quantifying and numerically benchmarking the environmental performance of the country's policies, and in order to provide positive incentives to decision-makers at provincial level. This will be in line with the work done globally to develop EPIs by the Yale Center for Environmental Law and Policy, Yale University and the Center for International Earth Science Information Network, Columbia University (see http://epi.yale.edu).

- The alternative also includes the project on Environmental Ranking (2013 – 2015). This will rank provinces in term of their environmental performance. This process will develop criteria and indicators for the environmental ranking of provinces.

- The above initiatives are implemented by ISPONRE with support from UNDP and the project ‘Strengthening Capacity on Natural Resources and Environment Policy Development and Environmental Performance’. This project support Environmental Ranking by assessing models from countries including China, it will help apply lessons learned to the development of an EPI for provinces in Viet Nam, and it will help formulate and test the model in three Vietnamese provinces. This will be done in association with Yale University and its partners. Specifically, it will develop an EPI for Vietnamese Provinces that:

- highlights current environmental problems and high priority issues;

- tracks pollution control and natural resource management trends;

- identifies policies currently producing good results;

- identifies where ineffective efforts can be halted and funding redeployed;

- provides a baseline for  cross-sectoral performance comparisons;

- facilitates benchmarking and offers decision-making guidance;

- spotlights best practices and successful policy models; and

- elucidates linkages between environmental policy and other issue areas such as public health, revealing new, effective leverage points for change.

- The alternative also includes training of provinces to undertake provincial level EPI and to use EPI as an environmental management tool.

- The GEF funds are used to ensure linkages and coordination with the five other Outputs, and to provide some additional training to pilot and roll out an EPI that fully addresses global environmental issues.

Activities

1.3.1 (covered by the UNDP Project) Develop a Provincial EPI by:

- Reviewing the standard EPI of Yale University and how it has been adopted and applied internationally, particularly at the sub-national level, as done by China. This also includes reviewing experiences in technical development and operation of sub-national EPIs and gauging their impacts over time;

- Reviewing statistic system in Viet Nam and availability of environment related data and information;

- Developing a feasible proposal for application of EPI in Provinces including elements, types of information and data, systematic data collection, indicator systems for evaluation and data analysis;

- Systematically involving stakeholders in the process of Provincial EPI development.

1.3.2 (covered by the UNDP Project) Pilot implementation of the Provincial EPI:

- Conduct training workshops on application of the EPI

- Test the EPI in three pilot provinces and evaluate test results

- Refine the Provincial EPI according to test evaluation recommendations

1.3.3 (covered by the UNDP Project) Produce a national report on EPI implementation at Provincial level:

1.3.4 Hold consultations and undertake technical analysis to ensure the work on EPI is mutually supportive of the work on indicators (Output 1.1) and natural resource accounting (Output 1.2).

1.3.5 Provide training to government officers and experts in three additional provinces on preparing EPI, with focus on biodiversity, climate change and land degradation related issues. Gender issues and mainstreaming will be covered under this EPI training.

Risks

- There is a risk that the work supported through the UNDP project will face delays.

Outcome 2: Viet Nam is integrating global environmental concerns into its national strategic planning and development processes

Output 2.1: Increased capacity to undertake SEA

Baseline

- The Law on Environmental Protection (2005) mandates SEA for a range of strategies, policies and plans (SPP), at national, inter-provincial and provincial level. This includes national socio-economic development strategies and plans; sector strategies and plans on a national scale; socio-economic development strategies and plans of provinces or regions; plans for land use, forest protection and development; plans for the exploitation and utilization of other natural resources in inter-provincial or inter regional areas; plans for development of key economic regions; and planning documents for inter-provincial river watersheds (See Annex 4 for complete list). Further, it stipulates the role of SEA in the SPP appraisal and approval process, and it clarifies the responsibilities and the basic contents of the SEA report. Notably, the SEA has to be conducted concurrently with the formulation of the SPP, either in a parallel process or as an integrated part of it (ex-ante principle).

- The draft new Law of Environmental Protection (2013), under preparation, will introduce some changes, mainly: (1) under the current (2005) Law, the SEA must be applied to Strategies, Master Plans and Land-use or Physical Plans. In the new Law, it will be applied to Strategies and Master Plans; (2) under the new Law, there is one additional article concerning the collection of SEA and the reporting of SEA results. Finally, the draft new LEP includes a chapter on how to include civil society organizations (CSOs) in SEA.

- The following legal documents provide further details on operationalizing SEA:

- Decree 140/2006/ND-CP covers the stages of SEA elaboration, evaluation, approval and implementation (scope and terms as well as responsibilities);

- MONRE Circular No. 05/2008/TT-BTNMT on SEI and EIA further defines the SEA review process and the requirements for the report;

- MONRE Circular No. 13/2009/TT-BTNMT provides operational regulations of the SEA review committees;

- Decree No. 29/2011/ND-CP gives a clearer provision on subject, time frame, contents, appraisal and responsibilities of SEA. This Decree includes 5 chapters with 41 articles and in Chapter 2 “Strategic Environmental Assessment” is covered by 9 articles;

- MONRE Circular No. 26/2011/TT-BTNMT provisions the details to implement the Decree No. 29/2011/ND-CP. Chapter 2 “Strategic Environmental Assessment” is covered by 7 articles.

- MONRE has also issued Circular No. 26/2011/TT-BTNMT (2011). Finally, the Department for Environmental Impact Assessment and Appraisal (under MONRE) prepared and issued “Technical Guideline for Strategic Environmental Assessment” (2009) and other draft Guidelines, such as “Technical Guideline to implement SEA for Regional Development Planning” (2011), “Technical Guideline to implement SEA for Land Use Planning” (2010), “Technical Guideline to implement SEA for Social – Economic Development at Regional/Provincial level” (2010).

- Hence, there is an array of laws and legislative documents related to SEA. After the LEP came into force, a number of pilot SEA initiatives were undertaken covering socio-economic development plans, land-use plans and hydropower planning.

- Moreover, in the baseline, the majority of focus of the SEA is on local environmental issues. Very little attention is paid to conserving mitigating climate change, adapting to climate change and to overcoming land degradation.

- Much of the above work on developing the SEA process and system has been supported by the ADB. Following on from that, the ADB is currently implementing Technical Assistance TA 7566-REG: “Strengthening and Use of Country Safeguard Systems” is supporting in Viet Nam “Capacity Development for the Implementation of the New Environment Decree” (2010 – 2013). This continues to support the SEA system and processes in Viet Nam. This is leading to the four following Outputs:

- Recommendations on the General Implementing Circular on Strategic Environmental Assessment, Environmental Impact Assessment, and Environmental Protection Commitments;

- Assessment of institutional capacity needs for implementing the General Circular of the revised Decree;

- Country Safeguard System Capacity Action Plan (CAP) for strengthening implementation of new assessment procedures and general circular; and

- Launch implementation of CAP in priority areas.

- This ADB baseline initiative has helped define and clarify capacity needs. In the coming years, it will help meet many of those needs. However, there is still an unattended need to conduct case and pilot studies on provincial application of SEA. The baseline also includes work by the Project partner WWF through the project “Sustainable Supply Chain for Pangasius in Vietnam”.

Alternative and Activities

- SEA is a vast area of environmental management, and there continues to be significant cooperation between the government and ADB on this issue. This Project, with GEF Support, will complement the ADB support through two case studies at selected provinces to analyze the practical integration of global environmental issues (biodiversity, biodiversity conservation, GHG mitigation measures, and land degradation) into the applied SEA process. Notably, the GEF support will ensure that the Rio Convention and related indicators (RCSI, Output 1.1) are applied into SEA case studies in two selected provinces to strengthen SEA process at local level and to integrate the Rio Conventions into the SEA processes in Viet Nam. The two provinces for the case studies will be identified based on the availability of natural capital and characteristics covered by the Rio Conventions. The provinces will be identified during the inception phase of the project.  Subsequently, based on lessons learnt in the case studies, support will be given to the overall ADB-supported process to strengthen SEA in Viet Nam.

2.1.1:Analyse and review the Law, the Circulars, the Decisions, the Decrees and the Guidelines to see how global environment (biodiversity, climate change, and land degradation) is addressed and, if necessary, in conjunction and coordination with ADB, propose changes and updates to the Law, Circular, Decisions, Decree and/or Guidelines;

2.1.3:  Determine how the products of Outcome 1 (i.e. RCSI and economic valuation methods) can be applied to the SEA process in two provincial case studies (with a special focus on the global environment). Prepare Guidelines on how to apply the products of Outcome 1 to the SEA process at province level. This will include the identification of how to address gender aspects.

2.1.4: Conducting training courses and undertake pilot cases on the use of the Guidelines for staff in the National (MONRE) and Provincial (DONRE) level (with co-financing);

2.1.5:  Monitor impact of the Guidelines and the extent to which they impact the global environment.

Risks

- The tools (products of the Outcome 1) are too difficult to apply to the SEA process (i.e. they are too complex or they require too much information);

- The knowledge of the staff, especially at provincial level, is too limited to apply the Guidelines and the training budget is insufficient.

Output 2.2: Increased capacity to undertake integrated land-use planning

Baseline

- There are several legal documents pertaining to LUP, notably:

- The Decision Number 04/2005/QD-BTNMT (2005) by MoNRE on the Procedure to establish the land-use planning and plans for national and local levels;

- The Decree Number 69/2009/ND-CP (2009) issued by the Government on land-use planning, land prices, land acquisition, compensation, support and resettlement. This has many articles addressing land-use planning and process at national, provincial, district and communal levels.

- Resolution Number 17/2011/QH13 (2011) of the National Assembly on National Land-use Planning to the year 2020 and the 5-year plan (2011 – 2015)

- As of October 2013, the National Assembly was reviewing the revised Law of Land. Following its approval, implementation documents will be approved (i.e. Decrees and Circulars) and issued by the Prime Minister and MARD.

- With support from the Swedish Government, the Project “Strengthening Environmental Management and Land Administration Vietnam – Sweden Cooperation Programme” prepared a Guideline to Integrate Environmental issues into Land-use Planning (2007), which set out the following seven steps:

- Step 1:  Identify the Background and Purposes of the Planning

- Step 2: Investigation and Collecting the baseline data and making trend analysis

- Step 3: Assessment the potential of land and establishing the planning scenarios

- Step 4: Evaluation of scenarios and choices the optimum scenario

- Step 5: Establishing the Planning and making the Environmental Report related to Planning

- Step 6: Approval

- Step 7: Implementation and Monitoring

- However, in the baseline, there are several challenges to rolling out integrated land-use planning. First, despite the number of legal documents related to land-use planning, the integrated land-use planning concept is not clear enough, and the differences between Integrated Management and Integrated Planning are not clear. Second, there is a lack of spatial data and inconsistency amongst the existing spatial data. Third, there is a lack of coordination across between Ministries. For example, there is an overlap between MONRE and MARD in establishing and managing topographic, land-use and forest cover maps. Both agencies are mandated to formulate regulations and implement actual tasks. Meanwhile, their cooperation is loose, notably with regards to defining the boundaries between agricultural land and forestry land and determining the criteria for classification of forest and forest land. This consequentially leads to difficulties in managing and annual reporting. Finally, the classification of spatial data on land cover and land use in Vietnam is confusing and not straightforward. In addition, Land use planning (LUP) focuses on different land use types, and does not fully consider different drivers and ecological functions. As a result, land-use plans do not provide any information on the ecological status and pressure – hence they are largely insufficient for biodiversity, climate change and desertification monitoring and planning.

- In general, in terms of land use planning, global benefits such as biodiversity and ecosystem services are not well considered in planning process. Moreover, the actual value of biodiversity and other ecosystem services are not well recognized in the LUP (when compared to economic benefits). The application of tools for integrating biodiversity and ecosystem services into land-use planning for in order to protect global values is limited.

- One recent development is the interest in “functional zoning” based on ecological characteristics, natural resources and potential impacts of climate change as a basis for development planning, land use planning and marine spatial planning.  In part, this interest stems from Viet Nam Communist Party Central Committee passed Resolution 24-NQ/TW (see Section B above) on actively responding to climate change, strengthening natural resource management and environmental protection. The Resolution specified that such functional zoning should be adopted.

- Functional zoning is essentially the spatial application of the ecosystem-based approach to development. Functional zoning involves the spatial classification and delineation of land and water resources, terrestrial and marine ecosystems, critical ecosystem functions of terrestrial and marine ecosystems, planned land and water resource use, projected climate change impacts, and assessment of status and trends. Areas where resource use and protection may be in agreement or in conflict are then identified, ranked and evaluated, in light of expected climate change impacts.

- The use of functional zoning is one approach to ensure that global environmental benefits can be considered during land-use planning processes. However, in the baseline, LUP in Viet Nam will not draw from functional zoning, but will adopt a traditional approach to LUP, whereby the most economically attractive use for land is identified and developed, followed by an environmental assessment.

- To summarize, as with most approaches to environmental management in Viet Nam, the baseline does not cover global environmental issues. The focus is on issues of consequence to local communities, economic development, local governments and local private sector organizations.

- MONRE is responsible for national land use planning and the provincial DONRE are responsible for provincial land use planning. Other line Ministries/Agencies (i.e Agriculture, Tourism, Forestry, etc.) also participate in the development of land-use plans.

- The Project partner, WWF, is implementing three projects in the baseline which will complement the working being supported by GEF. These are:

- Certification and better management practice among small scale shrimp farmers;

- Policy forum in the Mekong Delta to promote more sustainable development; and

- Strengthening biodiversity conservation and improving dependent local livelihoods through community based natural resource use.

Alternative and Activities

- With GEF Support, appropriate tools will be developed and tested for integrated LUP to ensure that the LUP takes into consideration the value of biodiversity and ecosystem services which can support climate change adaptation and protect land resources. Ecological zoning will be initiated as an approach to ensure that land-use development is driven by a consideration of ecological aspects. In addition, the impacts of LUP on biodiversity, land degradation and climate change will be assessed to reduce the pressure on ecosystem functions.

2.2.1: Assess experiences from other countries on integrated land-use planning, and the relationship between integrated land-use planning and Rio Conventions, especially with the UNCCD and the CBD. Assess also experience and use of ecological function zoning;

2.2.2: Review the activities in land-use planning in Viet Nam, identify strengths and weaknesses, and assess capacity to undertaken integrated land-use planning.Analyze current land cover and land use mapping and propose how to harmonize this, and how to ensure that mapping activities include spatial data relevant for the global environment (biodiversity, climate change and land degradation);

2.2.3: Determine how to apply the products of Outcome 1 (i.e. RCSI and economic valuation methods) to land-use planning;

2.2.4: Undertake case studies on two provinces (same provinces as output 2.1.3), showing how to apply the products of Outcome 1 in order to integrate biodiversity, climate change and land degradation into integrated land-use planning, and gender issues and gender mainstreaming will be included in the  LUP case studies.

2.2.5: Prepare a detailed proposal for the piloting of ecological function zoning in one of the analysed provinces, including full details of: capacities and data needed; potential benefits and how to evaluate them; how to monitor the piloting; how to feedback findings into future policy; how to ensure biodiversity, climate change and land degradation all benefit positively from ecological function zoning.

2.2.6: Conduct training courses for key staff in MONRE, DONRE, MARD and DARD in order to increase the capacity to undertaken integrated land-use planning at National and Provincial levels.

Risks

- Insufficient human resources/knowledge for preparing documents, case studies, tools;

- Complications may arise when applying the tools in diverse local conditions.

Output 2.3: Formal institutionalized commitment in the form of a Government Decision to SEA and integrated land-use planning

Baseline

- As described under the above Outputs, there are many laws, decrees and circulars related to indicators, resource valuation, and integrated land-use planning. However, they also suffer the same weakness – they do not adequately cover the Rio Conventions and the global environment.

- The above Outputs will prepare the tools and capacity needed to address the global environment through indicators, resource valuation, and integrated land-use planning. However, the above Outputs will not formalize these tools and capacity into law. Hence, in the baseline, their sustainability and applicability may be limited.

Alternative and Activities

- This Output is the formal institutionalization of Outputs 1.1 – 2.2. It takes each of the five above Outputs and ensures they are enshrined, as necessary, into the Vietnamese regulatory framework in the appropriate manner. This will ensure the sustainability and application of Outputs 1.1 – 2.2.

2.3.1: Based on the results of Outcome 1 (tools), prepare a draft Government Decision (in the form of an institutionalised commitment such as a Prime Ministerial Decree or Circular, or a Ministerial Decision);

2.3.2: Based on the findings and results under Outputs 2.1 and 2.2, (provincial case studies on SEA and integrated land-use planning), prepare a draft Government decision (in the form of an institutionalised commitment such as a Prime Ministerial Decree or Circular, or a Ministerial Decision). This will complement, as necessary, work undertaken by the ADB to develop the regulatory framework for SEA – and this GEF project is expected to only make a small technical contribution to that process (and thereby ensure that the Rio Conventions are adequately covered).

2.3.3 Launch the formal appraisal process for the decisions from Outputs 2.3.1 and 2.3.2, including broad consultations across the country;

2.3.4: Submit the final drafts to the appropriate Government body (Minister or Prime Minister) for approval.

Risks

- The time required to promote and approve legislation may be too long to be completed within the time frame of the project.

## C.3	Sustainability and Replicability

### C.3.a	Sustainability

- Sustainability of the Project’s outputs will be achieved through the following strategies (as explained in the subsequent paragraphs):

- building on existing initiatives and stakeholders;

- ensuring all aims and outputs are pragmatic and realistic;

- ensuring the project is aligned with political processes and developing political support;

- capacity building and learning by doing; and,

- working closely with a range of partners.

- The project builds upon an existing initiatives. It strengthens a series of existing tools (and tools that are being prepared) – rather than preparing new or isolated ones. These tools are already being supported and the process to their development has momentum and broad support. Moreover, the project strengthens the capacity of existing, concerned stakeholders, rather than developing capacity of stakeholders to undertake new tasks.

- The project will develop pragmatic and realistic tools, tools that are consistent with prevailing capacities and budgets and policies in Viet Nam, and avoid the temptation to introduce over-ambitious tools or tools that are just too innovative for the prevailing capacities in Viet Nam. The project does not attempt to introduce radically transforming approaches, but to improve and build up on existing approaches. The project’s fundamental approach to sustainability is to ensure that future policies and national developments take into account the global environment by designing a series of strong, context-relevant and replicable tools. The project will also develop the capacity for engaging with these tools and ensure an institutional commitment to the use of these tools.

- This initiative builds on 15 years of strengthening of the institutional, policy and legislative framework for environmental protection in Viet Nam. The strategies, laws and action programmes that have been formulated over the last years, as well as the planned initiative upon which this project is built, attest to Vietnam’s engagement to safeguard its environment and natural resources. This political willingness will be a key factor in ensuring that the outcomes of this project are sustainable. The Project will take the necessary measures to ensure this political support is maintained – notably through Output 2.3.

- The Project supports a series of capacity building and training to ensure that the tools developed can be used and are, indeed, being used. This ‘on-the-job’ learning will ensure that (i) tools are appropriate to their use and their users; (ii) tools enjoy the buy-in and support of stakeholders. This ‘on-the-job’ approach will also build the capacity of relevant institutions and stakeholders to draft sustainable environmental strategies and to mainstream the Convention in national policies. Through the proposed project, several manuals and guidelines will be developed to support and accompany future use of the tools – these are also key for sustainability. Moreover, during project implementation, a set of monitoring activities will ensure that the results are aligned with expectations. Finally, project implementation will include a number of capacity building workshops and trainings. This will ensure an understanding of the relevance and use of the Conventions to Vietnam’s socio-economic and environmental context. Capacity building will be undertaken to ensure stakeholders can use the tools prepared by the project;

- Similarly to the design of the proposal and its objectives, the implementation of the Project’s activities will be done in constant collaboration with all stakeholders. As explained previously, the stakeholders will play a key role in the design and testing of the tools. This is not only essential to build the capacity of the stakeholders but also to ensure a sense of ownership of the project’s outcomes amongst all stakeholders. Finally, the Project is one of several supporting the development of environmental management tools. This includes tools supported by the Vietnamese government and other development partners. This includes projects supported by UNDP/GEF, UNDP, the German Government, the World Bank, ADB and WWF (see section E.1). This partnership and collaborative approach also contributes to the Project’s sustainability.

### C.3.b	Replicability and Lessons Learned

- The project has many replicable aspects – both across Viet Nam and to other countries in the region with a similar environmental governance capacity.

- In Viet Nam, the Project is developing tools that will be part of the key arsenal of environmental management tools over the coming decades. Indicators, EPI, valuation, SEA and land-use planning will, over the coming decade, play a vital role in environmental management in Vietnam. This will be seen at national level, and it will be increasingly the case at provincial and district levels. This will be seen increasingly across all socio-economic sectors. Hence, the tools that this Project helps to develop will be used for many years by many actors in Viet Nam, achieving large levels of replicability. The fact that the Project is working with the core environmental management actors enhances the chances of rapid replication. Capacity building and training will facilitate immediate replication.

- Moreover, the tools being developed, and the process to developing them, can be applied in many other countries. Similar tools will be developed and used throughout Southeast Asia. As with many other capacity developments, the Vietnamese experience will have some replicability particularly to Cambodia, Indonesia, Laos and Myanmar. UNDP will facilitate the sharing of these lessons with these neighboring other countries. UNDP will also facilitate the sharing of the lessons with other countries with similar environmental management capacity across Asia and the world.

- The PMU and project management will ensure that adaptive learning and capturing lessons are central to the project approach. This will feed into both the governmental and the UNDP knowledge management structures, ensuring future projects build on these.

### C.3.c	Risks and Mitigation Measures

- The Table below elaborates the risks and outlines the mitigation measures to be taken by the Project.

| Risk | Severity | Description And Risk Mitigation Measures |
| --- | --- | --- |
| Inadequate Government and other stakeholder commitment to the process. | Medium | Viet Nam has many socio-economic priorities, of which the highest is alleviating poverty and overcoming inequality. Environment is also a priority issue. However, the local environmental issues such as air pollution, water pollution, waste, etc, are given a higher priority than global issues Commitment to the global environment may take second place in the face of these socio-economic challenges. The Government, in the baseline, has the vision and commitment to protect environmental resources. On the 3rd June 2013, The Party Central Committee (PCC) approved the Decision number 24 – NQ /TW at the PCC 7 - XI meeting on actively respond to climate change, strengthening resource management and environmental protection. Hence, the Government, notably MONRE and ISPONRE, is committed to the baseline of the project. The approach taken is to integrate GEF firmly into the baseline, thereby trying to benefit from the Government’s commitment to the baseline. |
| Inadequate coordination mechanisms. | Medium | The various ministries and departments involved in implementing the Rio Conventions have undergone several restructurings in recent years. They have the mandate and commitment to collaboration and coordination, but in many cases they do not have the operational tools and mechanisms to collaborate/coordinate. This could undermine implementation of the project. This Project will bring all concerned parties together to work on the activities under the six outputs and two outcomes. This Project will demonstrate how coordination and collaboration can yield benefits for all concerned. Through this learning by doing approach, the Project will generate operational linkages across the concerned departments and ministries. |
| By attempting too much, the project may over-stretch its resources. | Medium-low | The Project has activities across several sub-sectors and in several technical areas. The overall GEF Project budget is limited. Hence, there is a danger that by trying to do too much, the Project will not be able to properly achieve anything. Firstly, the strategy is for the GEF funds to complement a strong baseline. Hence, the GEF provides a limited amount of additional funding. This should ensure cost-effectiveness and optimal use of GEF funds. Secondly, the Project is designed to be focused into specific, tangible results. The UNDP and MONRE will monitor this situation closely, and take corrective measures if necessary. |
| Inadequate quality and quantity of data and information | Low | The proposed activities require data and information to be of a certain quality. This quality may not be available in Vietnam. They also require a certain quantity of information. The implementing partner (ISPONRE) has been involved in many research programmes in the past, often in collaboration with international partners, and has access to databases and studies undertaken by MONRE. ISPONRE should be able to assure access to data and information. |
| It is difficult to use the new tools. | Low | The Project will develop new tools. However, there may not be sufficient capacity to use these tools. This is particularly a challenge at provincial levels of government. Training on application of new tools will be provided for different stakeholders |

## C.4	Stakeholder Involvement

- The Project Development process was highly consultative. The Table below describes each of the stakeholders consulted during project formulation, the key issues on which they were consulted, and their potential role in project implementation.

| Stakeholder | Issue on which consulted during project formulation | Potential Role in Project |
| --- | --- | --- |
| Governmental agencies |  |  |
| ISPONRE (MONRE) | All issues related to project implementation and management. | Contributes co-financing, expertise and guidance. Benefits from the improved tools and trained staff |
| General Department of Land Management (MONRE) | All issues related to Land-use planning and processes. | To cooperate in the activities concerning land-use issues. Benefits from the improved tools and trained staff. |
| Department of International Cooperation (MONRE) | The issues related to international cooperation. | To cooperate by helping to develop relationships with international partners. May benefit from the improved tools and trained staff |
| Viet Nam Environment Administration (VEA / MONRE) | The issues related to Strategic Environmental Assessment and the Convention on Biological Diversity (note, the Biodiversity Conservation Agency, under the VEA, is the Focal Point for the CBD) | To cooperate in the activities concerning SEA and UNCBD issues. Benefits from the improved tools and trained staff. |
| Department of Meteorology, Hydrology and Climate Change (MONRE) | The issues related to Climate Change. This Department is Focal Point of UNFCCC. | To cooperate in the activities concerning Climate change issues. Benefits from the improved tools and trained staff. |
| Viet Nam Administration of Forestry (VAF, in MARD) | The issues related to UN Convention to Combat Desertification. VAF is Focal Point of UNCCD. | To cooperate in the activities concerning UNCCD issues. Benefits from the improved tools and trained staff. |
| Research Institute for Forest Ecology and Environment (MARD) | The issues related to economic valuation of natural resources. | To cooperate in the activities concerning economic valuation issues. They have experience in economic valuation of for forestry resources. Benefits from the improved tools and trained staff |
| Support Program for Response to Climate Change | The issues related to Climate change | To assist in the activities of international cooperation on climate change |
| Provincial DONRE | Not yet (at this stage) | Benefits from trained personnel and better tools. |
| Academic and Vietnamese non-governmental agencies |  |  |
| Centre for Natural Resource and Environmental Studies (CRES) | To explore partnerships and linkages with CRES projects | Contributes co-financing and participates in many activities, notably under Output 1.2 |
| Center for Development of Community Initiative and Environment (C&E) | The issues related to Land- use and economic valuation of natural resources | To cooperate in activities concerning Land- use and economic valuation. Benefits from the improved tools and trained staff. |
| National Economics University | The issues related to economic valuation of natural resources | To cooperate in activities concerning economic valuation issues. Benefits from the improved tools and trained staff. |
| Hanoi National University | Not yet (at this stage) | Technical cooperation on a wide range of potential issues. |
| Ho Chi Minh National University | Not yet (at this stage) | Technical cooperation on a wide range of potential issues. |
| Institute of Meteorology, Hydrology and Environment | Not yet (at this stage) | Technical cooperation on a wide range of potential issues. |
| Ha Noi University for Natural Resources and Environment (under MONRE) | The issues related to economic valuation of natural resources. | To cooperate in activities concerning economic valuation issues. Benefits from the improved tools and trained staff. |
| International partners |  |  |
| WWF | To explore partnerships and linkages with WWF projects | Contributes co-financing, and participates in many activities, notably under Outcome 2. |
| UNDP | All issues related to project implementation and management. | Contributes co-financing, expertise and guidance. |
| German Government/GiZ | Is supporting ISPONRE/MONRE through parallel initiatives. Concerned experts were involved in project planning and design. | Are expected to continue to support ISPONRE/MONRE through parallel initiatives, and therefore concerned experts should continue to be involved in project planning and provide ongoing support. |

- The Project takes an adaptive and collaborative management approach to execution. Hence, the project will ensure that key stakeholders are involved early and throughout project execution as partners for development. This includes their participation in the Project Steering Committee, the review of project outputs such as recommendations for amendments to policies, plans, programmes and legislation, as well as participation in monitoring activities.

Approach to Gender Issues

- According to a recent World Bank led assessment, Viet Nam has recently made remarkable progress on gender equality, but important gender differences still remain. For example, Viet Nam has had considerable progress in addressing gender disparities in education, employment and health and gender gap in earnings is lower in Viet Nam than in many other East Asian countries. However, a number of challenges still remain, with challenges being most notable with marginalized, remote and poorer communities. There is also the need to sustain the gains made, e.g. regarding women's participation in leadership political positions and in the wider society.

- This project mainstreams gender issues into all pertinent activities. Gender considerations will become an integral part of all capacity built, all tools prepared, all training undertaken and all materials developed. This in particular with regards to Outputs 1.1, 1.2, 1.3, 2.1 and 2.2 (as seen in previous sections).

- Although this Project does not act directly at the grassroots level, this approach recognizes that in rural and remote areas, women are particularly vulnerable to resource degradation, in particular women with young children and female headed households. Hence, Outputs 1.1 and 1.3 will contribute to enhanced environmental management in rural areas, and the livelihoods of marginal population groups will be improved by the improved environmental management. Likewise, Outputs 2.1 and 2.2 will enhance national capacities to conduct SEA and land use planning which will reduce risks for marginal groups.

## C.5	Monitoring and Evaluation

- Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures.  The project team and the UNDP Country Office (UNDP-CO) will undertake monitoring and evaluation activities, with support from UNDP-GEF, including by independent evaluators in the case of the final evaluation. The logical framework matrix in Annex 6 provides a logical structure for monitoring project performance and delivery using SMART indicators during project implementation. The output budget and the work plan (in Annexes 7 and 8) provide additional information for the allocation of funds, both the GEF and co-financing, for expected project deliverables and the timing of project activities to produce these deliverables. Annex 7 provides a breakdown of the total GEF budget by outcome, project management costs, and allocated disbursements on a per year basis. A GEF tracking tool for CCCD(Annex 5) will be used as part of monitoring and evaluation activities to assess project delivery. The work plan is provisional, and is to be reviewed during the first project Steering Committee and endorsed at the project initiation workshop.

- The following sections outline the principle components of monitoring and evaluation. The project’s monitoring and evaluation approach will be discussed in the project’s inception report so as to fine-tune indicators and means of verification, as well as define M&E responsibilities amongst project staff.

- A project inception workshop will be conducted with the full project team, National Project Director, MONRE, ISPONRE, other relevant government partners, co-financing partners, the UNDP-CO, with representation from the UNDP-GEF Regional Coordinating Unit as appropriate. Non-governmental stakeholders should be represented at this workshop.

- One aim of this workshop will be to further develop understanding and ownership of the project’s goals and objectives among the project team, government and other stakeholder groups.  The workshop also serves to finalize preparation of the project’s first annual work plan on the basis of the project’s log-frame matrix. This will include reviewing the log frame (indicators, means of verification, assumptions), imparting additional detail as needed, and on the basis of this exercise, finalize the Annual Work Plan (AWP) with precise and measurable performance (process and output) indicators, and in a manner consistent with the expected outcomes for the project.

- Specifically, the project inception workshop will: (i) introduce project staff to the partners involved in the project, i.e. government counterparts, UNDP and co-financiers; (ii) detail the roles, support services and complementary responsibilities of UNDP-CO and Project Management Unit staff with respect to the project team; (iii) provide a detailed overview of UNDP-GEF reporting and monitoring and evaluation (M&E) requirements, with particular emphasis on the combined Annual Project Reports - Project Implementation Reviews (APR/PIRs), Project Steering Committee (PSC) meetings, as well as final evaluation. The inception workshop will also provide an opportunity to inform the project team on UNDP project-related budgetary planning, budget reviews, and mandatory budget re-phasing; (iv) review and as necessary update the project logical framework, to account for the most recent developments and opportunities in the sector.

- The inception workshop will also provide an opportunity for all parties to understand their roles, functions, and responsibilities within the project’s decision-making structures, including reporting and communication lines, and conflict resolution mechanisms.  The Terms of Reference for PMU staff and associated decision-making structures will be discussed again, as needed, in order to clarify for all, each party’s responsibilities during the project’s implementation phase.

- The inception workshop will present a schedule of M&E-related meetings and reports. The Project Manager in consultation with UNDP will develop this schedule, and will include: (i) tentative time frames for PSC meetings; and (ii) project-related monitoring and evaluation activities. The provisional work plan will be approved in the first meeting of the PSC.

- Day-to-day monitoring of implementation progress will be the responsibility of the Project Manager based on the project’s Annual Work Plan and its indicators. The Project Manager will inform the UNDP-CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

- The Project Manager will fine-tune outcome and performance indicators in consultation with the full project team at the inception workshop, with support from UNDP-CO and assisted by the UNDP-GEF. Specific targets for the first year implementation performance indicators, together with their means of verification, will be developed at the inception workshop. These will be used to assess whether implementation is proceeding at the intended pace and in the right direction and will form part of the Annual Work Plan. Targets and indicators for subsequent years will be defined annually as part of the internal evaluation and planning processes undertaken by the Project Team, and agreed with ISPONRE among other key project partners sitting on the PSC.

- Periodic monitoring of implementation progress will be undertaken by the UNDP-CO through the provision of quarterly reports from the Project Manager. Furthermore, specific meetings may be scheduled between the PMU, the UNDP-CO and other pertinent stakeholders as deemed appropriate and relevant (particularly the PSC members).  Such meetings will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

- Annual Monitoring will occur through the Annual Project Steering Committee meeting. This is the highest policy-level meeting of the parties directly involved in the implementation of a project. The project will be subject to PSC meetings at least twice per year. The first such meeting will be held within the first nine months following the inception workshop. For each year-end meeting of the PSC, the Project Manager will prepare harmonized Annual Project Report / Project Implementation Reviews (APR/PIR) and submit it to UNDP-CO, the UNDP-GEF Regional Coordination Unit, and all PSC members at least two weeks prior to the meeting for review and comments.

- The APR/PIR will be used as one of the basic documents for discussions in the PSC year-end meeting. The Project Manager will present the APR/PIR to the PSC members, highlighting policy issues and recommendations for the decision of the Committee participants. The Project Manager will also inform the participants of any agreement(s) reached by stakeholders during the APR/PIR preparation, on how to resolve operational issues. Separate reviews of each project output may also be conducted, as necessary. Details regarding the requirements and conduct of the APR and PSC meetings are contained with the M&E Information Kit available through UNDP-GEF.

- The terminal review meeting is held by the PSC, with invitation to other relevant Government and municipal stakeholders as necessary, in the last month of project operations. The Project Manager is responsible for preparing the terminal review report and submitting it to UNDP-COs, the UNDP-GEF Regional Coordinating Unit, and all participants of the terminal review meeting. The terminal review report will be drafted at least one month in advance of the terminal review meeting, in order to allow for timely review and to serve as the basis for discussion. The terminal review report considers the implementation of the project as a whole, paying particular attention to whether the project has achieved its stated objectives and contributed to the broader environmental objective. The report also decides whether any actions remain necessary, particularly in relation to the sustainability of project outputs and outcomes, and acts as a vehicle through that lessons learned can be captured to feed into other projects under implementation or formulation.  The terminal review meeting should refer to the independent final evaluation report, conclusions and recommendations as appropriate.

- The UNDP-CO, in consultation with the UNDP-GEF Regional Coordinator and members of the PSC, has the authority to suspend disbursement if project performance benchmarks are not met as per delivery rates, and qualitative assessments of achievements of outputs.

- A project inception report will be prepared immediately following the inception workshop. This report will include a detailed First Year Work Plan divided in quarterly time-frames as well as detailed activities and performance indicators that will guide project implementation (over the course of the first year). This Work Plan will include the proposed dates for any visits and/or support missions from the UNDP-CO, the UNDP-GEF Regional Coordinating Unit, or consultants, as well as time-frames for meetings of the project decision-making structures (e.g., PSC). The report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, and including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 month time-frame.

- The inception report will include a more detailed narrative on the institutional roles, responsibilities, coordinating actions and feedback mechanisms of project related partners. In addition, a section will be included on progress to date on project establishment and start-up activities and an update of any changed external conditions that may affect project implementation, including any unforeseen or newly arisen constraints. When finalized, the inception report will be circulated to project counterparts who will be given a period of one calendar month to respond with comments or queries.

- The combined Annual Project Report (APR) and Project Implementation Review (PIR)is a UNDP requirement and part of UNDP’s Country Office central oversight, monitoring and project management.  As a self-assessment report by project management to the Country Office, the APR/PIR is a key input to the year-end Project Steering Committee meetings. The PIR is an annual monitoring process mandated by the GEF. It has become an essential management and monitoring tool for project managers and offers the main vehicle for extracting lessons from on-going projects. These two reporting requirements are very similar in input, purpose and timing that they have now been amalgamated into a single APR/PIR Report.

- An APR/PIR is to be prepared on an annual basis for submission in June. It shall be prepared sufficiently in advance (at least one month) in order to be considered at the PSC meeting. The purpose of the APR/PIR is to reflect progress achieved in meeting the project’s Annual Work Plan and assess performance of the project in contributing to intended outcomes through outputs and partnership work.  The APR/PIR is discussed by the PSC, so that the resultant report represents a document that has been agreed upon by all of the key stakeholders.

- A standard format/template for the APR/PIR is provided by UNDP-GEF. This includes the following:

- An analysis of project performance over the reporting period, including outputs produced and, where possible, information on the status of the outcome;

- The constraints experienced in the progress towards results and the reasons for these;

- The three (at most) major constraints to achievement of results;

- Annual Work Plans and related expenditure reports;

- Lessons learned; and

- Clear recommendations for future orientation in addressing key problems in lack of progress.

- UNDP will analyze the individual APR/PIRs by focal area, theme and region for common issues/results and lessons. The APR/PIRs are also valuable for the independent evaluators who can utilize them to identify any changes in the project’s structure, indicators, work plan, among others, and view a past history of delivery and assessment.

- Quarterly Progress Reports are short reports outlining the main updates in project performance, and are to be provided quarterly to the UNDP Country Office. UNDP-CO will provide guidelines for the preparation of these reports, which will be shared with the UNDP-GEF Regional Coordination Unit (RCU).

- Progress made shall be monitored in the UNDP Enhanced Results Based Managment Platform.

- Based on the initial risk analysis submitted, the risk log shall be regularly updated in ATLAS.  Risks become critical when the impact and probability are high.  Note that for UNDP GEF projects, all financial risks associated with financial instruments such as revolving funds, microfinance schemes, or capitalization of ESCOs are automatically classified as critical on the basis of their innovative nature (high impact and uncertainty due to no previous experience justifies classification as critical).

- Based on the information recorded in Atlas, a Project Progress Reports (PPR) can be generated in the Executive Snapshot.

- Other ATLAS logs can be used to monitor issues, lessons learned etc. The use of these functions is a key indicator in the UNDP Executive Balanced Scorecard.

- During the final three months of the project, the PMU will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs of the project, lessons learned, the extent to which objectives have been met, structures and mechanisms implemented, capacities developed, among others. Together with the independent final evaluation, the project terminal report is one of two definitive statements of the project’s activities during its lifetime. The project terminal report will also recommend further steps, if necessary, in order to ensure sustainability and replicability of the project outcomes and outputs.

- An independent final evaluation will take place three months prior to the terminal Project Steering Committee meeting, and will focus on: a) the cost-effectiveness, efficiency and timeliness of project implementation and performance; b) highlighting issues requiring decisions and actions; and c) presenting initial lessons learned about project design, implementation and management. Findings of this evaluation will be adopted as lessons learned, and recommendations for follow-up action addressed to ensure the institutional sustainability of project outputs, particular for the replication of project activities. The final evaluation will also look at project outcomes and their sustainability. The terms of reference for the final evaluation will be prepared by the UNDP-CO based on guidance from the UNDP-GEF Regional Coordinating Unit, in consultation with ISPONRE.

- The Project Manager will provide the UNDP Resident Representative with certified periodic financial statements and an annual audit of the financial statementsrelating to the status of UNDP (including GEF) funds according to the established procedures set out in UNDP’s Programming and Finance manuals.  The audit will be conducted by the legally recognized auditor of UNDP Vietnam. Audit on project will follow UNDP Financial Regulations and Rules and applicable Audit policies.

- Learning and knowledge sharing: Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing networks and forums.

The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

- Communications and visibility requirements: Full compliance is required with UNDP’s Branding Guidelines.  These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at:http://intra.undp.org/branding/useOfLogo.html.  Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects needs to be used.  For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF logo. The GEF logo can be accessed at: http://www.thegef.org/gef/GEF_logo. The UNDP logo can be accessed at http://intra.undp.org/coa/branding.shtml.

Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”). The GEF Guidelines can be accessed at: http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf. Amongst other things, the GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment.  The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.  Where other agencies and project partners have provided support through co-financing, their branding policies and requirements should be similarly applied.

- The following table summarizes the monitoring and evaluation activities and estimated costs.

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | - ISPONRE - Project Manager - UNDP CO, UNDP GEF | Indicative cost: 10,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. Estimated $5-10,000. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Manager - Project team | To be determined as part of the Annual Work Plan's preparation. Estimated $5-10,000. | Annually prior to ARR/PIR and to the definition of annual work plans |
| ARR/PIR | - ISPONRE - Project manager and team - UNDP CO - UNDP RTA - UNDP EEG | None | Annually |
| Periodic status/ progress reports | - Project manager and team | None | Quarterly |
| Mid-term Evaluation | - Project manager and team - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Not Required for MSP project | At the mid-point of project implementation. |
| Final Evaluation | - Project manager and team, - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Indicative cost : 30,000 | At least three months before the end of project implementation |
| Project Terminal Report | - Project manager and team - UNDP CO - local consultant | 0 | At least three months before the end of the project |
| Audit | - UNDP CO - Project manager and team | Indicative cost per year: 3,000 | Yearly |
| Visits to field sites | - UNDP CO - UNDP RCU (as appropriate) - Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses |  | Estimated $59,000 - 69,000. |  |

# D.	Financing

## D.1	Financing Plan

- The financing of this project will be provided by the GEF, with co-financing from the Government of Viet Nam, UNDP, WWF and CRES. The allocation of these sources of finances is structured by the two main project components, as described in section C.2.b above.

- The following Tables provide information on:

- The allocation of GEF and co-financing across components/outcomes;

- The allocation of GEF and co-financing to project management and use of these funds by input.

Table:  Project Costs (US$)

| Total Project Budget by Component | GEF ($) | Co-Financing ($) | Project Total ($) |
| --- | --- | --- | --- |
| Component 1/Outcome 1 | 484,000 | 1,199,500 | 1,683,500 |
| Component 2/Outcome 2 | 411,000 | 295,000 | 706,000 |
| Project Management | 80,000 | 110,000 | 190,000 |
| Total project costs | 975,000 | 1,604,500 | 2,579,500 |

Total budget and workplan

| Award ID: | 00079893 | Project ID(s): | 00089760 |
| --- | --- | --- | --- |
| Award Title: | Country Name Project Title: Viet Nam - Enhancing Capacity for Implementing Rio Conventions |  |  |
| Business Unit: | VNM 10 |  |  |
| Project Title: | Country Name Project Title: Viet Nam - Enhancing Capacity for Implementing Rio Conventions |  |  |
| PIMS no.5099 |  |  |  |
| Implementing Partner (Executing Agency) | Institute of Strategy and Policy on Natural Resources and Environment (ISPONRE) of the Ministry of Natural Resources and Environment (MONRE) |  |  |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 2014 (USD) | Amount Year 2015 (USD) | Amount Year 2016 (USD) | Total (USD) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: Vietnam has the environmental management tools that fully address global environmental concerns | ISPONRE | 62000 | GEF | 71200 | International Consultants | $43,890 | $47,880 | $41,230 | $133,000 | 1 |
|  |  |  |  | 71300 | Local Consultants | $56,100 | $61,200 | $52,700 | $170,000 | 2 |
|  |  |  |  | 757000 | Training, Workshops and Confer | $44,880 | $48,960 | $42,160 | $136,000 | 3 |
|  |  |  |  | 72100 | Contractual services - Companies | $9,900 | $10,800 | $9,300 | $30,000 | 4 |
|  |  |  |  | 72200 | Equipment and Furniture – Office supplies | $4,950 | $5,400 | $4,650 | $15,000 | 5 |
|  |  |  |  |  | Sub-total GEF | $159,720 | $174,240 | $150,040 | $484,000 |  |
|  |  |  |  |  | sub-total ISPONRE | $100,000 | $150,000 | $150,000 | $400,000 |  |
|  |  |  |  |  | sub-total CRES | $19,500 | $40,000 | $40,000 | $99,500 |  |
|  |  |  |  |  | sub-total WWF | $10,000 | $20,000 | $20,000 | $50,000 |  |
|  |  |  |  |  | sub-total UNDP | $150,000 | $250,000 | $250,000 | $650,000 |  |
|  |  |  |  |  | sub-total co-financing | $279,500 | $460,000 | $460,000 | $1,199,500 |  |
|  |  |  |  |  | Total Outcome 1 | 439,220 | $634,240 | $610,040 | $1,683,500 |  |
| OUTCOME 2: Vietnam is integrating global environmental concerns into its national strategic planning and development processes. | ISPONRE | 62000 | GEF | 71200 | International Consultants | $11,880 | $12,960 | $11,160 | $36,000 | 1 |
|  |  |  |  | 71300 | Local Consultants | $56,100 | $61,200 | $52,700 | $170,000 | 2 |
|  |  |  |  | 72100 | Contractual services - companies | $9,900 | $10,800 | $9,300 | $30,000 | 4 |
|  |  |  |  | 72200 | Equipment and Furniture | $4,950 | $5,400 | $4,650 | $15,000 | 5 |
|  |  |  |  | 75700 | Training, Workshops and Confer | $52,800 | $57,600 | $49,600 | $160,000 | 3 |
|  |  |  |  |  | Sub-total GEF | $135,630 | $147,960 | $127,410 | $411,000 |  |
|  |  |  |  |  | sub-total ISPONRE | $35,000 | $70,000 | $60,000 | $165,000 |  |
|  |  |  |  |  | sub-total CRES | $10,000 | $10,000 | $10,000 | $30,000 |  |
|  |  |  |  |  | sub-total WWF | $30,000 | $40,000 | $30,000 | $100,000 |  |
|  |  |  |  |  | sub-total UNDP | 0 | 0 | 0 | $0 |  |
|  |  |  |  |  | Sub-total co-financing | $75,000 | $120,000 | $100,000 | $295,000 |  |
|  |  |  |  |  | Total Outcome 2 | $210,630 | $267,960 | $227,410 | $706,000 |  |
| Project management unit | ISPONRE | 62000 | GEF | 71300 | Local Consultants | $10,560 | $11,520 | $9,920 | $32,000 | 2 |
|  |  |  |  | 74100 | Professional Services – Audit | $3,000 | $3,000 | $3,000 | $9,000 | 8 |
|  |  |  |  | 75700 | Training, Workshops and Confer | $5,280 | $3,460 | $2,960 | $11,700 | 6 |
|  |  |  |  | 72200 | Equipment and Furniture | $990 | $1,080 | $930 | $3,000 | 5 |
|  |  |  |  | 74599 | UNDP-cost recovery charges Bills | $8,100 | $8,100 | $8,100 | $ 24,300 | 7 |
|  |  |  |  |  | Sub-total GEF | $27,930 | $27,160 | $24,910 | $80,000 |  |
|  |  |  |  |  | sub-total ISPONRE | $8,000 | $9,000 | $8,000 | $25,000 |  |
|  |  |  |  |  | sub-total CRES | $3,000 | $4,000 | $3,146 | $10,146 |  |
|  |  |  |  |  | sub-total WWF | 0 | 0 | 0 | $0 |  |
|  |  |  |  |  | sub-total UNDP | $25,000 | $25,000 | $25,000 | $75,000 |  |
|  |  |  |  |  | Sub-total co-financing | $36,000 | $38,000 | $36,146 | $110,146 |  |
|  |  |  |  |  | Total Project Management | $63,930 | $65,160 | $60,910 | $190,000 |  |
|  |  |  |  | GEF PROJECT TOTAL |  | $323,280 | $349,360 | $302,360 | $975,000 |  |
|  |  |  |  | Co-financing TOTAL |  | $390,500 | $618,000 | $596,146 | $1,604,646 |  |
|  |  |  |  | Project TOTAL |  | $713,780 | $967,360 | $898,506 | $2,579,646 |  |

Budget notes:

1	International Consultants cost: ToRs prepared for each expert in Annex 9. 1 m/m including all costs estimated at $18,000, including M&E cost

2	Local Consultants cost: ToRs prepared for each expert in Annex 9. 1 m/m including all costs estimated at $2,500

3	Mostly training for provincial governmental and non-governmental staff. Each training workshop estimated to cost $8000

4	Sub-contracts  used to collect data/information to prepare Outputs 1.1, 1.2 and 2.1, 2.2

5	Equipment to support technical activities. Office equipment and supplies, monitoring equipment, etc.

6	Inception workshop and planning workshops

7	Direct project services, as per LoA attached

8            Audit fee, yearly, 3x$3,000

- An independently recruited consultant will be contracted to undertake the independent final evaluation towards the end of the project.  The travel budget includes the costs of DSA, TE and return airfare for the international consultants.  The travel budget also includes financing for to cover the cost of local consultant travel to the regions where they will be facilitating the negotiations and drafting of sectoral policy, programmes, plans, or legislation.

- No UNDP Implementing Agency services are being charged to the Project Budget. All such costs are being charged to the IA fee. The Government of Viet Nam has requested UNDP to provide a few execution services (including procurement and recruitment) under the National Execution Arrangements, and these will be charged to the Project Budget. Details of such charges can be provided at the time these services are requested.

## D.2	Cost Effectiveness

- In line with GEF strategy, the GEF finances only the ‘incremental costs’ of achieving the global environmental benefits. This means that the UNDP/GEF project builds on top of a significant baseline. The UNDP/GEF project will influence investments by both government and development partners, and will have an impact beyond the limited GEF contribution.

- For both Outcomes, the strategic use of GEF funds is to mainstream into/onto ongoing processes and to modify them in order to yield global environmental benefits, this is far more cost-effective than if GEF was to support the entire initiative.

- In Outcome 1, there is a large baseline supported by UNDP, ISPONRE and other partners, addressing the issues of indicator systems, resource valuation and EPI. Almost all the EPI related outputs is covered by UNDP. GEF supports additional activities and inputs to ensure the Rio Conventions are integrated into the baseline

- Outcome 2 includes work on SEA. The vast majority of work on SEA is covered by government and ADB. The GEF funds support additional activities and inputs to ensure the Rio Conventions are integrated into the baseline process.

- GEF contribution to management costs is limited to $80,000, or 8.2% of all GEF funds. This is 3.1% of the entire Project costs. See Table.

Table: Project Costs by Components as percentage

| Project Budget Component by Contribution type | Contribution (US$) | Percentage (%) |
| --- | --- | --- |
| Component 1: GEF | $484,000 | 19% |
| Component 1: Co-Financing | $1,199,500 | 47% |
| Component 2: GEF | $411,000 | 16% |
| Component 2: Co-Financing | $295,000 | 11% |
| Project Management: GEF | $80,000 | 3% |
| Project Management: Co-Financing | $110,146 | 4% |
| Total |  | 100 |

- In almost all cases, GEF activities fill gaps and make connections, rather than supporting an entire process or complete initiative.

- Several alternative designs and approaches were considered for cost-effectiveness during project design. These alternatives included providing more hardware and focusing all capacity development efforts on national government agencies. Ultimately, it was decided that these approaches would not have as much impact per input, hence the chosen focus of developing the capacity of the local governments through a learning-by-doing approach, and of focusing on data and information management.

- The Project also intends to minimize the use of international consultants where national expertise is available. This will reduce the travel costs and the costs of consultancy fees. Notwithstanding, where international expertise is unique or exceptionally credible, it will be utilized.

## D.3	Co-financing

- The main partners and co-financers are ISPONRE, UNDP, CRES and WWF.

- ISPONRE will provide $150,000 support in kind, providing project staff, office facilities, experts, meeting facilities, supporting communications, etc. ISPONRE is also providing $440,000 grant support through two projects: (i) “investigation, assessment and piloting of environmental performance ranking in Viet Nam”.  This project focuses on developing a methodology for environmental performance ranking, and piloting it in several provinces, and (ii) “Development of methodology for integration of natural resource master plans in regional land-use planning in Vietnam”. This project support land-use planning processes.

- UNDP will provide $725,000 of grant co-financing through the project “Support Strengthening Capacity on Natural Resources and Environment Policy Development and Environmental Performance”. This project contributes directly to the delivery of Output 1.3, covering most of the costs.

- CRES will provide $60,000 support in kind, providing project staff, office facilities, experts, meeting facilities, supporting communications, etc. CRES will also provide approximately $79,646 in grant support through the project “Sustainable Use of Cam Thanh Nypa Wetlands, Hoi An city, Quang Nam Province”.

- WWF will provide $100,000 in grant support and $50,000 in-kind support, providing project staff, office facilities, experts, meeting facilities, support communications etc. thought the following projects: 1) Annamites Carbon Sinks and Biodiversity (CarBi project): towards the protection and management of trans-boundary forest area rich in carbon and biodiversity” (funded by KFW, Germany): Forest and species monitoring indicators. 2) Policy forum in the Mekong Delta to promote more sustainable development planning (funded by HSBC).3) Promoting certification & better Management practice among small scale shrimp farmer in Vietnam (environmental standards for responsible shrimp production – ASC standards for shrimp aquaculture). 4) Establishing A Sustainable Supply Chain for Pangasius in Vietnam (environmental standards for pangaius production – ASC standards for pangasius). 5) Strengthening biodiversity conservation and improving dependent local livelihoods through community based natural resource use and management in Tram Chim National Park (funded by Coca Cola).

Table 8:  Co-financing Sources

| Name of Co-financier | Classification | Type | Amount |  |
| --- | --- | --- | --- | --- |
|  |  |  | Confirmed (US$) | Unconfirmed (US$) |
| ISPONRE | Government | Grant | 440,000 | 0 |
| ISPONRE | Government | In-Kind | 150,000 | 0 |
| UNDP | GEF Implementing Agency | Grant | 725,000 | 0 |
| CRES | NGO | Grant | 79,646 | 0 |
| CRES | NGO | In-Kind | 60,000 | 0 |
| WWF | NGO | Grant | 100,000 | 0 |
| WWF | NGO | In-Kind | 50,000 | 0 |
| Total Co-financing |  |  | 1,604,646 | 0 |

# E.	Institutional Coordination and Support

## E.1	Core Commitments and Linkages

### E.1.a	Linkages to other activities and programmes

- The key linked activities are the projects financed by UNDP, CRES and WWF which co-finance the project Outputs

- UNDP Project:Strengthening Capacity on Natural Resources and Environment Policy Development and Environmental Performance, implemented by MONRE/IsponrE. This project will assist in strengthening the policy framework and effective implementation of policies, through helping to enhance capacity to undertake evidence-based policy research and providing quality inputs to planning and policy-making, through the formulation, promotion and application of new policies, and tools and market mechanisms that strengthen natural resources and environment (NRE) law and policy implementation. Specifically, the project will assist in formulating more comprehensive and highly consistent natural resources and environmental protection laws and policies, from revising the old, and formulating new policies, laws and regulations, filling in legislative gaps for the control of air pollution and enhancing resource efficiency, and strengthening integrated coastal zone management. New tools and market mechanisms to improve environmental performance of provinces and sectors will be developed to reinforce the implementation of new laws and regulations. Research and policy analysis will be conducted to provide quality inputs for planning and policy formulation. The project will also enhance capacity of relevant research institutions and authorities to formulate and undertake evidence-based policy analysis.

- The expected results are:

- enhanced capacity of relevant authorities and research institutions to undertake evidence-based policy analysis to provide quality inputs for planning and policy formulation;

- more comprehensive and highly consistent NRE laws and policies (either resulting from revising the old laws and regulations or formulating new policies, i.e. upgrading law and policy for environmental protection and efficient natural resource use, effecting reduced pollution and waste; strengthened policy and regulatory environment governing seas and island and coastal areas and mineral resource extraction); and

- improved environmental performance at provincial or sectoral level by introducing and applying new tools and mechanisms to reinforce the implementation of the laws and regulations. This latter includes the support to EPI and ranking.

- CRES is implementing the project on “Sustainable Use of Cam Thanh Nypa Wetlands, Hoi An city, Quang Nam Province”. The project focuses on raising awareness and capacity on sustainable use of Nypa wetlands of stakeholders and developing a model of community based ecotourism for Cam Thanh Commune, Hoi An city, Quang Nam province. This is directly related to the development of capacity for natural resource accounting under Outcome 1.

- WWF is implementing five projects for protecting carbon sinks, biodiversity and forest areas. WWF is furthermore supporting sustainable development planning in Mekong Delta, promoting environmental standards for shrimp farmers, working with sustainable supply chain management and of pangasius production, and promoting biodiversity conservation through community based natural resource use and management in Tram Chim National Park. WWF’s project activities are related to provincial application of SEA and integrated land-use planning, mostly under Outcome 2.

- UNDP is also supporting a series of related initiatives. The project “Strengthening National Capacities to Respond to Climate Change in Vietnam, Reducing Vulnerability and Controlling GHS Emissions (2009 – 2012)” focuses on the formulation of climate change policies and strengthening national research capacity to carry out analysis for evidence-base planning and policy development. The project “Strengthening Sustainable Development and Climate Planning (2010 – 2014)” supports the Government to integrate sustainable development and climate change into national social and economic development plans and investments, and to develop a Green Growth Strategy.

- The United Nations Collaborative Programme on Reducing Emissions from Deforestation and Forest Degradation in Developing Countries (UN-REDD Programme in Vietnam) focuses its support on application of various approaches to reducing GHGs emissions, increasing forestation and at the same time protecting land from degradation.

- In addition the following-financed projects are highly relevant:

- GEF-UNEP (global) project “Project for Ecosystem Services” (implemented in Viet Nam by MONRE/ISPONRE) aims to reduce threats to globally important biodiversity through integrating the findings and tools of ecosystem service assessments into policy and decision making. ISPONRE will ensure coordination and collaboration with this initiative;

- GEF-UNDP project: "Removing barriers hindering PA effectiveness" and GEF-UNDP project "Conservation of critical wetland PAs and linked landscapes". Both focus on protected areas management. The former supports Viet Nam in sustainable financing for protected areas to contribute to effectively biodiversity conservation in Viet Nam, while the latter addresses wetlands conservation linked with landscapes management; and

- UNDP is presently working with Viet Nam Environmental Administration (VEA, i.e. the CBD Focal Point) on a GEF-financed project to update the National Biodiversity Strategic Action Plan (NBSAP).

- The following are also relevant:

- MONRE is currently conducting a government-funded project on the application of market-based approach for natural resources management. Under that project, the approach and methodology for application of valuation for natural resources has been developed and it will be used as input for further development of the tools. The present proposed project will use results from that project as an input to further study and capacity building.

- MONRE is also implementing a government funded project on “Development of legal framework for promoting green growth in Viet Nam”. One of the components of this project is to develop criteria for assessment and monitoring of green growth in Viet Nam.

- Funded by the German Government (BMZ), the GIZ project entitled “Preservation of Biodiversity in the Forest Ecosystem in Vietnam”, running until 2020, is divided into three phases. The first phase, from 2010 – 2013, focused on biodiversity assessment in relation to climate change, capacity building, and the establishment of monitoring and evaluation systems that can support biodiversity conservation of forest eco-systems. This phase will be followed by an extended GIZ program entitled ‘Conservation and sustainable use of biodiversity and ecosystem services of forests in Vietnam’ (2014 –2016).

- UNDP and/or ISPONRE are involved in most of the above initiatives, and will take the lead in ensuring collaboration and avoiding duplication.

- The ADB, through Technical Assistance TA 7566-REG: “Strengthening and Use of Country Safeguard Systems” is supporting in Viet Nam “Capacity Development for the Implementation of the New Environment Decree” (2010 – 2013). This notably supports the SEA system and processes in Viet Nam. This is leading to the four following outputs for Viet Nam’s safeguards systems.

- Recommendations on the General Implementing Circular on Strategic Environmental Assessment, Environmental Impact Assessment, and Environmental Protection Commitments;

- Assessment of institutional capacity needs for implementing the above General Circular of the revised Decree;

- Country Safeguard System Capacity Action Plan (CAP) for strengthening implementation of new assessment procedures and general circular; and

- Launched implementation of the CAP in priority areas.

## E.2	Implementation and Execution Arrangements

- UNDP is the GEF Implementing Agency for this project, with the UNDP Country Office responsible for transparent practices, appropriate conduct and professional auditing.

- The Executing Agency is the Institute of Strategy and Policy on Natural Resources and Environment (ISPONRE) of the Ministry of Natural Resources and Environment (MONRE). ISPONRE will assign a senior staff member as National Project Director (NPD) and provide its staff and network of experts as support to Project Management Unit (as part of government co-financing).

- The Project contributes directly to the One United Nations Plan in Vietnam, 2012 - 2016. It notably contributes to Outcome 1.4 (by 2016, key national and sub-national agencies, in partnership with the private sector and communities, implement and monitor laws, policies and programmes for more efficient use of natural resources and environmental management, and implement commitments under international conventions).

- The Project implementation structure will include the following:

- Steering Committee (PSC);

- A Project Management Unit (PMU).

Project Steering Committee

- The PSC is specifically established by the project to provide management oversight of project activities. The PSC will make all necessary decisions and provide guidance for implementation of project activities, including approval of the overall project work-plan, and budget revisions. The Committee will review progress and evaluation reports, and approve programmatic modifications to project execution, as appropriate and in accordance to UNDP procedures.

- The PSC will consist of members representing MONRE, ISPONRE, MARD and UNDP. Co-financers will be represented on the Steering Committee, but will not have voting rights regarding use of GEF/UNDP funds. The Vice Minister in MONRE will chair the PSC. The Director of ISPONRE will be the Deputy Chair. The PSC will meet every six months, or more often on an ad-hoc basis as needed. The PSC will meet within at most 9 months of the Inception Workshop.

Government Agency/National Implementation Agency (ISPONRE)

- ISPONRE will be accountable to the Government and UNDP for ensuring: (i) the substantive quality of the project; (ii) the effective use of both national and UNDP resources; (iii) the availability and timeliness of the national contributions to support project implementation and; (iv) proper coordination among all project stakeholders.

- ISPONRE will appoint a senior official to act as National Project Director (NPD, see below).

- Under the NPD, ISPONRE will establish a project management unit (PMU) to be responsible for day-day management (see below).

- National Project Director:  A senior government official from ISPONRE will be designated as the National Project Director (NPD), and will be responsible for management oversight of the project.  The NPD will devote a significant part of his/her working time on the project.  Duties and responsibilities of the NPD are described in Annex 9. In the fulfillment of his/her responsibilities, the NPD will be supported by the Project Steering Committee and a full-time National Project Manager (NPM).

- Project Management Unit:  ISPONRE will establish a Project Management Unit (PMU) for the day-to-day management of project activities. The PMU will be administered by a full-time National Project Manager (NPM) and supported by financial and logistics assistant.

- The PMU is responsible for the following:

- Preparing an inception report with detailed work plan;

- Supporting the PSC and translating the guidance and decisions of the PSC into day-day project coordination and management;

- Providing technical support to ISPONRE, MONRE and MARD and other stakeholders for implementation efforts to achieve the project outcomes;

- Mobilizing technical assistance in support of the achievements of all project outcomes;

- Undertaking project monitoring, budget management, detailed work planning (annual, quarterly) and fulfilling reporting requirements to government and international donors.

- The PMU will be hosted in the ISPONRE building and will comprise the following positions:

- NPD (part time, financed by government);

- National Project Manager (full time, financed by project);

- Finance and procurement and logistical support staff (full time, financed by project).

- Consultants:  The project will hire national and international consultants as necessary to achieve the substantive aims of the Project. Outline TOR are provided in Annex 9.

- Capacity Development Activities: The project will take an adaptive collaborative management (ACM) approach to implementation. That is, ISPONRE and UNDP will manage project activities in order that stakeholders are involved early and throughout project implementation, providing regular input of the performance of project activities. This will help signal unforeseen risks and contribute to the timely modification and realignment of activities within the boundaries of the project's goal and objectives.

- Technical Working Group: A working group comprised of independent experts, technical government agency representatives, as well as representatives from stakeholder groups will discuss and deliberate on all project outputs, help design project activities, help mobilize resources to project.

- GEF Visibility: Visibility of GEF financial support will be ensured by using the global GEF branding in all electronic and printed materials.  The GEF logo will appear on all relevant project publications, including amongst others, project hardware and other purchases with GEF funds. Any citation in publications regarding projects funded by GEF will acknowledge the GEF.  Logos of the Implementing Agencies and the Executing Agency will also appear on all publications.  Where other agencies and project partners have provided support (through co-financing) their logos may also appear on project publications.  Full compliance will be made with the GEF’s Communication and Visibility Guidelines.

# F.	Legal Context

Standard Basic Assistance Agreement (SBAA)

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA [or other appropriate governing agreement] and all CPAP provisions apply to this document.

Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

# PART II:	ANNEXES

## Annex 1:	(Draft) Law on Environmental Protection

See separate Word file

## Annex 2: 	List of laws, policies and decisions related to biodiversity, climate change and land degradation, POPS and international waters

See separate Word file

## Annex 3: 	Additional Information on Environmental Indicators

See separate Word file

## Annex 4: 	List of Strategies, Master Plans and Spatial Plans Which Requirea Detailed SEA

See separate Word file

## Annex 5:	Capacity Development Scorecard

See separate Word file

## Annex 6:	Logical Framework

See separate Word file

## Annex 7:	Outcome Budget (GEF Contribution and Co-financing)

See separate Word file

## Annex 8:	Provisional Work Plan

See separate word file

## Annex 9:	Terms of References

See separate word file.

## Annex 10:	Environmental and Social Review Criteria

See separate Word file

## Annex 11:	PDF/PPG Status Report

| PPG Grant Approved at PIF: |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF/LDCF/SCCF/NCIF/ Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent to Date (9.12.13) | Amount Committed |
| International Consultant | 17,500 | 0 | 17,500 |
| National Consultant | 7,350 | 0 | 6,900 |
| Misc. | 150 | 0 | 600 |
| TOTAL | 25,000 | 0 | 25,000 |

## Annex 12:	Standard letter of agreement between UNDP and the Government of Vietnam

for the provision of support services

# PART III:	GEF Letters of Endorsement and Co-Financing

Annex A    GEF Endorsement Letter

Annex B    Letters of Co-Financing

Also referred to as the ‘Bien Dong Sea’.

UNFCCC COP 13

ADB Project Preparatory Technical Assistance (PPTA) 7215-VIE Interim Report (2009)

The following draws from Review and update of the mobilization and implementation of GEF projects in Viet Nam, submitted by the Government of Vietnam to GEF in 2010

Broadly similar to an economic exclusion zone.

Source: Convention on Biological Diversity (http://www.cbd.int/countries/profile/default.shtml?country=vn#facts)

One ton CO2eq is the amount of the concerned green house gas with the equivalent global warming potential as one ton of CO2

Source: Vietnam’s Second National Communication to the UNFCCC (2010).

The following draws from Review and update of the mobilization and implementation of GEF projects in Viet Nam, submitted by the Government of Vietnam to GEF in 2010.

This includes 5 municipalities having the same status as provinces.

Source: Implementation of Sustainable Development in Vietnam: National Report at the United Nations Conference on Sustainable Development (Rio+20) (Government of Viet Nam, 2012)

Table is copied from the NCSA report. Italicized sections have been edited for clarity.

This to be mostly covered by co-financing

See draft law in Annex 1 (Chapter 2, Section 1) for full details.

For example, currently, forest cover and land use maps are not available for all districts and communes. Where available, they were established in different times at different scales and formats based on different input data. Hence, the maps and data are not synchronized, causing difficulties in monitoring changes of forest cover and land use over periods of time. The consistency of published data and maps is also low. For example, MONRE, MARD and General Department of Statistics all provide information of forest areas, but the data they give may differ largely and confuse users. (Source: baseline study of GIZ CCCEP program).

World Bank. 2011. Vietnam - Country gender assessment.

See http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf.