request for

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

part i: project information

| Project Title: Enhancing Capacity for Implementing Rio Conventions |  |  |  |
| --- | --- | --- | --- |
| Country(ies): | Viet Nam | GEF Project ID: | 5097 |
| GEF Agency(ies): |  | GEF Agency Project ID: | 5099 |
| Other Executing Partner(s): | Institute of Strategy and Policy on Natural Resources and Environment (ISPONRE) of the Ministry of Natural Resources and Environment (MONRE) | Submission Date: | 2014-04-29 |
| GEF Focal Area (s): |  | Project Duration(Months) | 36 |
| Name of Parent Program (if applicable): - For SFM/REDD+ - For SGP - For PPP |  | Project Agency Fee ($): | 92,625 |

- Focal Area Strategy framework

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | Trust Fund | Grant Amount ($) | ### Cofinancing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | 1. Vietnam has environmental management tools that fully address global environment concerns. | 1.1 A set of indicators to monitor environmental status and pressure developed 1.2. Economic valuation of environmental and natural resources, and capacity to undertake this valuation 1.3: Environmental performance indices (EPI) developed and monitored, in line with international standards |  | 484,000 | 1,199,500 |
|  | 2. Vietnam is integrating global enviroment concerns into its national strategic planning and development processes. | 2.1: Increased capacity to undertake strategic environmental assessment (SEA) 2.2: Increased capacity to undertake integrated land-use planning 2.3: Formal institutionalized commitment in the form of a Government Decision to SEA and integrated land-use planning |  | 411,000 | 295,000 |
|  | Project Management |  |  | 80,000 | 110,146 |
| Total project costs |  |  |  | 975,000 | 1,604,646 |

- Project Framework

| ### Project Objective: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Grant Amount ($) | ### Confirmed Cofinancing ### ($) |
| Develop and pilot innovative tools for global benefits |  | 1. Vietnam has environmental management tools that fully address global environment concerns. | 1.1 A set of indicators to monitor environmental status and pressure developed 1.2. Economic valuation of environmental and natural resources, and capacity to undertake this valuation 1.3: Environmental performance indices developed and monitored, in line with international standards |  | 484,000 | 1,199,500 |
| National decision-making and planning for global benefits |  | 2. Vietnam is integrating global enviroment concerns into its national strategic planning and development processes. | 2.1: Increased capacity to undertake strategic environmental assessment (SEA) 2.2: Increased capacity to undertake integrated land-use planning 2.3: Formal institutionalized commitment in the form of a Government Decision to SEA and integrated land-use planning |  | 411,000 | 295,000 |
| Subtotal |  |  |  |  | 895,000 | 1,494,500 |
| Project management Cost (PMC) |  |  |  |  | 80,000 | 110,146 |
| Total project costs |  |  |  |  | 975,000 | 1,604,646 |

- sources of confirmed Cofinancing for the project by source and by name ($)

Please include letters confirming cofinancing for the projeSct with this form

| Sources of Co-financing | Name of Co-financier (source) | Type of Cofinancing | Cofinancing Amount ($) |
| --- | --- | --- | --- |
|  | ISPONRE |  | 440,000 |
|  | ISPONRE |  | 150,000 |
|  | UNDP |  | 725,000 |
|  | CRES |  | 79,646 |
|  | CRES |  | 60,000 |
|  | WWF |  | 100,000 |
|  | WWF |  | 50,000 |
| Total Co-financing |  |  | 1,604,646 |

- trust fund Resources Requested by agency, Focal Area  and country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
|  |  |  | Viet Nam | 975,000 | 92,625 | 1,067,625 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 975,000 | 92,625 | 1,067,625 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide information for this
    table.  PMC amount from Table B should be included proportionately to the focal area amount in this table.

2   Indicate fees related to this project.

- Consultants working for technical assistance components:

| ### Component | ### Grant Amount ($) | ### Cofinancing ($) | ### Project Total ($) |
| --- | --- | --- | --- |
| ### International Consultants | 169,000 | 250,000 | 419,000 |
| ### National/Local Consultants | 372,000 | 400,000 | 772,000 |

- Does the project include a “non-grant” instrument?

(If non-grant instruments are used, provide in Annex D an indicative calendar of expected reflows to your Agency 
       and to the GEF/LDCF/SCCF/NPIF Trust Fund).

part ii:  project justification

A. describe any changes in alignment with the project design of the original pif

A.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSA, NIPs, PRSPs, NPFE, Biennial Update Reports, etc. 1. The PIF provides an accurate description of the Project’s alignment to national strategies and plans. 2. More detailed information is provided in the UNDP Project Document in sections B2b, B2c and B2d.

A.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities.

3.	The PIF provides an accurate description of the Project’s alignment to GEF focal areas and strategies.

4.	More detailed information is provided in the UNDP Project Document in section B2a and C1.

A.3 The GEF Agency’s comparative advantage:

5.	The PIF provides an accurate description of the UNDP’s comparative advantage to implement this Project.

6.	A full description of the UNDPprogramme in Viet Nam and related activities is provided in the UNDP Project Document in section E1.The approach to implementation is provided in E2.

A.4. The baseline project and the problem that it seeks to address:

7.	The PIF provides a description of the baseline project and the problem to be addressed. This description remains generally valid. These are described in detail in the UNDP Project Document in section B2b and C2a.

8.	In the period following the submission of the PIF, there have been some developments in the baseline. Notably:

•	With regards to EPI (i.e. Output 1.3), UNDP has significantly stepped up its support to EPI (through project “Support Strengthening Capacity on Natural Resources and Environment Policy Development and Environmental Performance”) and ISPONRE has commenced the project “investigation, assessment and piloting of environmental performance ranking in Viet Nam”. These are described under the concerned Outputs in the Project Document and also in Section E1a.

•	With regards to SEA (Output 2.1), the ADB has provided a great deal of support to developing the SEA system and related capacity in Viet nam. As a result, SEA capacity has evolved in Viet Nam. Hence, this project can build on those developments and focus into the gaps related to the global environment.

9.	Due to these changes in the baseline, some of the focus of the GEF support has been re-aligned (see next section).

10.	Moreover, there have been some minor changes to the US$ amounts of co-financing, as described in the following table.

| Source of Co-financing | Amount in PIF | Actual Amount | Description/Comment |
| --- | --- | --- | --- |
| ISPONRE | $550,000 | $590,000 | This increase illustrates the strong interest and support from ISPONRE, and the Government in general, to the project. |
| UNDP | $725,000 | $725,000 | Unchanged |
| CRES | $100,000 | $139,646 | This increase (40% over the original value) illustrates the strong interest and support from CRES to the project, and from the academic and NGO sector in general. |
| WWF | $200,000 | $150,000 | The decrease in co-finance is not cause by a diminishing interest or support by WWF but mainly due to internal re-allocation of funds. |
| Total | $1,575,000 | $1,604,646 | Total (increase by $29,646) |

A. 5. Incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:   cd

11.	The PIF provides a description of the activities and strategies to be supported by GEF. The scope and the range of outputs and activities described in the PIF are, on the whole, unchangedand remain valid.

12.	As mentioned above, due to advances in the baseline, some activities identified in the PIF, whilst still important, are being covered by other partners and so less GEF support is required. These changes are summarized in the following Table.

| Outcome | GEF Allocation (in PIF) | GEF Allocation (actual) | Description/Comment |
| --- | --- | --- | --- |
| 1. Vietnam has environmental management tools that fully address global environment concerns. | 600,000 | 484,000 | The parallel work being supported by UNDP is covering many activities related to EPI, thereby releasing some GEF funds. GEF allocation to this has therefore been reduced. |
| 2. Vietnam is integrating global enviroment concerns into its national strategic planning and development processes. | 295,000 | 411,000 | The costs required to mainstream global environmental factors into SEA (Output 2.1) and Land-use planning (Output 2.2) were underestimated at the time of PIF preparation. Moreover, current baseline developments (see Project Document) in Viet nam mean that this is an optimal time to mainstream global environmental factors into SEA and Land-use planning – hence this project is allocating sufficient resources to grasp this unique opportunity. |

13.	As can be seen from the Table above, some minor reallocation of GEF support has been made in order to respect activities of other partners (UNDP) and exploit unique opportunities in Viet Nam.

A.6  Risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and measures that address these risks:

14.	An initial analysis of Risks was provided in the PIF in section B.4. This has been developed in the UNDP Project Document (Section C3c). The risks and mitigation measures are summarized in the following Table.

| Risk | Severity | Description And Risk Mitigation Measures |
| --- | --- | --- |
| Inadequate Government and other stakeholder commitment to the process. | Medium | Viet Nam has many socio-economic priorities, of which the highest is alleviating poverty and overcoming inequality. Environment is also a priority issue. However, the local environmental issues such as air pollution, water pollution, waste etc, are given a higher priority than global issues Commitment to the global environment may take second place in the face of these socio-economic challenges. The Government, in the baseline, has the vision and commitment to protect environmental resources. On the 3rd June 2013, The Party Central Committee (PCC) approved the Decision number 24 – NQ /TW at the PCC 7 - XI meeting on actively respond to climate change, strengthening resource management and environmental protection. Hence, the Government, notably MONRE and ISPONRE, is committed to the baseline of the project. The approach taken is to integrate GEF firmly into the baseline, thereby trying to benefit from the Government’s commitment to the baseline. |
| Inadequate coordination mechanisms. | Medium | The various ministries and departments involved in implementing the Rio Conventions have undergone several restructurings in recent years. They have the mandate and commitment to collaboration and coordination, but in many cases they do not have the operational tools and mechanisms to collaborate/coordinate. This could undermine implementation of the project. This Project will bring all concerned parties together to work on the activities under the six outputs and two outcomes. This Project will demonstrate how coordination and collaboration can yield benefits for all concerned. Through this learning by doing approach, the Project will generate operational linkages across the concerned departments and ministries. |
| By attempting too much, the project may over-stretch its resources. | Medium-low | The Project has activities across several sub-sectors and in several technical areas. The overall GEF Project budget is limited. Hence, there is a danger that by trying to do too much, the Project will not be able to properly achieve anything. Firstly, the strategy is for the GEF funds to complement a strong baseline. Hence, the GEF provides a limited amount of additional funding. This should ensure cost-effectiveness and optimal use of GEF funds. Secondly, the Project is designed to be focused into specific, tangible results. The UNDP and MONRE will monitor this situation closely, and take corrective measures if necessary. |
| Inadequate quality and quantity of data and information | Low | The proposed activities require data and information to be of a certain quality. This quality may not be available in Vietnam. They also require a certain quantity of information. The implementing partner (ISPONRE) has been involved in many research programmes in the past, often in collaboration with international partners, and has access to databases and studies undertaken by MONRE. ISPONRE should be able to assure access to data and information. |
| It is difficult to use the new tools. | Low | The Project will develop new tools. However, there may not be sufficient capacity to use these tools. This is particularly a challenge at provincial levels of government. Training on application of new tools will be provided for different stakeholders |

A.7. Coordination with other relevant GEF financed initiatives

15.	The PIF (section B.6) provides a description of the related GEF-supported and other initiatives. More details are provided in the UNDP Project Document in section E1.

B. additional information not addressed at Pif stage:

B.1 Describe how the stakeholders will be engaged in project implementation. 16. A study of stakeholders was undertaken as part of the preparation of this Project. The detailed findings are presented in the UNDP Project Document (see Section C4 for details). 17. The stakeholders consulted during project preparation include representatives from several departments under the Ministry of Natural Resources and the Environment (MONRE), the structures for the three Convention Focal Points,and various other government ministries and specialized departments. Civil society and academia was also consulted, such as CRES and Universities. Representatives of development partners (WWF, GiZ) were also consulted. 18. As a result of those consultations, the project is to be implemented through an adaptive and collaborative management approach. Through this, the project will ensure that key stakeholders are involved early and throughout project execution. This will include their participation in the Project Board, their review of project outputs as well as involvement in monitoring activities. 19. The UNDP Project Document provides additional information on concerned national government agencies, on regional and local government agencies, on key international partners, and on NGOs and research institutes. It provides information on their responsibilities, and their probable role in the project.

B.2 Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF):

20.	Since the adoption of market-oriented reforms almost two decades ago, and the opening of its economy to international trade, Viet Nam has taken great strides to overcoming economic and human poverty. It is now well on its way to achieving middle-income status. For example, the national poverty rate declined from 58% in 1993 to 16% in 2008, and rural poverty declined from 64% to 20% over the same period. Yet, despite these overall achievements in overcoming poverty, poverty remains persistently entrenched in some areas: rural areas have far more poverty than urban areas; and areas with a large ethnic minority population often have high poverty levels.

21.	Moreover, Viet Nam is considered one of the five countries the most vulnerable to the adverse effects of climate change. Viet Nam already suffers from typhoons, floods, droughts, landslides, etc, and climate change threatens to exacerbate these, with the potential for extensive economic damage and loss of life, affecting coastal, mountainous and urban areas.

22.	Finally, environmental challenges risk becoming increasingly acute in Viet Nam, and it is generally accepted that the poor and marginalized sections of society will incur proportionally greater costs than the rest of society. For example land degradation, forest degradation, ecosystem decline and climate change (as well as air and water pollution) will affect the poor and the marginalized more than others. This is partly because the poor are more dependent on natural resources, and partly because they have less capacity to adapt.

23.	Vietnam’s efforts to overcome these socio-economic challenges are focused on the implementation of national policies and plans, notably the Comprehensive Growth and Poverty Reduction Strategy (CGPRS) and the five-yearly Five Year Socio-Economic Development Plans (SEDP). Notably, both the previous SEDP and the present SEDP focus on poverty reduction.

24.	This project has been designed, both institutionally and substantively, to contribute to the CGPRS and SEDP (as described in detail in the Project Document in section B). Institutionally, the project is firmly anchored into government decision-making mechanisms, through MONRE and also aligned to the Ministry of Planning and Investment. Substantively, the Project’s activities and outputs have been designed to have secondary effects that directly support the SEDP – notably through SEA and land-use planning.

25.	Moreover, this project will lead to a direct increase in capacity to manage environmental resources and therefore lead to direct improvements in the lives and livelihoods of the poor, as follows:

•	Improved indicator systems will lead to improved environmental monitoring and management, especially at provincial level;

•	Improve performance monitoring will lead to increased incentives for environmental management as well as to lesson-learning that leads to improved performance;

•	Improve environmental valuation techniques will mean the true value of natural resources, as often appreciated by the poor, can be better accounted for in decision-making; and

•	Enhanced processes for SEA and land-use planning will lead to better allocation of resources, better decision-making, and improved protection of the assets of the poor communities.

26.	See Project Document sections B and C for full details.

Gender

26a According to a recent World Bank led assessment (Vietnam - Country gender assessment, 2011), Viet Nam has recently made remarkable progress on gender equality, but important gender differences still remain. For example, Viet Nam has made considerable progress in addressing gender disparities in education, employment and health and gender gap in earnings is lower in Viet Nam than in many other East Asian countries. However, a number of challenges still remain, with challenges being most notable with marginalized, remote and poorer communities. There is also the need to sustain the gains made, e.g. regarding women's participation in leadership political positions and in the wider society.

26b. This project mainstreams gender issues into all pertinent activities. Gender considerations will become an integral part of all capacity built, all tools prepared, all training undertaken and all materials developed. This has been clarified in the Project document in particular with regards to Outputs 1.1, 1.2, 1.3, 2.1 and 2.2 and in Section C4.

26c. Although this Project does not act directly at the grassroots level, this approach recognises that in rural and remote areas, women are particularly vulnerable to resource degradation, in particular women with young children and female headed households. Hence, Outputs 1.1 and 1.3 will contribute to enhanced environmental management in rural areas, and the livelihoods of marginal population groups will be improved by the improved environmental management. Likewise, Outputs 2.1 and 2.2 will enhance national capacities to conduct SEA and land use planning which will reduce risks for marginal groups.

B.3. Explain how cost-effectiveness is reflected in the project design: 27. In line with GEF strategy, the GEF finances only the ‘incremental costs’ of achieving the global environmental benefits. This means that the UNDP/GEF project builds on top of a significant baseline. The UNDP/GEF project will influence investments by both government and development partners, and will have an impact beyond the limited GEF contribution. 28. For both Outcomes, the strategic use of GEF funds is to mainstream into/onto ongoing processes and to modify them in order to yield global environmental benefits, this is far more cost-effective than if GEF was to support the entire initiative. 29. For example, in Outcome 1, there is a large baseline supported by UNDP, ISPONRE and other partners, addressing the issues of indicator systems, resource valuation and EPI. Almost all the activities and outputs related to EPI are covered by UNDP. GEF supports additional activities and inputs to ensure the Rio Conventions are integrated into the baseline 30. For example, in Outcome 2 includes work on SEA. The vast majority of work on SEA is covered by government and ADB. The GEF funds support additional activities and inputs to ensure the Rio Conventions are integrated into the baseline process. 31. GEF contribution to management costs is limited to $80,000, or 8.2% of all GEF funds. This is 3.1% of the entire Project costs.

C.  describe the budgeted m &e plan:

32.	The UNDP Project Document provides a detailed description of the monitoring, reporting and evaluation to be undertaken during the Project (Sections 4 E and 4 F).

33.	Full details of indicators, baseline values and targets are presented in Annex 1 (Results Framework).

34.	Monitoring and evaluation activities will follow UNDP and GEF monitoring and evaluation policies and guidelines. Monitoring and evaluation of progress in achieving project results and objectives will be done based on the targets and indicators established in the project Results Framework (RF) (Annex 1). The costs of project Monitoring and Evaluation Plan have been estimated at USD54-59,000(see Table below). Integrated into all Outcomes, the Project monitoring and evaluation approach will also facilitate learning and mainstreaming of project outcomes, and lessons learning for international good practice, as well as into national and local policies, plans and practices.

35.	A summary of the envisaged M&E activities is provided in the following Table.

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | - ISPONRE - Project Manager - UNDP CO, UNDP GEF | Indicative cost: 10,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. Estimated $5-10,000. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Manager - Project team | To be determined as part of the Annual Work Plan's preparation. Estimated $5-10,000. | Annually prior to ARR/PIR and to the definition of annual work plans |
| ARR/PIR | - ISPONRE - Project manager and team - UNDP CO - UNDP RTA - UNDP EEG | None | Annually |
| Periodic status/ progress reports | - Project manager and team | None | Quarterly |
| Mid-term Evaluation | - Project manager and team - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Not Required for MSP project | At the mid-point of project implementation. |
| Final Evaluation | - Project manager and team, - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Indicative cost : 30,000 | At least three months before the end of project implementation |
| Project Terminal Report | - Project manager and team - UNDP CO - local consultant | 0 | At least three months before the end of the project |
| Audit | - UNDP CO - Project manager and team | Indicative cost per year: 3,000 | Yearly |
| Visits to field sites | - UNDP CO - UNDP RCU (as appropriate) - Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses |  | Estimated $59,000 - 69,000. |  |

PART iII: Approval/endorsement by gef operational focal point(s) and gef agency(ies)

- Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): ): (Please attach the Operational Focal Point endorsement letter(s) with this form. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Dr. Nguyen Van Tai | GEF Operational Focal Point, Director General, ISPONRE/MONRE | MINISTRY OF NATURAL RESOURCES AND ENVIRONMENT | 06/15/2012 |

B.  GEF agency(ies) certification

This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for CEO endorsement/approval of project.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu, Executive Coordinator and Director a.i., UNDP-GEF |  | March 28, 2014 | Tom Twining-Ward, UNDP Green-LECRDS | +421 2 59337 386 | tom.twining-ward@undp.org |

GEF_CEOENDR_52

ANNEX A:  PROJECT RESULTS FRAMEWORK (either copy and paste here the framework from the Agency document, or provide reference to the page in the project document where the framework could be found).

See Project Document, Annex 6

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

The GEF Secretariat Review of the PIF (dated April 25th, 2013) made no specific requirements to be addressed through this Request for CEO Endorsement.

Annex C:  status of implementation of project preparation activities and the use of funds

A.  provide detailed funding amount of the ppg activities financing status in the table below:

| PPG Grant Approved at PIF: 25,000 |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF/LDCF/SCCF/NPIF Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent Todate | Amount Committed |
| International Consultant | 17,500 | 0 | 17,500 |
| Local Consultant | 7,350 | 0 | 6,900 |
| Miscellaneous | 150 | 0 | 600 |
| Total | 25,000 | 0 | 25,000 |

annex D:  calendar  of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/NPIF  Trust Fund or to your Agency (and/or revolving fund that will be set up)

Project ID number will be assigned by GEFSEC.

Refer to the Focal Area Results Framework and LDCF/SCCF Framework when completing Table A.

PMC should be charged proportionately to focal areas based on focal area project grant amount in Table D below.

For questions A.1 –A.7 in Part II, if there are no changes since PIF and if not specifically requested in the review sheet at PIF  stage, then no need to respond, please enter “NA” after the respective question.

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.