Project Identification Form (PIF)

Project Type: FULL SIZED PROJECT

Type of Trust Fund: THE GEF TRUST FUND

PART I: Project Identification

| Project Title: | Strengthening Management Effectiveness and Generating Multiple Environmental Benefits within and around Protected Areas in Zambia |  |  |
| --- | --- | --- | --- |
| Country(ies): | Zambia | GEF Project ID: | 4629 |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 4625 |
| Other Executing Partner(s): | Ministry of Tourism, Environment and Natural Resources; Zambia Wildlife Authority; Forestry Department; Ministry of Energy and Water Development | Submission Date: | 22 September 2011 |
| GEF Focal Area (s): | MULTIFOCAL AREA | Project Duration: | 60 months |
| Name of parent program (if applicable): For SFM/REDD+ |  | Agency Fee: | 1,314,886 |

- Focal Area strategy Framework:

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | ### Indicative Financing from GEF | ### Indicative Co Financing ### ($) |
| --- | --- | --- | --- | --- |
| BD 1: Improve sustainability of protected area systems | 1.1 Improved management effectiveness of existing and new protected areas 1.2 Increased revenue for protected areas to meet total expenditures required for management | - New protected areas and coverage of unprotected ecosystems - Sustainable financing plans | 2,431,591 1,200,000 | 12,541,824 |
| LD 3: Reduce pressures on natural resources from competing land uses in the wider landscape | 3.1 Enhanced cross-sector enabling environment for integrated landscape management 3.2 Integrated landscape management practices adopted by local communities | - Integrated land management plans developed and implemented - Information on INRM technologies and good practice guidelines disseminated | 1,100,000 1,452,046 | 9,406,368 |
| SFM / REDD+ 1: Reduce pressures on forest resources and generate sustainable flows of forest ecosystem services | 1.1: Enhanced enabling environment within the forest sector and across sectors 1.2: Good management practices applied in existing forests 1.3 Good management practices adopted by relevant economic actors | - Forest area under sustainable management, separated by forest type - Types and quantity of services generated through SFM | 400,000 649,345 2,050,030 | 9,406,368 |
| CCM 3: Promote investment in renewable energy technologies CCM 5: Promote conservation and enhancement of carbon stocks through sustainable management of land use, land-use change, and forestry | 3.2 Investment in renewable energy technologies increased 5.1 Good management practices in LULUCF adopted both within the forest land and in the wider landscape | - Renewable energy capacity installed - Forests and non- forest lands under good management practices - Carbon stock monitoring systems established | 658,409 2,550,000 | 11,290,000 |
| Project management cost |  |  | 657,443 | 2,145,441 |
| Total project costs |  |  | 13,148,864 | 44,790,000 |

- Project Framework

| ### Project Objective: To ensure that the biodiversity and carbon sinks of Zambia – particularly those critical forest landscapes in selected protected areas (including core National Parks and buffer Game Management Areas) – are better protected from threats through improved management effectiveness at the institutional level; sustainable forestry management practices and integrated land use planning at the local level; and application of appropriate low-carbon, biomass-energy technologies. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ### Project Component | ### TA | ### Expected Outcomes | ### Expected Outputs | ### Indicative Financing from GEF | ### Indicative Co Financing ### ($) |
| Increasing the sustainability of Zambia PA system and the effectiveness of its core areas | TA (A) TA (B) TA (C i. ii and iii) INV (C iv) | Improved system capacity increases over the long term - the management effectiveness of all 19 National Parks (core PA) covering 64,000 km2 increases by at least 15% (as measured by a) UNDP Capacity Scorecard and b) a sample of METT). Reduction in funding gap of core PAs - all 19 Parks move up one category (based on REMNPAS financial viability assessment) and one new PPP formed Baseline status; Target status. Currently viable; Currently viable. Viable in 5 yrs; Currently viable. Viable in 10 yrs; Viable in 5 yrs. Viable in 15 yrs; Viable in 10 yrs. West Lunga; Add one Public-Private-Community Partnership. Management effectiveness increased in target core PAs: West Lunga and Kafue National Parks covering 24,084 km2 of Miombo Woodland and Dry Evergreen Forest ecosystems (measured by increase of 15% in the Management Effectiveness Tracking Tool for the two Parks). Expansion of core PAs through increased protection to an estimated 5,579 km2 of forest ecosystems by upgrading PA status in terms of new categories reduces representivity gaps as follows: Forest Ecosystem type; Total area (km2); % under PA category that ensures BD Conservation*. B’line; Target. Miombo Woodlands; 2,899; 6.1%; 7%. Dry Evergreen Forest; 2,680; 4.5%; 11.7%. Total; 5,579. * This could be a new Partnership Park in Mufunta (linked to Kasonso Busanga), a new Game Reserve in Namwala, and the proposed West Lunga Game Reserve across Lukwawa and Chibwika-Ntambu - to be confirmed in PPG phase. Increased site capacities reduce pressure in target core PAs from: - Wildfire (reduction in incidence shown in wildfire records) - Wildlife poaching (increase in sightings of key wildlife - elephant, buffalo, impala, puku, warthog, zebra, Kafue lechwe and Tsessebe – species list and baseline to be confirmed in PPG) - Illegal harvesting of wood products (halting of deforestation rates confirmed in comparison with baseline values acquired in PPG phase through sampling) Improved financial sustainability of target core PAs measured by: - Increase in financial scorecard score Scorecard section; Baseline 2012; Target 2016. 1 Legal, regulatory & institutional frameworks; WL 15%; K; WL 35%; K. 2 Business planning & tools for cost-effective management; WL 58.9%; K; WL 65%; K. 3 Tools for revenue generation; WL 33.3%; K; WL 40%; K. (Kafue baseline and targets to be completed in PPG phase) Halting of deforestation by improving PA status to effective protection over 5,579 km2 has the following GEB: - 311,688 t C emissions are avoided over 5 years by changing deforestation rate from 0.3% pa to 0% over 2,680 km2 of Dry Evergreen Forest - 298,218 t C t C emissions are avoided over 5 years by changing deforestation rate from 0.3% pa to 0% over 2,899 km2 of Miombo Woodland | A. PA system framework strengthened. This includes: i) Professional development program to build ZAWA Head Office operational and planning capacity; ii) Leadership training program for all Park Managers and Area Wardens (iii) Business intelligence system established at Head Office; (iv) Sustainable financing plan for PA system incl. identifying specific revenue generation mechanisms B. Site level operations strengthened for Target Core PAs. This includes for target NPs: (i) Strengthened system for enforcement for pilot sites; (ii) Staff training for planning; accounting and record-keeping (iii) Business plans developed and implemented (iv) User fees collection system developed C. Expansion of PA Core through upgrading and gazetting. (i) Zoning and boundary demarcation based on land use planning (Component 2) (ii) Reclassification and gazetting of 5,579 km2 of forested portions of GMAs in terms of new categories (iii) Incorporation into Core PA management system of newly gazetted areas (iv) Establishment of PA infrastructure – ranger posts in Mufunta and Namwala to support existing ZAWA capacity, and completion of infrastructure in West Lunga | 5,181,278 (BD 3,631,591 + FSM 1,549,687) | 15,541,824 |
| 2. Sustainable land and forest management in targeted Game Management Areas (Target buffer GMAs are Mufunta and Namwala in Greater Kafue NP, and Lukwawa and Chibwika-Ntambu in West Lunga Management Area – selected in relation to degree of a) valuable BD and b) conflicting land use – to be confirmed in PPG phase) | TA (A) TA (B I, iii and iv) INV B (ii and v) INV (C i) TA (C ii) | Improved land use governance and diversification of income streams over target GMA buffer area of 12,794 km2 reduces: - Uncontrolled spread of agriculture – target is to intensify production and maintain total area under grazing and crops – no net increase (measured by remote sensing in partnership with ILUA, UNZA) - Deforestation and degradation rates – target is to halt outright loss of forest cover and severe degradation in the target area, with small losses offset by a) allowing natural recovery of slightly degraded areas and b) reforestation projects (Existing land cover data collated and analysed in the PPG phase to provide a baseline of total project target area (core PAs + GMA buffer) of 36,878 km2 – to determine extent of forested, slightly degraded, severely degraded and transformed areas. Data collected and analysed again at mid-term and end of project.) At least 30,000 ha more sustainably managed, with 3,200 ha established as community woodlots, supplying the improved kilns with 15,158 tons of renewable biomass per year (with harvesting ready after 5 years if established as a green field), with other areas earmarked through the ILUA process for short-rotation coppicing during the project period while the woodlots mature. Adoption of sustainable land management and conservation farming practices over 7,215 km2 across 4 GMAs leading to improved flow of ecosystems services as demonstrated by:  an improvement in soil aggregate stability as measured in project sites over time  improvement in groundwater retention as measured in project sites over time (baseline and targets to be determined through PPG) | A. Land use governance and planning in GMAs strengthened: (i) Multi-stakeholder partnerships established for managing new Partnership Parks / Game Reserves; (ii) Integrated Land Use Assessment plans developed and implemented, linked to the national REDD readiness programme; (iii) Business plans / investment frameworks developed for GMAs B. Land and forest resources managed more sustainably: (i) Farmer support programme providing extension and capacity building on conservation agriculture - fostering natural ecological processes to increase yields, reducing pressure on forests ii) Establishment of infrastructure for new practices in conservation farming; (ii) Research on sustainable harvesting rates for non-timber forest products and for short-rotation coppicing; (iv) Training of Forestry Department officials, Community Resource Boards and village structures on sustainable harvesting, and restoration methods; building of enforcement capacity; (v) Restoration of forest portions by forestry role-players through assisted natural regeneration with enrichment planting, in areas with key biodiversity and important as wildlife dispersal corridors - for inclusion in new PAs C. Establishment of community woodlots to supply improved kilns with renewable biomass (i) Community woodlots of fast-growing plantation species established on unproductive agricultural land to supply poles and fuelwood, and service 240 charcoal retort kilns; ii) Training of community cooperatives to operate woodlots | 6,151,734 (LD 2,552,046 + SFM 1,549,688 + CCM 2,050,000) | 22,812,735 |
| 3. Establishment of financial incentives and dissemination of appropriate technologies for sustainable charcoal production and SFM in selected charcoal-producing GMAs (Mufunta and Namwala in Greater Kafue NP) | TA (A i and iii) INV (A ii) TA (B) | Improved data collection and monitoring of biomass energy and charcoal production and use in GMAs Low-carbon charcoal production technologies have successfully replaced inefficient systems in targeted GMAs leading to: - Total avoided emission reductions of 319,680 tons of CO2 equivalent over 15 years from switching to renewable biomass: 89t CO2 per year reduced from each retort kiln deployed from eliminating use of non-renewable biomass - Total direct reduction in GHG emissions of 302,400 t CO2 from methane capture over 15 years: 84 t CO2 per year reduced from adoption of each retort kiln based on reduction of CH4 emissions from new technologies - Verified increased earnings per unit of charcoal produced due to sustainable practices and technology transfer Sustainable charcoal recognized as a viable livelihoods activity in pilot GMAs and financial incentives proposed for scale-up post-project Basic carbon project design completed for voluntary carbon market project linked to improved kilns and sustainable biomass use | A. Deployment of low-carbon technologies and development of sustainable charcoal schemes in two target GMAs (i) Community cooperatives formed and trained to operate kilns; (ii) Charcoal retort kiln pilots introduced - 240 (120 in two GMAs) to replace earth kilns; (iii) Monitoring, tracking and licensing system established for all improved kilns B. Scale-up of improved technology promoted through (i) Integrated national data system on charcoal use and production in GMAs developed; (ii) National standardized baseline developed for sustainable charcoal; (iii) Financial incentives implemented to encourage purchase of kilns by producer associations nationally | CCM: 1,158,409 | 4,290,000 |
| Project management costs |  |  |  | 657,443 | 2,145,441 |
| TOTAL |  |  |  | 13,148,864 | 44,790,000 |

- Indicative Co-financing for the project by source and by name if available ($)

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| National government | Ministry of Tourism, Environment and Natural Resources (Zambia Wildlife Authority and Forestry Department) Ministry of Energy and Water Development | Cash | 5,000,000 |
| GEF Implementing Agency | UNDP | Cash | 4,000,000 |
| GEF Implementing Agencies | UN REDD Programme Zambia | Cash | 4,490,000 |
| Bilateral Aid Agency | Millennium Challenge Corporation (USA) | Cash | 28,000,000 |
| Bilateral Aid Agency | USAID – US Forestry Service | Cash | 3,300,000 |
| (select) |  | (select) |  |
| (select) |  | (select) |  |
| (select) |  | (select) |  |
| (select) |  | (select) |  |
| (select) |  | (select) |  |
| (select) |  | (select) |  |
| Total Co-financing |  |  | 44,790,000 |

D. GEF Resources Requested by Agency (ies), Focal Area(s) and Country(ies)

| GEF Agency | Type of Trust Fund | Focal area | Country | Project amount (a) | Agency Fee (b) | Total c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
| UNDP | GEF | BD | Zambia | 3,822,727 | 382,273 | 4,205,000 |
| UNDP | GEF | CC | Zambia | 3,377,273 | 337,727 | 3,715,000 |
| UNDP | GEF | LD | Zambia | 2,686,364 | 268,636 | 2,955,000 |
| UNDP | GEF | SFM | Zambia | 3,262,500 | 326,250 | 3,588,750 |
| Total GEF Resources |  |  |  | 13,148,864 | 1,314,886 | 14,463,750 |

part ii:  project JustiFication

- Description of the consistency of the project with:

A.1.1.  the GEF focal area strategies:

This project has been designed based on extensive consultations with local stakeholders with the express intention of responding to GEF’s overall strategic vision under GEF V of helping countries meet their sustainable development needs and achieve multiple environmental benefits through an integrated approach. The proposed project satisfies the requirements for GEF financing under multiple focal area strategies and is designed in an integrated manner to enable Zambia’s PA system to reach its potential for delivering high value multiple benefits on a large scale – protecting globally significant biodiversity, forest carbon stocks and critical ecosystem services such as watershed protection. Zambia’s vast PA estate covers 40% of the country’s surface area and has the greatest potential to provide these multiple environmental benefits. The PA estate is made up of three main categories – National Parks which are set aside primarily for biodiversity conservation (8.5% of land), Game Management Areas where sustainable utilization of natural resources and human settlement are allowed (22%), and Forest Reserves where sustainable utilization of resources is allowed (8.9%). This project works across the landscape in core and buffer – improving the management effectiveness and financial sustainability of core areas of the PA system; reducing conflicting land uses in the buffer zone GMAs, and increasing energy efficiencies to reduce deforestation and carbon emissions in GMAs.

Biodiversity Focal Area 1 is addressed by the project’s focus on both the management effectiveness and the financial sustainability of Zambia’s Protected Area (PA) estate. Zambia’s National Parks, managed by the Zambia Wildlife Authority, cover an area of 64,000km2 or 8.5% of Zambia’s landmass. National Parks are buffered by Game Management Areas, which allow settlement, agriculture and sustainable utilization of wildlife by communities and cover a further 166,000km2 or 22% of the country. This project builds on the previous GEF investment in reclassification of new types of PAs, working at a systemic level to strengthen the management effectiveness of Zambian PAs in conserving biodiversity and addressing drivers of degradation such as poaching, wildfire and illegal timber. It also builds on the previous work done to quantify the funding gap, now seeking ways to address the gap through establishing innovative Public-Private-Community partnerships, improving user fee systems and earning revenue through the REDD system. At a site level the project works in two National Parks, which protect poorly represented vegetation classes – Dry Evergreen Forest in West Lunga and Miombo Woodland in Kafue National Park – covering a total area of 24,084 km2. The project employs a landscape approach – with Component 1 of the project, focused on the core National Parks, fully integrated with Component 2 which focuses on the buffer-zone Game Management Areas, improving land use planning and land and forest management to reduce pressures on biodiversity in the core. Strengthening the PA estate is also important for climate change mitigation (Component 3) – Zambia’s forests are the 6th largest carbon reservoir globally. Land Degradation Focal Area 3 and Sustainable Forest Management Focal Area 1 are addressed through Component 2 working to reduce pressures on forest resources and generate sustainable flows of forest ecosystem services, as well as reducing pressures on natural resources from competing land uses in the four Game Management Areas (GMAs) with a combined area of 12,794km2 – proposed target areas are Namwala and Mufunta GMAs adjacent to Kafue National Park and Lukwakwa and Chibwika Ntambu GMAs adjacent to West Lunga. National trends show an alarming degradation of wildlife habitat and carbon stocks – as well as a plethora of unsustainable land use practices – throughout the country's GMAs, with 12 of the 34 GMAs now classified as depleted in comparison to none in 1997 and land use conflicts widespread. Through promoting integrated land use planning, the project aims to halt the uncontrolled spread of unsustainable cropping and grazing, to protect high-value forest land in terms of new PA categories, and to promote sustainable land and forest management practices. The project has also been designed in line with GEF Investment Guidelines for Sustainable Forest Management and the REDD+ Programme, and supports the development of policies and regulations to roll out and implement SFM interventions that complement existing UN-REDD activities. SFM challenge account funding will help to establish a sound policy environment to recognize the value of forest ecosystem functions and reduce GHG emissions from deforestation and forest degradation. Climate change Mitigation Focal Area 1 is addressed by the demonstration of commercially available sustainable charcoal technology in two of the four targeted GMAs where charcoal burning is a widespread practice. Current trends in charcoal production and the possibilities presented by promoting sustainable charcoal production align well with GEF strategies since the need for woodfuel – both for rural and urban markets – is the quintessential form of competing land use. Consumption of fuel wood and charcoal was estimated at over 1.2 million tons in 2010 and is predicted to grow with rising urban energy demand. Component 3 of the project contributes to reduced GHG emissions by replacing inefficient traditional earth kilns with 240 charcoal retort kilns, which use less wood per unit of charcoal produced and emit less CO2 (60-70% of reduction) and less CH4 (30-40% of reduction), and by providing the improved kilns with an alternative, sustainable supply of biomass through the establishment of community woodlots (see Component 2). In response to the growing GEF interest in linking activities with carbon markets, the project will attempt to develop schemes to raise finance on voluntary carbon markets for the proposed low-carbon technologies to be disseminated as well as a national standardized baseline approach for sustainable charcoal, providing a potential revenue stream to encourage future uptake of the technologies and leading to significant ease of data collection burden on other project developers.

A.2.   national strategies and plans or reports and assessments under relevant 
conventions, if  applicable, i.e. NAPAS, NAPs, NBSAPs, national communications,  TNAs, NIPs, PRSPs, NPFE, etc.:

The Zambia Government has completed a comprehensive prioritization exercise to develop a GEF V pipeline. Several multi-agency steering committee meetings were held to review various project proposals. This project was prioritised following a lengthy consultative process including a Country GEF Portfolio Review workshop held in April 2010 and GEF National Steering Committee meetings held in late 2010. UNDP undertook extensive consultations and field visits in October 2010 and February 2011 as part of the development of the PIF. Zambia ratified the Convention on Biological Diversity in 1993 and United Nations Convention to Combat Desertification in 1996. Following the IPCC reports confirming the anthropogenic origin of climate change, the Government ratified the UNFCCC and its Kyoto Protocol (KP) in 1997 and commenced activities to respond to the challenge of climate change. The project is consistent with the following national strategies and structures:

a) The Sixth National Development Plan: Recently launched, this Plan has an Environment and Natural Resources program, which includes a focus on strengthening management of protected areas (national parks, forests resources, wetlands), updating the NBSAP, and Access and Benefit Sharing. The integration of climate change into national development has been prioritized across all sectors in order to avoid obstacles to progress towards the achievement of the targets set in the Plan, the MDGs and Vision 2030.

b) National Biodiversity Strategy and Action Plan (NBSAP): In response to threats to biodiversity, Government in 1999 developed the NBSAP - a policy framework that promotes the conservation, management and sustainable use of Zambia’s biological resources and the equitable sharing of benefits from these resources by all sectors of the population.

c) National Adaptation Programme of Action (NAPA): The NAPA (2007) evaluates the likely impacts of climate change on relevant sectors in Zambia and uses a multi-criteria analysis to rank the most urgent needs identified in order to generate a prioritized list of ten adaptation interventions, which include a promotion of the natural regeneration of indigenous forests, use of renewable energy sources (biomass) and managemnent of critical habitats.

d)  The National Climate Change Strategy: The National Climate Change Strategy is currently being finalized and the policy is expected to be developed by end of 2011, including costed interventions for various CC interventions. UNDP is supporting the formulation of the strategy. The establishment of a temporary institution, a Climate Change Facilitation Unit, has been established within MTENR for spearheading climate change initiatives, with support from UNDP and the Government of Norway.

e) The National Energy Policy (2008): The updated 2008 national energy policy is explicit in its focus on renewable energy sources and biomass energy in particular. The situation analysis states that woodfuel can no longer be considered a renewable resource, as consumption rates are exceeding yield rates. Relevant are - management programmes for indigenous forest resources with stakeholders; training of technical staff and extension workers from wildlife, agriculture and forestry sectors; establishment of forest plantations/woodlots in current or future wood deficit areas; tree planting programmes; monitoring of price trends, volumes of production and consumption; effective regulation of the woodfuel sector; and training of charcoal producers in better organisation and management and encouraging the adoption of other production techniques which are more efficient and cost-effective.

f) National Forestry Policy – NFP (2009): Under Objective (B) - Natural Resources Management, the NFP defines the following priorities relevant to this project: to set aside areas and provide guidelines and supervision for forestry areas’ management; to encourage community participation; to restore environmental quality in degraded areas; to establish forest plantations in wood deficit areas; and to facilitate the establishment of natural resource-based industries and regulate their operations.

g) Pilot Programme on Climate Resilience (PPCR): Zambia  is a pilot country for PPCR with the potential to support improvements in policies and regulations, climate resilient infrastructure, sustainable agriculture  production and ecosystems, and strengthening of early warning and information management

h) The Environment and Natural Resources Management and Mainstreaming Programme (ENRMM): ENRMM is an initiative of the Government of Zambia that aims to bring improved coordination and implementation capacity to the Environment and Natural Resources (ENR) management sector.  The programme is based on the principles, priorities and objectives of Zambia’s Fifth National Development Plan (FNDP). The program mentions the need reduce dependence on charcoal and firewood and ensure sustainable provision of affordable, reliable modern energy services to rural and urban households as a means of reducing poverty and raising standards of living.

- Project Overview:

B.1. Describe the baseline project and the problem that it seeks to address:

Background

1. Zambia is a repository of globally significant biodiversity and has very large tracts of wild areas with low human population densities that, with sound management, could provide important refugia for flora and fauna that are rapidly being extirpated elsewhere in the region. Zambia lies at the heart of the Miombo Ecoregion, which is listed as a WWF Global 200 Ecoregion because of its high species richness. Also referred to as the Zambezian Regional Centre of Endemism, this area covers some 3,770 million km2 extending from the Katanga (DRC) to the Vaal River (South Africa). The ecoregion supports important populations of fauna, particularly large mammals, and is also floristically diverse, harboring some 8,500 plant species, of which approximately 54% are endemic (WWF-SARPO, 2002). National Parks (NPs), Forest Reserves and Game Management Areas (GMAs) cover an exceptionally large area (+40%) of the country. Zambia has approximately 50 million hectares of forest remaining, covering 66% of the proportion of total land area. However Zambia is among the 6 biggest global emitters of greenhouse gases from deforestation (Boucher, 2008) and according to the OSIRIS global Reduce Emissions from Deforestation and Forest Degradation (REDD+) and Carbon Stock Enhancement economic model can contribute 4.3 % of the global REDD+ abatement potential (Bush et al. 2009).

2. The three main protected area categories in Zambia are i) National Parks – a non- consumptive model excluding human settlement except for management purposes, ii) Game Management Areas – a consumptive use model allowing local community settlement, and 3) Forest Reserves – a consumptive use model excluding human settlement. At present in Zambia, only National Parks (NPs), when properly managed, provide good assurance of biodiversity conservation. In the Game Management Area category, customary land under control of the traditional authorities, the lack of any legal restrictions on conversion to smallholder agriculture, commercial farming or other land uses is a major barrier to effective biodiversity conservation over time. The Forests Reserves have proven to be almost ineffective in Zambia in terms of ensuring biodiversity conservation (MTENR, 2005) due to outdated policy/legal framework and limited capacity for effective management. A large percentage of forested land falls in GMAs, which were created as buffer areas to NPs, on the basis that NPs protect nucleus breeding populations of wildlife, and that spillover populations can be utilized in GMAs by local communities for their own use and for trophy hunting to generate income. Wildlife resources in the GMAs are co-managed by the local communities together with the Zambia Wildlife Authority. Revenue is shared with the local communities from proceeds from wildlife hunting, thereby creating an incentive for local communities to conserve the wildlife in their areas. There is however little enforcement of forest laws in these areas and villagers and migrants clear forests for cropland within gazetted forests and Game Management Areas largely with impunity. There is de facto open and local and district administrative bodies generally lack the capacity to regulate land management in a comprehensive manner. It is reported that in gazetted forest areas, only half of the forest remains intact. A map of Zambia’s PA estate system (national parks and GMAs) is provided in Figure 1 in Annexure 1.

3.  Forests have been identified as a valuable environmental and economic resource for supporting natural systems and improving sustainable livelihoods (GRZ, 2004). Zambia‘s forests are not only important for their specialized high timber species and fuel wood, they are also important repositories of biodiversity and provide a wide range of environmental services to wildlife and wildlife-based tourism, agriculture, biomass energy, hydro-electricity generation and municipal water supply by regulating watercourses and flood regimes.  Miombo woodland is the most widespread woodland type in Zambia, but it is under-represented in the national PA system, according to the vegetation gap analysis conducted for the REMNPAS project. Miombo is important for various uses including charcoal, timber, fruits, medicines, mushrooms, etc. As noted in the diagram below, Miombo woodland is the most extensive Zambian ecoregion covering about 65% of the Country. Miombo is further divided into Central Zambezian and Southern Miombo Woodlands. The central miombo woodland which is predominantly of Isoberlinia angolensis, Brachystegia spp. and Julbernadia paniculata is the dominant vegetation types in Northern, Luapula, North-Western and the northern part of Central Province and part of Kafue National park. However, in the southern miombo woodland, Isoberlinia angolensis is absent.

4. The largest remaining block of forests in Zambia occurs in the North Western Province, where the West Lunga NP is located and which neighbors the Northern Kafue NP GMAs on the southern border of the Province. The Dry Evergreen Forests are the least represented vegetation type in Zambia under National Park status. The Zambezian Cryptosepalum Dry Forests – an internationally recognized WWF Global 200 Ecoregion – is only found in North-western Zambia and Eastern Angola and constitutes the largest area of tropical dry evergreen forest in Africa outside the equatorial zone. Dry evergreen forest occurs in three main subtypes, one for each distinctive site: Parinari forest on the plateau, Marquesia forest in the lake basin and Cryptosepalum forest in the Kalahari basin. In West Lunga, the Cryptosepalum Forest Canopy dominants are restricted to Cryptosepalum exfoliatum spp. pseudotaxus and Guibourtia coleosperma in the lower rainfall areas of Zambezi, Kapompo and Kaoma districts but associated with Marquesia acuminate, M. macroura, Parinari excelsa and Syzygium guineese spp. afromontanum in the higher rainfall of Mwinilunga district.

Threats to biodiversity:  Wildlife poaching in the core National Parks, as well as over-hunting in the buffer zone formed by the GMAs, poses a serious threat to biodiversity. With West Lunga having few resources invested in its management until recently, many wildlife species have been hunted to such low levels that potential for tourism is jeopardized. Kafue National Park has the greatest range of antelope species in Zambia and in terms of large mammals it is only second to Chobe National Park in Botswana. The presence of sable, kudu, warthog and impala has been recently recorded in Mufunta GMA (Simasiku et al., 2008). In the GMAs nationally a total of 25 species are being harvested in terms of the safari hunting quota (especially lion, leopard, sable, roan, eland, zebra and elephant) and a further 16 species for meat. An analysis in 2006 showed that buffalo was the only larger mammal whose numbers were sufficient to be targeted for both trophy hunting and meat, with declining trends for most species (Simasiku, op cit.). An increase in wildfires in the core PAs and their buffer zone in recent years poses a threat to biodiversity, while also contributing to the release of carbon into the atmosphere.  Particularly vulnerable are fragmented and degraded Dry Evergreen Forests in GMAs which no longer have their natural ability to withstand fire. Indiscriminate late bush fires have been observed to reduce wood annual increment by 50% in Miombo Woodland, as trees less than 3m high are generally susceptible to destruction and late fires destroy 84% of the herbage biomass. Uncontrolled extraction of fuelwood, timber for construction and wood for charcoal in the GMAs are posing a serious threat to biodiversity, as ecosystem functioning is disrupted, species diversity is reduced and habitats are degraded, fragmented and lost. Dry Evergreen Forests and Miombo Woodlands are two of five vegetation classes underrepresented in the National Park system (www.remnpas.org.zm) and need to be protected where they occur in GMAs around West Lunga and Kafue.

Threats to land and forest resources: The major threats to ecosystem integrity and functioning in the GMAs come from the uncontrolled spread of agriculture, the uncontrolled extraction of resources, and unsustainable agricultural practices. If not arrested, habitat destruction and woodland depletion in the GMAs will eventually reach the national parks they are supposed to buffer and threaten the economic and ecological viability of entire forest ecosystems. Forest degradation and deforestation are occurring at a rapid pace in the GMAs, as communities extract fuelwood, timber and wood for charcoal. According to the FAO, the national deforestation rate from 2005 to 2010 was on average 166,600 ha leading to an annual deforestation rate of 0.33 %. Land degradation is caused by unsustainable agricultural practices including shifting cultivation, “slash and burn”, monoculture, use of heavy machinery, overuse of inorganic fertilisers, over-grazing, cultivation in wetlands and on unstable slopes. Land degradation causes soil erosion, soil infertility, siltation, sedimentation and flooding and a loss of usable water for agriculture and grazing. This has been reflected in a loss of agricultural productivity nationally with the average maize yield per hectare decreasing from 1.48 tons in 1989/90 to 1.27 in 1997/98.

Threats to global climate: According to the FAO, between 1990 and 2010, Zambia lost an average of 166,600 ha or 0.32% of its forest cover per year, 6.3% of its cover over the whole period. Deforestation and degradation are significant contributors to the country’s GHG emissions. The major drivers of deforestation in the Kafue and West Lunga GMAs are unsustainable agricultural extension, whereas fire charcoal production, wood and illegal timber extraction are the major drivers of forest degradation, with harvested forests left severely depleted and high-value species replaced by those of low value. These causes/drivers are a result of the overwhelming reliance of the largely poor rural (and some cases urban) populations on natural resources (e.g. charcoal) for day-to-day survival. About 76% of the Zambian population depends on wood fuel energy (Chidumayo, 1997). At this time, there is no operational sustainable natural forest management system anywhere in Zambia. Namwala GMA to the East of Kafue is one of the three highest charcoal-producing GMAs nationally (Simasiku et al., 2008), servicing local communities and the densely populated area towards Lusaka. Mufunta to the West of Kafue is also a significant charcoal producing areas (F. Mupemo, REMNPAS, pers. comm.) In West Lunga GMAs, charcoal production is an emerging threat, increasing the urgency for large, intact forests to be secured in terms of new PA categories. Mining activities in North Western Province are increasing rapidly with the discovery of large copper ore bodies at the Kalumbila and Ntambu prospecting sites by First Quantum Minerals. It can be observed from the development of Kansanshi Mine in Solwezi that within a 5-year period of the mine being functional, charcoal production has extended to as far as 50 km away to meet the fuel needs of the resulting settlers. For the Ntambu mining area 20km North of the Chibwika-Ntambu GMA boundary, the energy requirements for new settlers would exert pressure on the GMA, as well as the Musele-Matebo GMA/Luji Forest Reserve, both of which form part of the intended expanded core of the West Lunga Management Area.

Baseline

Zambia’s Ministry of Tourism, Environment and Natural Resources has the mandate to conserve the country’s biodiversity, wildlife and natural resources, and is committed in terms of the 6th National Development Plan to strengthening management of National Parks, forests resources and wetlands, and integrating climate change into national development. The Ministry’s budget for 2012-2016 for natural resources, including management of Protected Areas and Forestry Reserves, will be an estimated $75 million (based on the 2012 budget of $14.8 million). The Forestry Department, with an estimated budget of $11,3 million for 2011-2015, has jurisdiction over National and Local Forest Reserves, and the authority to issue timber-harvesting licenses and collect revenues from charcoal production and firewood collection. The Department is currently testing models for Joint Forest Management (JFM) and incorporated into a revised National Forest Policy and legislation. JFM emphasizes management of natural forests as a community-based business that generates revenue and operates sustainably on a cost-recovery basis.

The country’s 19 National Parks and the 36 adjacent Game Management Areas are managed by the Zambian Wildlife Authority (ZAWA), an agency under the MTENR, which generates revenue from the Parks in addition to its budget allocation. Government promotes the formation of public-private-community partnerships and is in the process of creating legislation for new PA categories which could be declared on GMA land – Game Reserves, Partnership Parks and National Reserves. Over the period 2012-2016 ZAWA is projected to spend $60 million in total on managing the PA estate, including expenditure on enforcement and maintenance of tourism infrastructure, unevenly spread across the Parks. It also includes expenditure on CBNRM in the GMAs – involving local communities in management through 63 Community Resource Boards. The management of wildlife and habitat in GMAs is enforceable with a management plan prepared by the CRBs and approved by the ZAWA Board, and a number of GMAs have undertaken a planning process, supported by ZAWA, including project target GMA Chibwika-Ntambu. The Zambian Government is also investing heavily in tourism, and in terms of its 6th National Development Plan will focus over the next five-year period on the Northern Circuit around Mweru wa Ntipa and Nsumbu National Parks. A total of $50 million has already been spent or committed on infrastructural investments to promote tourism and wildlife conservation, including a road, power line and airport, and further large-scale expenditure on Park infrastructure and enforcement is planned.

A major intervention is currently in the inception phase in the Greater Kafue National Park, one of the proposed project’s target Park systems, through the Millennium Challenge Corporation (MCC), a US government agency providing large-scale grants to developing countries. The MCC will invest $90 million in the Greater Kafue National Park and Community Economic Development Project over the next five years to increase incomes derived through sustainable nature-based tourism by improving access to and within KNP. The Millennium Challenge Account Zambia will build the capacity for improved park and wildlife management, and increase the benefits from tourism and diversified livelihood activities to communities adjacent to the park. MCC-funded feasibility studies currently underway include needs assessments and a study of priority investments in four selected GMAs, different ones from those where the proposed project will be working. Investment areas are infrastructure, marketing, governance, enforcement and resource management.

The Zambian government has committed itself to a National REDD-Readiness Programme and facilitated this though a Climate Change Facilitation Unit, temporarily housed in the MTENR, but due to be taken up by the Ministry of Energy and Water Development. The UN-REDD Programme has committed $4.49 million to the Zambia Quick Start Initiative (2010-2013), which aims to prepare Zambian institutions and stakeholders for effective nationwide implementation of the REDD+ mechanism. This will involve building institutional and stakeholder capacity developing an enabling policy environment for REDD+, developing REDD+ benefit-sharing models and developing Monitoring, Reporting and Verification (MRV) systems. This work will be carried out in tandem with the Integrated Land Use Assessment II programme, which aims to improve the utilisation & dissemination of ILUA-generated data (from the first phase 2005-2008) and seeks to enhance methodological and human capacity in collecting and analyzing forest resource information for sustainable forest management, REDD monitoring and carbon inventory. The Government of Finland is funding the ILUAII work with FAO 1.9 million euros for three years. This is being complemented by two surveys of charcoal use and production patterns being conducted by the United States Forestry Service in collaboration with USAID in southern Zambia, and by CIFOR in collaboration with Government of Finland in northern Zambia, as part of a REDD support programme to which $9 million has been committed over the next few years.

Despite a unique natural resource base, the aforementioned governance structures, funded initiatives and new legislative efforts, Zambia’s PA estate still faces many problems, with significant barriers in place to effective conservation of biodiversity through the PA estate, to sustainable land and forest management, and to effective climate change mitigation.

| Barriers to effective conservation of biodiversity through the PA estate | Barriers to optimal management effectiveness and sustainability include weaknesses in the overall framework of the PA system. Administrative, financial and enforcement capacity need to be strengthened at Head Office level in ZAWA, and a sustainable financing plan is needed for the system as a whole, including innovative revenue-generating activities, and marketing and communication strategies, and a system systems to collect Park user fees. A related barrier is the relevant actors’ inadequate knowledge and information base with regard to carbon finance (REDD, LULUCF, voluntary carbon markets) opportunities and procedures, leading to unfulfilled potential to generate revenue for the PA system. At site level in Kafue and West Lunga core NPs there are also barriers to management effectiveness and financial sustainability, with a need for staff training, strengthened enforcement and business planning. Both these NPs were estimated in 2007 as only likely to be financially viable within 15 years and their full tourism potential has not been exploited, especially in West Lunga. There is a need to establish partnerships with tourism operators and other private sector actors, to support certain aspects of PA management. Finally, a barrier to effective conservation of biodiversity is the under-representation of five vegetation classes in the core NPs, including Miombo Woodlands and Dry Evergreen Forest. There is a need for new PAs to be demarcated and gazetted in the current GMA territory around these Parks to increase the areas of these threatened ecosystems under effective conservation, using the new legal categories for government and community co-managed Game Reserves and Partnership Parks. This involves expanding enforcement operations and putting in place the management and financial structures to manage them efficiently and sustainably. |
| --- | --- |
| Barriers to sustainable land and forest management | Barriers to sustainable land and forest management in GMAs arise from the absence of effective land use and governance, which means there are no restrictions on conversion to agriculture and de facto open access to resources. There is also a lack of institutional capacity amongst GMA role-players such as ZAWA, the Forestry Department and traditional authorities for sustainable land and forest management. There is a need both for pilot projects that convincingly demonstrate SFM and SLM practices such as sustainable harvesting of forest resources and sustainable agriculture, and for extension and training that builds these stakeholders’ capacity to promote such practices with communities and to undertake enforcement. A third barrier to effective management of resources in the GMAs is a perception by communities that that PAs generate few benefits but impose high costs, and that community interests are insufficiently catered for, with 70-80% of trophy hunting license fees being spent outside the GMAs. There is a need for state and private sector resources to be invested in these areas through public-private-community partnerships, stimulating jobs and livelihoods relating to enforcement, tourism, reforestation and energy. Revenue generation should also be maximized through collecting fees for the charcoal and firewood trade, and to access REDD+ funding by management structures of new PAs. |
| Barriers to effective climate change mitigation | Barriers to successful widespread adoption of low-carbon technologies and sustainable charcoal production include the absence of appropriate technology – there is a need to introduce, demonstrate and disseminate technologies such as charcoal retort kilns. Another barrier is the complexity and difficulty of accessing finance to scale up the adoption of such new technologies, including finance internationally through voluntary carbon markets. Access to carbon markets is impeded by a further barrier – the absence of agreed national tools to measure emissions, as well as the absence of an integrated and comprehensive national data system. |

B. 2. incremental /Additional cost reasoning:  describes the incremental (GEF Trust Fund) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF  financing and the associated global environmental benefits  to be delivered by the project:

The GEF-funded project would address these multiple barriers in an integrated manner, working across the PA estate of Zambia as a whole, as well as making site-level interventions in key areas. The focus on Zambia’s PA estate is appropriate, given that the core PA system has enormous potential to be expanded through the broader system of GMAs and Forest Reserves, which covers over 40% of the country and coincides with many of the highest carbon stocks.  The broader system also has high value in terms of conservation of watershed services and of biodiversity, and provides the highest value for generating multiple benefits.

Incremental activities and benefits: The proposed project is requesting a grant from the GEF, which will be used to support activities that are incremental to the existing baseline(s). The project is designed to lift barriers that are currently preventing the effective and sustainable management of the PA estate in Zambia, with its multiple benefits. Without this GEF intervention, there will be a continuing loss of globally significant biodiversity values and ecosystem services, as well as the loss over time of forest cover, resulting in increased carbon emissions released into the atmosphere. This will happen despite the considerable intervention of Government and other stakeholders in the area. The loss of forest cover and biodiversity will happen in three ways. Firstly, areas of intact natural forests and biodiversity significance will remain excluded from the core PA system. Secondly, there will be increased isolation within core PAs, unless landscape planning provides for effective conservation management of dispersal areas and corridors. Thirdly, there will be increased pressures on the core PAs, from resource-dependent communities, and reduced capacities / finance to provide adequate protection. Project interventions under GEF will add to, and support, Government's commitment to addressing these complex pressures and problems. The project will strengthen institutional capacities for PA and forest management within ZAWA, the Forestry Department, the Community Resource Boards and local government. The integrity of core PAs will be secured by expanding them strategically, and by integrating their management with that of surrounding landscapes and corridors on production lands. This will increase the proportion of under-represented vegetation classes effectively conserved and help rebuild wildlife populations. Management effectiveness in Zambian NPs and GMAs has been shown to be positively correlated with increases in wildlife.

The baseline activities mentioned – while significant, particularly with regard to MCC investments in KNP – fall short of comprehensively addressing the challenges of sustainable land and forest management in the Zambian PA system and would benefit from an additional suite of complementary activities. The solution being proposed by this project is to strengthen the institutional and financial capacity of ZAWA and local stakeholders living in GMAs – as well as provide them with the requisite planning tools and low-carbon technologies – to better address core drivers of resource degradation and provide for the long-term ecological, social and financial sustainability of the landscapes in which they live and operate. The project will develop capacity to apply, sustain and replicate innovative management practices across the PA estate through three complementary components:

Component 1: Increasing the sustainability of Zambia PA system and the effectiveness of its core areas This component focuses on strengthening the entire system of core PAs in Zambia through a systemic focus on ZAWA – building Head Office capacity, training park managers and establishing a business intelligence system. It also involves addressing the financing gap by influencing budget allocations, accessing carbon finance, increasing Park entrance fee collection and revenue from trophy hunting and photographic tourism, and involving new private sector partners. At site level, the component aims to strengthen management effectiveness and financial sustainability in the two target core PAs – Kafue and West Lunga. The core PA estate will also be expanded through establishing new Partnership Parks and Game Reserves in the target GMAs, using the new PA categories to be legislated shortly, involving zoning, reclassification and establishment of infrastructure including new ranger posts.

Component 2:  Sustainable land and forest management in targeted Game Management Areas This component works to promote sustainable land and forest management practices in four GMAs which provide a buffer zone to the NPs - Mufunta and Namwala in Greater Kafue NP, and Lukwakwa and Chibwika-Ntambu in West Lunga Management Area, all of which have both valuable biodiversity and conflicting land use pressures. The component aims to strengthen land use governance and planning in these four GMAs, though multi-stakeholder partnerships, land-use planning, and business planning to increase income. The component also involves a farmer support programme for intensive and sustainable agriculture, including infrastructure investment, and extension to develop capacity of communities and government stakeholders for sustainable land and forest resource management. Community woodlots of fast-growing trees will be established on underproductive agricultural land to supply the improved kilns (Component 3) with renewable biomass.

Component 3: Establishment of financial incentives and dissemination of appropriate technologies for sustainable charcoal production and SFM in selected charcoal-producing GMAs This component involves the deployment of low-carbon technologies and the development of sustainable charcoal schemes in two of the target GMAs. Community co-operatives will be formed and trained in the use of charcoal retort kilns, which are more efficient and emit significantly less GHGs than traditional earth kilns. A total of 240 improved kilns will be introduced (120 each in two GMAs) to replace earth kilns, with licenses granted for all improved kilns. Scale-up of this improved technology will be promoted through the development of an integrated national data system on charcoal use and production in GMAs, and a national standardized baseline for sustainable charcoal. Financial incentives will be implemented to encourage the purchase of kilns by producer associations outside of the project area (see Annexure 2 for detail).

Global Environmental Benefits: Global environmental benefits arising from the project include reducing threats to the PA system and strengthening it to enable the continued provision of multiple benefits on large scale – globally significant biodiversity, carbon stocks and watershed services. The benefits are: i) Expansion of core PAs through increased protection to 5,579 km2 of forest ecosystems; ii) increased coverage of Miombo woodlands from 6.1% of its original extent under effective conservation nationally to 7%, and Dry Evergreen Forest from 4.5% nationally to 11.7%; iii) Recovery in populations of important wildlife species, including such as elephant, buffalo, impala, puku, warthog, zebra, Kafue lechwe and Tsessebe.iii) 311,688 t C emissions are avoided over 5 years by changing deforestation rate from 0.3% pa to 0% over 2,680 km2 of Dry Evergreen Forest; iv) 298,218 t C emissions are avoided over 5 years by changing deforestation rate from 0.3% pa to 0% over 2,899 km2 of Miombo Woodland; v) Adoption of sustainable land management and conservation farming practices over 7,215 km2; vi) total avoided emissions of 319,680 tons of CO2 equivalent over 15 years from switching to renewable biomass; vii) 302,400 t CO2 reduction in GHG emissions from methane capture over 15 years.

Alternative approaches considered: One alternative approach considered was to design a national Sustainable Forest Management project. To work largely with forestry stakeholders, however, would ignore the fact that large portions of Zambia’s forested areas fall into National Parks and their surrounding GMAs. There is a need to work with ZAWA, and with a range of stakeholders living in and utilizing GMAs, as well as forestry stakeholders, in order to increase protection and improve management of Zambia’s forests. For this reason, a project focusing on the PA estate 	and a broad range of stakeholders provides the best value for generating multiple benefits and is seen as likely to have more impact than a stand-alone national SFM project.

A second alternative considered was to design separate and stand-alone projects in terms of the Biodiversity, Land Degradation and Climate Change Mitigation focal areas. This alternative was not chosen because it would have meant that the synergies between these focal areas could not be maximized, for example, between the establishment of a financial sustainability plan for protected areas and the sourcing of carbon finance, or the synergy between the establishment of community woodlots to supply an alternative and sustainable source of biomass and the deployment of improved charcoal kilns. Tackling these issues in isolation would not maximize the PA system’s potential for delivering high value multiple benefits, hence Zambia’s decision to design an integrated, multifocal project.

B.3. 	Describe the socio-economic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund)

In contrast to the national parks, where officially no human settlement is tolerated, the buffer zones are areas with human habitation and their resources support various livelihood activities and provide safety nets in times of need. The households in the GMAs depend on forest and woodland resources to meet their energy needs, construction and roofing materials, fodder for livestock, wild foods that support a healthy diet, and medicines. The United Nations estimates that 78% of Zambia’s rural population lives below the national poverty line (UN Statistics 2007). Modal income for the rural areas of the country, representing 26% of the country, was ZMK 150,000 – 300,000 (US$31-62) per month (Central Statistics Office: 2010).

Improved income streams for charcoal workers will be a key outcome of this project. The charcoal production process is done mostly by men. Women are also involved at different stages in production, transportation and sale. It is common in Zambia to find women selling small quantities of charcoal to end-users at market points in urban centers. The management and development of energy resources at the grass-root level requires the effective participation of both genders in the decision- making process. Further, women play a vital role in the provision and management of energy resources in the rural areas and need to take proactive decisions on how energy resources are managed and developed. Protected area managers will benefit from a new collaboration with local and adjacent communities who will employ traditional community-based enforcement systems to assist with the management of boundary areas.

The six GMAs selected for targeting under components #3 and #4 are in some poorest areas of the country. North Western province – the location of West Lunga NP – is the second poorest province in the country. A socio-economic survey carried out in the Chibwika-Ntambu GMA by the reclassification project estimated that 90% of the respondents were classified as poor or very poor. Their estimated earnings from agriculture for the past year ranged from ZMK100,000-ZMK600,000 (USD20-120). Supplementary activities include fishing, beekeeping, vegetable gardening, beer brewing and informal cross-border trading, free-range livestock production, carpentry, and small-scale artisanal mining (West Lunga Trust 2007).

Marginal health benefits will be realized from the adoption of improved technologies in carbonization. Direct inhalation of noxious fumes, as well as cases of bodily burns and bruises from traditional practices will also be reduced.  Employment creation along the charcoal production chain will result from formalization of the trade. Local entrepreneurs will have to meet the demand for the improved kilns which can be fabricated from materials available locally. Charcoal associations can begin to function as small businesses offering expanded employment opportunities. The new category of PA for community management of wildlife and other resources will be a major step in strengthening community control of land and resources and in maximizing the revenue they receive from natural resource management.

Institutional and financial sustainability: Provision is being made to ensure the institutional, financial and socio-economic sustainability of the project outcomes. A number of factors combine to ensure that the prospects for achieving a high level of sustainability are good. Firstly, there is a commitment by government to the ongoing development of community-public-private partnerships, using the new policy and legislative framework which will be in place by the time the project commences. This means that private sector partners will continue to be sought to fulfil untapped tourism potential, generating revenue for the PA system. Secondly, there is also a commitment by government, specifically MTENR and ZAWA, to outing in place a financial sustainability plan for the PA system thorough this project, and implementing it on an ongoing basis, and also to mainstream the needs of PA financing into national development planning. This will include influencing budget allocations, accessing carbon finance (REDD, LULUCF, voluntary carbon markets), increasing Park entrance fee collection, increasing revenue from trophy hunting and photographic tourism, and involvement of new private sector partners in GMAs and areas of NPs without tourism facilities to increase concession revenues. Finally, at site level, the project will also improve financial sustainability of the two target core National Parks and their surrounding GMAs, by undertaking the collaborative development of site-specific business plans.

B.4	Indicate risks, including climate change risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks to  be further developed during the project design:

| Risk | Rating | Risk Mitigation Measure |
| --- | --- | --- |
| Revision of wildlife policy and Wildlife Act is not completed, and new PA categories are not signed into force. | M | This risk is mitigated by the Ministry’s commitment in writing to complete the legal and policy review by the end of 2011. The Millennium Challenge Corporation investment also has an interest in helping to ensure that the process is completed. |
| Landscape planning and subsequent implementation of plan will be affected by institutional inflexibility, reducing collaborative efforts between PAs, District Councils and Villages. | L/M | ZAWA and Forestry Department have selected to work in landscapes where this risk will be muted, and builds on strong Government will to strengthen management of the North Western province natural resource management. The project will invest in building conflict avoidance and resolution skills, and build on existing institutional mechanisms such as district environmental committees, and seek to establish economic arguments for the tradeoffs between wildlife, forestry, tourism, agriculture and other land uses and to reduce opportunity costs thus reducing the prospects that institutions will not find common ground |
| Climate change could lead to changed distributions of BD components, and changes in community and private sector demands on wildlife and forest resources. | L | A focus on landscapes (as opposed to small patches), with sufficient buffer zone protection mitigates against short-term change and ensures ecosystem resilience. The maintenance of forest cover is a good adaptation policy in the face of uncertainty (because rainfall in this region is expected to increase; the maintenance of watershed integrity is critical to avoid major floods). |
| Significant increases in externally driven pressures on forest and protected area resources e.g. logging pressures, mining. | M | This project will work at a landscape level, with a focus on governance processes in the Forest PAs. Mining and logging concessions will be dealt with in a land-use plans and areas identified where these activities can take place. |
| The type of kilns proposed could prove to be unsuitable for the designated areas; semi-industrial charcoal kilns may only be a viable option in large-scale, plantation-based production enterprises; and modern, stationary kilns may not be viable if the woodlots are not well-established and managed. | M | The PPG phase should assess whether retort kilns are indeed the appropriate technology choice for the GMAs proposed following an in-depth assessment of the institutional capacity and environmental considerations of the areas; if stationary retort kilns are deemed not appropriate other types of improved kilns like the casamance kiln should be considered for piloting in the project. |
| The introduction of improved kilns in charcoal-producing areas with large areas of standing forest could actually create a perverse incentive whereby efficiencies incentivize more production of charcoal rather than replacement of inefficient methods and reduced pressure on forests. | M/H | The project will ensure that all kilns piloted have appropriate licenses and regulations and will be monitored by the forestry department and local authorities. As part of the certification schemes the producer cooperatives will have to document the amount of charcoal produced with each kiln. The Component 3 work will also take place within the context of land use planning involving a broad range of stakeholders, to ensure that wise decisions are made. |
| Resource-use could exceed resource generation. Even fast growing short-rotation species will take up to five years to mature. Moreover climate change risks and rainfall variability could impact both sequestration rates for the forests under management, as well as the ability of the woodlots to produce a sufficient amount of renewable biomass for the kilns using coppicing methods. | M | - Specific criteria will be developed to validate the areas in the GMAs that can support the activities in component #3 and will include evidence demonstrating (i) available woodfuel resources, (ii) secure land tenure, (iii) access to markets, (iv) and past charcoal production experience and other indicators. |
| Another project risk is the possible collapse of the carbon markets or a drop in the carbon prices. This will reduce the benefits accrued to the communities but will not affect the GEBs to be accrued from the project. | L | With regards to the carbon finance component, the control of the carbon markets is beyond the scope of this project but alternatives to a failure in the compliance markets regulated under the UNFCCC will leave the option of voluntary markets. |
| Finally, various factors have to come together simultanously to support technology transfer. The technology has to be adaptable to the local communities’ preferences, affordable and accessible. The financing options for the uptake of the technology transfer component post-project will have to be carefully assessed, as will maintenance issues. | M | The PPG phase will look at all these issues in-depth and propose appropriate mechanisms and structures to insure appropriate uptake and long-term sustainability of the tech transfer activities. The choice for only focusing those activities in two GMAs in the same geographic area was to ensure that the project team can devote sufficient time and resources to making sure that the relevant stakeholders receive the maximum attention and technical support to operate and maintain the technologies. A strategy will be developed during the project as regards the financing options for other interested producer groups to purchase related technologies. |

B.5. Identify key stakeholders involved in the project including the private sector, civil society organizations, local and indigenous communities, and their respective roles, as applicable:

A number of key stakeholder groupings will be involved in carrying out the project:

- The Ministry of Tourism, Environment and Natural Resources will be the principal implementing partner and a key role-player in overseeing improved management effectiveness and financial sustainability of the PA system.

- The Zambia Wildlife Authority (ZAWA) as an agency under the MTENR and the main national institution responsible for the management of the wildlife estate in Zambia will be the key partner for implementing Component 1, building the PA system at national level, and focusing on two target core National Parks.

- The Forestry Department under MTENR will be key in implementing sustainable forest management and the establishment of community woodlots in Component 2.

- The Ministry of Energy and Water Development will be a key partner on Component 3 of the project around climate change mitigation and the introduction of new low-carbon technology.

- The Natural Resources Consultative Forum will also provide the Ministry with solid inputs on policy development from civil society – this will facilitate MTENR’s oversight role for ZAWA and other PA areas managers.

- Local communities and Community Resource Boards in the four target GMAs, as well as the traditional Chiefs of the area, and District Councils, will be key role-players in Components 2 and 3, undertaking joint management and planning for the GMAs and supporting the introduction of the new technology.

- Private Sector Tourism Investors will be key both in GMAs and in the two NPs targeted - better protected area management practices will result in improved wildlife estates, which will lead to an increase in the flow of photographic safari tourists as well to an increase in hunting concessions in rehabilitated GMA. This increased tourist traffic will be the engine of growth for private sector investments which will in turn lead to increased foreign exchange earnings at local level and employment opportunities for local communities.

- Tertiary institutions, in particular the University of Zambia and the Copperbelt University are expected to play a role in research efforts supporting the project, in the charcoal technology and on remote sensing and land cover data.

| Key Stakeholder | Role |
| --- | --- |
| Ministry of Tourism, Environment and Natural Resources | Key implementing partner |
| Zambia Wildlife Agency | Responsible party |
| Forestry Department | Responsible party |
| Ministry of Energy and Water Development | To be clarified |
| District Councils in relevant districts | Cooperation on implementation |
| Chiefs / traditional authorities in 4 GMAs | Cooperation on implementation |
| Zambia UN-REDD Programme | Cooperation on implementation |
| University of Zambia | Cooperation on implementation |
| Copperbelt University | Cooperation on implementation |
| Ministry of Agriculture and Cooperatives | Sharing information |
| Department of Fisheries | Sharing information |
| Tourism Department | Sharing information |
| Zambia Environmental Management Agency | Sharing information |
| Millennium Challenge Corporation / MCA Zambia | Co-finance and sharing information |
| USAID / United States Forestry Service | Co-finance and sharing information |

B.6. Outline the coordination with other related initiatives:

The proposed project adds value to a number of related initiatives as set out below:

The GEF-funded Reclassification and Effective Management of the National Protected Areas System project was funded by the GEF through UNDP from 2006-2012, aiming to pilot public-private-community partnerships in and around GMAs. Lessons learned from pilot projects in Bangweulu and Lower Zambezi and their broad-based stakeholder interactions are to be applied to future management of PAs, and to assist with the integration of successful conservation management across larger areas. The main aim of the project was to lay the groundwork for the revision of the Wildlife, Tourism and Heritage Acts to include new PA categories and provide a framework for partnerships. The proposed GEF project add value to this by strengthening the PA system at a central level and addressing multiple global benefits, taking a multifocal approach to which comprises a highly catalytic GEF programme on PAs in the country.

A project funded by the International Climate Initiative in West Lunga National Park acted as an additional demonstration project in terms of the REMNPAS work and developed infrastructure for enforcement and monitoring in the Park. It also laid the groundwork for reclassification of neighboring GMAs and Forest Reserves. The proposed GEF project goes beyond the ICI project to work inside GMAs on sustainable land and forest management as well as introducing new technology to reduce pressure on forest use. The project also takes a systemic approach, targeting two Parks but doing this within the framework of a system-wide intervention.

The World Bank-funded Programme for the Development of Kafue National Park as a Model of Sustainable Economic Use and Biodiversity Conservation in a Management Extensive Environment, also known as the “SEED Project” is funded by the Norwegian Government ($12 million), the Global Environment Facility ($4 million) and International Development Agency ($7.5 million). It started implementing 2005 and phases out in 2011, and its focus is to develop the Park to generate revenue and help develop communities bordering the park or living in the adjacent GMAs. The SEED Project has focused mainly on the core National Park, while the proposed GEF project works in the broader landscape, including the GMAs as buffers to the Park. It also goes beyond a focus on biodiversity and wildlife to address sustainable land management, sustainable forest management and climate change mitigation.

The GEF-funded MSP Extension of Kasanka Management System to Lavushi Manda National Park (LMNP) is USD $1.8 million (total with co-financing) project implemented by the World Bank that aims to improve the sustainable conservation management of the Lavushi Manda National Park and the Kasanka National Park to uplift their ecological value as part of the greater Bangweulu ecosystem. It consists of three thematic components: 1) Conservation systems; 2) Stakeholder involvement; and Management capacity building. The project, which started last year, will develop and implement an effective PA management system based on the existing and successful Public-Private Partnership approach (PPP) in KNP. The project builds on the impressive progress made in LMNP's neighboring KNP due to an efficient management scheme, introduced and administered over the past 20 years by the non-governmental Kasanka Trust (KTL), under a special PPP agreement with ZAWA.

The GEF-funded regional Sustainable Management of the Nyika Transfrontier Conservation Area Project is a USD $11 million (total with co-financing) project implemented by the World Bank that aims to establish more effective transfrontier management of biodiversity in the Nyika Transfrontier Conservation Area, which straddles Zambia and Malawi. The Project supports transboundary biodiversity conservation through planning, institution building, fundraising and capacity building for protected area management within three blocks belonging to the Nyika TFCA. The project is coordinated through ZAWA for all Zambia-related activities. It started in early 2011 year and is planned to run through 2016.

The GEF-funded MSP Open Africa North South Tourism Corridor (OANSTC) is a USD 1.2 million (total with co-financing) project that has the objective of contributing to mainstreaming biodiversity into pro-poor tourism by communities along the OANSTC routes (Zambia and Namibia) through barrier removal. The project has an incentive-based and unique "partnership tourism route" approach, aimed at enhanced awareness, training and capacity-building for current and future local business operators The key actors on the Zambian side are the Ministry of Tourism, Environment and Natural Resources and the Zambian Tourism Board. The project started in 2008 and will be completed in 2011.

The Lusaka Sustainable Energy Project is a registered CDM project which aims to provide up to 30,000 households of Lusaka City with highly efficient and durable Save80 Cooking Systems to replace the consumption of charcoal from non-renewable biomass by the use of small sticks from renewable sources of biomass. The project reduces greenhouse gas emission through the switch from non-renewably logged trees for charcoal fuel to the sustainable and renewable biomass from brittle sticks of renewably harvested fuelwood through the use of the highly efficient Save80 Cooking Systems.

WCS and COMACO (Community Markets for Conservation) are doing a range of rural livelihood, SLM and charcoal-related interventions as part of their broader mandate to protect biodiversity conservation and reverse environmental degradation across the Zambia’s Luangwa Valley. They are using GPS to monitor charcoal stacks along main roads in COMACO target areas and control areas and Nyimba CTC maintains an on-going monitoring of families who sell charcoal along the Great east Highway. The focus of their charcoal work is Mwasemphangwe, where COMACO is working with the forestry dept and Luangwa Valley Natural Resource Management Partnership to confiscate illegal charcoal and provide alternative livelihoods for charcoal producers.

A WWF-Zambia CBNRM project in Mufunta GMA, supported by the Royal Government of Norway, aims to establish efficient, equitable and sustainable participatory natural resource management systems. The WWF project has been successful in combating poaching by appointing village scouts and promoting alternative livelihoods such as horticulture, poultry, piggery, honey and wax production, fish farming, carpentry, tailoring and handicrafts, with 10 village action groups. and 154 enterprise and commodity groups established. The Mufunta Land-use and Natural Resource Management Plan will be used to zone the GMA and allocate land in consultation with the CRB, but has not yet been signed off by government. The GEF project will build on WWF’s work and add value to it through the introduction of kilns, the promotion of tourism partnerships and the furthering of the reclassification process.

C.   describe the GEF agency’s comparative advantage to implement this project:

Protected Areas is one of UNDP’s signature programmes and the agency has a large portfolio of PA projects across Africa dealing with PA expansion and using strategies attuned to the African reality. The proposed project falls clearly within the comparative advantage of UNDP as stated in the GEF Council Paper C31.5.rev.1 (Intervention type: capacity building/technical assistance). UNDP was selected by the Government of Zambia and has a comparative advantage in addressing the primary challenge of this project - environmental conservation in protected landscapes. Furthermore, UNDP has a large global portfolio and extensive experience in developing the enabling environment (policy, governance, institutional capacity and management know-how) at the systems level to improve PA management effectiveness. The proposed project will benefit as well from UNDP's experience as implementing agency for several other related GEF-funded projects in Zambia, which will complement and create synergies with the proposed project.

UNDP is implementing a number of biomass and bio-energy projects across Africa. Promoting more efficient resource use through, for example, energy-efficient cook stoves has been demonstrated successfully in a range of UNDP projects, most recently in Kenya, Pakistan and Bhutan. Other projects in UNDP’s biomass energy portfolio range from community-run biogas digesters (e.g. Bhutan, Tanzania, Egypt) to gasifiers for turbine-driven on-grid electricity generation (e.g. in India, Malaysia and  Brazil). UNDP is a founding member of the Nairobi Framework which aims to increase carbon markets participation and build capacity in Sub-Saharan Africa and elsewhere. Moreover, Zambia is one of six participating countries in the UNDP/UNEP CDM Capacity Development Project for sub-Saharan Africa. The project will also work in close collaboration with UNDP’s MDG Carbon Facility (MDG-CF), a unique public-private partnership facility that offers emission reduction projects a comprehensive package of project development services, and is developing several biomass energy projects in Africa as part of its current portfolio. Finally, Zambia is currently one of nine developing countries in the world that will be piloting the UN-REDD Programme, which aims to prepare countries for future REDD+ implementation. The first phase in the UN-REDD Programme is the UN-REDD Quick Start initiative. The NJP will develop a National REDD+ strategy and thereby assist in attracting financing for National REDD+ implementation.

C.1   indicate the co-financing amount the GEF agency is bringing to the project:

UNDP is contributing US$ 4 million in cash from its core environment program.

c.2  how does the project fit into the GEF agency’s program (reflected in documents such as UNDAF, CAS, etc.)  and staff capacity in the country to follow up project implementation:

The project fits into UNDP’s programme in Zambia as framed by the United Nations Development Assistance Framework (UNDAF) for the Republic of Zambia 2011-2015, which has five outcomes covering: (1) HIV and AIDS; (2) Sustainable Livelihoods and Food Security; (3) Human Development; (4); Climate Change, Environment and Disaster Risk Reduction and Response; and, (5) Good Governance and Gender Equality. This project relates to Outcome 4, which aims to achieve the development of institutional capacities to effectively sustain, manage and protect livelihoods from the risks of climate change, disasters and environmental degradation, and will be pursued through the realization of three Country Programme Outcomes around disaster mitigation, adaptation and sustainable community-based natural resource management. This project also relates to Outcome 2 – achieving more sustained levels of development, employment and food security.

The Country Programme Action Plan is a five-year framework defining mutual cooperation between the Government of Zambia and UNDP prepared in line with the UNDAF. It will contribute towards Zambia’s goals of reducing poverty, eradicating hunger, becoming a middle-income country by 2030, and achieving the Millennium Development Goals (MDGs) by 2015. The CPAP sets out the challenge to increase productivity and reduce deforestation and land degradation, and to increase capacity for enforcement and management of programmes for the sustainable utilization of natural resources. The CPAP aims to implement policies and legal frameworks for sustainable community based natural resources management. It involves working to establish functional Community Resource Boards with by-laws for addressing deforestation and wildlife management. It involves scaling up gender-sensitive livelihood partnerships by MTENR and the Ministry of Community Development and Social Services (MCDSS) to promote community participation in natural resource management. It also involves working to reduce the annual average deforestation rate in the period from 2011-2015, and the establishment of public-private and community partnerships for natural wildlife and forestry management.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template).

| Name | Position | Ministry | Date (MM/DD/YYYY) |
| --- | --- | --- | --- |
| Dr K. Nkowani | Operational Focal Point (now Acting Permanent Secretary) | MTENR | 26 April 2011 |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF policies and procedures and meets the GEF/LDCF/SCCF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator & Name | Signature | Date (09/18/2011) | Project Contact Person | Telephone | Email Address |
| Yannick Glemarec, UNDP/GEF Executive Coordinator |  | September 22, 2011 | Caroline Petersen ai / Alice Ruhweza, Regional Technical Advisor Ecosystems and Biodiversity and Lucas Black, Regional Technical Advisor – Climate Change Mitigation & Carbon Finance UNDP Environment and Energy Group | +27123548123 +27 12 354-8132 | alice.ruhweza@undp.org lucas.black@undp.org |

ANNEXURE 1

Figure 1 - Map of Zambia’s Protected Area Estates (National Parks and Game Management Areas – GMAs)

West Lunga NP and neighboring GMAs

Kafue NP and neighboring GMAs

Figure 2 - Map of Zambian Ecosystems

Annexure 2: Detail on Component 3 – charcoal retort kilns

Charcoal production and slash and burn agriculture have been identified as the most prominent drivers of deforestation and degradation of Miombo woodlands in Zambia. Charcoal production was estimated to reach 1.3 million tons per year in 2010 and is expected to increase substantially in the coming decade. Most of the charcoal produced in Zambia comes from Brachystegia, Isoberlinia and Julbernardia (Miombo) tree species. Charcoal production in GMAs is most prominent in those areas with concentrated populations or along roads leading to urban areas. Before the 1980s, the Forest Department carried out extensive forest management activities production in GMAs and forest reserves to supervise woodland clearing by charcoal producers to ensure that producers followed felling regulations and paid appropriate licensing fees; however with current budgetary shortfalls and lack of resources those oversight activities have been significantly diminished.

The impact of the charcoal trade on Zambian forests/woodlands is exacerbated by the inefficient methods being used in its processing and consumption. Almost all the charcoal in Zambia is made using the earth clamp method, the process of which involves felling trees and cross-cutting them into short logs, piling the logs into a clamp, covering the clamp with soil lumps, igniting the kiln, carbonizing the wood into charcoal, and then harvesting and packaging the charcoal into bags. The conversion efficiency of this type of kiln is typically very low – estimated at about 10-15%. In addition to being inefficient and requiring a large amount of wood, this carbonization process emits significant amounts of CH4 and non-methane hydrocarbons (NMHC). Moreover as one recent study in Zambia noted the severe heat generated by a traditional kiln during wood carbonization kills all sources of regeneration in the area and colonization by new trees may take many decades.  In 1996 a Charcoal Production Manual, the first of its kind in Zambia, was produced as part of a cooperation between the MEWD and the Stockholm Environment Institute (SEI). The manual attempted to explain best practices for the traditional earth clamp production method but made clear in the introduction that it “does not deal with other [more efficient] methods as these are not yet practiced in Zambia.” Moreover it did not address the issue of land use change in charcoal production. As in any bioenergy system, carbon dynamics from charcoal are linked to both terrestrial carbon dynamics and emissions from fuel processing and combustion.

A number of recent studies have demonstrated that for areas where charcoal is a primary driver of deforestation the introduction of improved kilns can be a powerful tool in both reducing emissions and increasing forest cover. The results of a study by the World Bank on the impacts of improved kilns in a Miombo woodlands context demonstrated that improved kilns were by far the most effective instruments in improving forest cover compared to a business-as-usual scenario (see diagram below which illustrates the combined and individual impacts of the three policy options on forest cover).

The diagram above illustrates that improved kiln technology – although only increasing efficiency – has a significant positive impact on forest area. The relatively larger impact of improved kiln technology on forest management, compared to policy interventions on the consumption side, can be explained by the fact that production-side measures are not offset by population growth and, thus, have a more profound impact. In an effort to popularize more efficient charcoal production technologies and fuel switch practices, this component will replace traditional earth kilns with 240 improved retort kilns in two GMAs where charcoal production is a major driver of forest degradation. The project will make every effort to source these kilns from local manufacturers if possible. Whereas a regular kiln carbonises biomass in a closed container and releases gas and vapour to the atmosphere, a retort carbonizes biomass, condenses the gas and vapor, and collects the gas or liquid tar in a container (resulting in low emissions of CH4 during production). The Adam’s retort represents one of the most efficient means of producing good-quality charcoal with less fuel wood and can carbonize about 3 m3 of wood (about 600 – 900 kg) per run. Up to three runs can be done in a week yielding up to a 1 ton of charcoal (the effective carbonisation of the biomass takes only about 30 hours compared with 4-5 days for traditional kilns). Retorts are designed to meet the needs of producer cooperatives as they are relatively expensive (USD 700 – 900) per unit and are immovable.

The two GMAs where the retorts will be disseminated will be Mufunta and Namwala bordering the Kafue NP. The choice of these GMAs was based on consultations with a variety of stakeholders and data analysis, including a recent study done by the Millennium Challenge Corporation (Situational and Livelihoods Analysis Study in Nine Game Management Areas, surrounding Kafue National Park, Zambia – August 2011) which inventoried all the livelihood activities in each GMA (including charcoal production). The table below shows that Mufunta and Namwala are GMAs where charcoal production is already happening (the report notes that charcoal production from Julbernardia paniculata and Brachystegia spp. trees is an important livelihood activity for both men and women in these areas) and which threatens SLM and biodiversity conservation. Moreover they are both areas with a large amount of standing forests still remaining and demonstrated high or medium interest in or potential for scale-up of charcoal production based on interviews with GMA inhabitants. Therefore they offer an optimal localized environment in which to pilot improved charcoal technologies (i.e. Adam retort kilns) to reduce pressure on critical forest resources.

Excerpt from MCC Livelihoods Study – Analysis of Charcoal Production in Mufunta and Namwala GMAs

| GMA | Type of Livelihood Activity | For Livelihoods Involving Natural Resources: Current Status of Natural Resource Based on Availability | Currently Supports or Threatens Sustainable Land use or Conservation of Biodiversity | Interest in/or Potential for Scaling up: High, Med, Low ** |
| --- | --- | --- | --- | --- |
| Mufunta | Charcoal | High | Threatens | High |
| Namwala | Charcoal | High | Threatens | Medium |

Several related activities will accompany and precede the introduction of the kilns. In collaboration with Community Resource Boards (CRBs), village leaders and forestry officials, community cooperatives will be formed and trained in the two GMAs on sustainable charcoal production and marketing, as well as the use of new kiln technologies (both installation, operations and maintenance). The selection of sites in the GMAs will be done in collaboration with the relevant ILUA assessments, GMA management plans and zoning guidelines. The formation of producer cooperatives will be linked to the establishment of the community woodlots under component #2 and the sites for the kilns will be situated in proximity to the woodlot sites. Each cooperative that receives a kiln must be licensed and certified with the appropriate local authorities (and will be monitored by the project) to insure that the kilns are replacing the traditional practices and not supplementing existing practices.  Several mines in the Copperbelt are involved in large reforestation schemes and stove EE dissemination schemes and based on consultations have expressed a strong interest in potentially partnering with the project on funding such low-carbon technologies (kilns) or assistance with the community woodlots.

With regards to the renewable biomass produced for the kilns in the community woodlots, the choice of which fuel wood to use will be done based on consultations and analysis done at the PPG stage. Acacia polycantha, Acacia mearnsii, Casuatina equisetifolia, Eucalyptus camadulensis, Acacia seyal, Leuceana leucocephala and Tectonia grandis are shortlisted as possible short-rotation crops for sustainable charcoal fuel sources under this project. These species have successfully been used for sustainable charcoal production in other parts of East Africa (Mugo & Ong, 2006). An estimated minimum of 3,200 hectares of land will need to be coppiced at any given time to provide the sustainable biomass source for the kilns; a short-term scheme will have to be developed to provide fuel stock for the kilns until the first harvesting period of the woodlots. In order to insure the integrity of the emissions reductions and avoided deforestation it is essential that the management and operations of the woodlots in collaborations with the kiln operation be integrated in as formalized a structure as possible. Institutions like Copperbelt University who are doing research on improved charcoal technologies and best practices in the sustainable management of Miombo woodland ecosystems will also be incorporated into this project component.

Together with related activities funded by USAID, the project will establish a national data inventory on charcoal use and consumption in GMAs and also provide technical assistance and assess the feasibility of linking the sustainable charcoal technologies implemented under the project to a carbon finance scheme under voluntary carbon markets) using a PoA approach. This will be assisted by the development of a standardized national baseline for sustainable charcoal production in Zambia together with support from several well-known carbon finance consulting firms who has done significant work in this area. The complex procedures for baseline emissions calculation are the prime obstacle for sustainable charcoal carbon finance projects and it is thus essential to simplify these methodologies allowing the use of standard baseline factors (existing methodologies have alone so far not been able to incentivise the more efficient production of charcoal). Standardized approaches can overcome the problem of high transaction costs incurred by the plant-specific data collection. As a result, standardized approaches will likely enable the implementation of emission reduction projects which have previously been prevented; the burden of baseline determination would largely be shifted away from project developers by establishing standardized factors. Given that it is a “public good”, GEF funds will only be used for fund the standardized baseline and will not cover actual project development costs. Finally, if the dissemination of the improved kilns are successfully operated and confirmed as an appropriate and in-demand technology for the pilot cooperatives a feasibility study will be conducted in the latter years of the project that will specifically analyze the most appropriate financing mechanism to be established to allow charcoal producers who are not part of the project to mobilize the financial resources needed to rather manufacture or purchase similar kilns under commercial terms (see Annexure 2 on cost-effectiveness).

Annexure 3: Cost-Effectiveness

The immediate global benefits from this project include direct emission reduction estimates from the introduction of the improved kiln technologies and sustainable woodlots (avoided deforestation) – assuming all 240 kilns are operational and using renewable biomass – of 622,000 t CO2 over 15 years, which translates into an abatement ratio of  5 USD of GEF CCM funds requested per tCO2 reduced. With regards to the incremental value of GEF-funded CC mitigation activities, the proposed additional GHG emission reductions from low-carbon technologies and SFM practices (switch to renewable biomass) compared to the business-as-usual case are based on the following assumptions:

| 1) | The baseline is comprised of traditional charcoal-making facilities (earth kiln or other) – to be verified during the PPG phase) in the targeted GMAs. |
| --- | --- |
| 2) | In the baseline scenario assuming the use of inefficient method, a minimum charcoal yield of 250 kg can be obtained from about 1,200 kg wood. |
| 3) | In each of the targeted GMAs, with the support of GEF funds traditional charcoal-making facilities are replaced by 1) 120 high-yield, low-emission Adam’s retorts, each with an average yield of 250 kg of charcoal from 650 kg of wood (dry basis). |
| 4) | Based on field studies, each Adam retort is capable of producing 250 kg of charcoal in each batch process with a 30-hour batch duration. Each retort therefore has an average annual production of 24 tons of charcoal. |
| 5) | Optimized charcoal production from use of retorts can entirely avoid the emissions of CH4 from pyrolytic gases resulting from traditional processes. Avoiding CH4 emissions through such a technology represents an emission reduction of roughly 3.5 tCO2e per tons of charcoal of produced – see conversion factor in table below (Pronatura 2009). |
| 6) | Based on data from a leading study in the region, with a conservative estimate of the percentage carbon content in wood, the CO2 reduction conversion factor savings from avoiding the use of non-renewable biomass represents an emission reduction of roughly 3.7 tCO2e per ton of charcoal of produced (Bailis, Modeling climate change mitigation from alternative methods of charcoal production in Kenya, 2009). |
| 7) | Based on other studies, the capital cost of each retort is approximately USD 840 (cost of retort, plus 20-percent allowance to cover other capital costs). GEF funding will cover these costs. Adam retorts have an average lifetime of 15 years. The Return on Investment (ROI) has not been determined but the estiamted pay-back period (if purchased on a commercial basis) and IRR (from higher earnings and carbon finance revenue) will be calculated during the PPG phase. |
| 8) | For each retort, total losses (i.e., production facility, charcoal transport, and distribution to consumers) do not exceed 5 percent. |
| 9) | The estimated amount of hectares of land to be set-aside for the establishment of woodlots for cultivation of a sustainable biomass source for the kilns mentions above is approximately 3,200 ha based on a short-rotation coppice system. Field trials in Bondo district of Kenya show that Acacia polycantha can be harvested for charcoal at year 5 (Mugo and Ong, 2006). 3,200 ha of Acacia polycantha matches the woodfuel requirements of 240 retorts over five years. The choice of an appropriate indigenous or exotic species for the aforementioned woodlots in a Zambian context will be made during the PPG phase based on appropritae analysis and the assumptions on harvesting rates and hectares under SFM modified. The total wood biomass in miombo woodlands of central Zambia is estimated at 90 t ha-1, on average consisting of 90% cord wood suitable for charcoal production and 10% small stems and twigs (Chidumayo 1990). |

The tables below highlight the various assumptions used for the ERs in the project with regards to component #3:

PIF_WITH_MACRO

1.0

Dry Evergreen Forest stores 78 t C/ha – from UN Collaborative Programme on REDD in Developing Countries: Zambia National Joint Programme Document, 2010, p. 39.

Miombo Woodland (semi-evergreen) stores 69 t C/ha – from UN Collaborative Programme on REDD in Developing Countries: Zambia National Joint Programme Document, 2010, p. 39.

www.nicholas.duke.edu/institute/pb-redd.pdf

Simasiku, P., Simwanza, H.I., Tembo, G., Bandyopadhyay, S., Pavy, J-M. (2008) The Impact of Wildlife Management Policies on Communities and Conservation in Game Management Areas in Zambia: Message to Policy Makers. National Resources Consultative Forum

Zambia Environment Outlook, Environmental Council of Zambia, 2008

Opportunities and challenges for sustainable management of miombo woodlands: the Zambian perspective, Fabian M. Malambo and Stephen Syampungani (Copperbelt University, School of Natural Resources), Working Papers of the Finnish Forest Research Institute 98

Simasiku, P., Simwanza, H.I., Tembo, G., Bandyopadhyay, S., Pavy, J-M. (2008) The Impact of Wildlife Management Policies on Communities and Conservation in Game Management Areas in Zambia: Message to Policy Makers. National Resources Consultative Forum

Commonwealth Forestry Association: Zambia Branch

Others are Kalahari Woodland, Grasslands and Munga Woodland.

Global Environment Facility (2010) Results of the GEF Biodiversity Portfolio Monitoring and Learning Review Mission, Zambia

Dry Evergreen Forest stores 78 t C/ha – from UN Collaborative Programme on REDD in Developing Countries: Zambia National Joint Programme Document, 2010, p. 39.

State of Environment Report, Solwezi District, Government of Zambia, February 2008

Ibid, pg. 48

Malambo et al., op cit

Determining the Non-Renewable portion of Biomass Utilized in Charcoal Production for Lusaka, Emmanuel Ngulube Chidumayo, Univ. of Zambia

Manual for Charcoal Production in Earth Kilns in Zambia, MEMD, 1996.

Several of these assumptions are taken from the chapter on Improved Charcoal Production (6.1) in the Low-carbon Energy Projects for Development in Sub-Saharan Africa Unveiling the Potential: Addressing the Barriers, Christophe de Gouvello, Felix B. Dayo, and Massamba Thioye, World Bank (2008). Others are from Towards a more standardized approach to baselines and additionality under the CDM - Determining nationally appropriate performance standards and default factors, Case study II: Charcoal production, Perspectives GmbH, May 2010