request for  

Project Type:  
Type of Trust Fund:
[image: image2.jpg]gef




part i: project information
	Project Title: 5th Operational Phase of the GEF Small Grants Program in Brazil

	Country(ies):
	Brazil
	GEF Project ID:

	4560

	GEF Agency(ies):
	           
	GEF Agency Project ID:
	4578

	Other Executing Partner(s):
	Instituto Sociedade População e Natureza (ISPN) 
	Submission Date:
	2012-10-24

	GEF Focal Area (s):
	
	Project Duration(Months)
	48

	Name of Parent Program (if applicable):

· For SFM/REDD+ 
	5th Operational Phase of the GEF Small Grants Program
	Agency Fee ($):
	400,000


A. Focal Area Strategy framework

	Focal Area Objectives
	Expected FA Outcomes
	Expected FA Outputs
	Trust Fund
	Grant Amount ($)
	Cofinancing

($)

	    
	Increase in sustainably managed landscapes and seascapes that integrate

biodiversity conservation

	- National and sub-national land-use plans (15) that incorporate biodiversity and ecosystem services valuation

- Certified production land-scapes and seascapes (400,000 hectares)

	
	1,761,390
	1,746,500

	    
	Restoration and enhancement of carbon stocks in forests and non-forest lands, including peat land
	Forests and non-forest lands under good management practices
	
	1,761,390
	1,750,000

	    
	Improved agricultural management



	Types of innovative SL/WM practices introduced at field level



	
	474,055
	489,502

	    
	Sustained flow of services in agro-ecosystems
	- Suitable SL/WM interventions to increase vege-tative cover in agro-ecosystems

- Information on SLM technologies and good practice guidelines disseminated.

	
	431,889
	443,898

	    
	Increased capacity of stakeholders to diagnose, understand and transform complex dynamic nature of global environmental problems and develop local solutions
	Stakeholders are better informed via workshops and trainings about global challenges and local actions required
	
	135,100
	130,100

	    
	Evaluation of programs and projects strengthened and improved against expected results



	Learning system established to provide feedback to policy, strategies and management decisions from evaluation reports



	
	26,000
	26,000

	    
	Increased capacity for evaluation 
	Capacities for monitoring of projects and programs developed
	
	14,000
	14,000

	    
	Outcome 3.2: On-the-ground modest actions implemented in water quality, quantity (including basins draining areas of melting ice), fisheries, and coastal habitat demonstrations for “blue forests” to protect carbon
	Demo-scale local action implemented, including in basins with melting ice and to restore/protect coastal “blue forests” (up to $904,000 corresponding to 20% of programmable project  resources, pending community requests - co-financing will match GEF resources)
	
	0
	0

	    
	     
	     
	
	     
	     

	    
	     
	     
	
	     
	     

	    
	Others
	     
	
	     
	     

	Subtotal
	
	4,603,824 FORMTEXT 

4,603,824

	4,600,000 FORMTEXT 

4,600,000


	 Project management cost

	
	396,176
	450000

	Total project costs
	
	5,000,000 FORMTEXT 

5,000,000

	5,050,000 FORMTEXT 

5,050,000



B. Project Framework

	Project Objective: Conservation of the Cerrado and Caatinga biomes of Brazil through community initiatives on sustainable resource use, and actions that maintain or enhance carbon stocks and increase areas under sustainable land management   

	Project Component
	Grant Type


	Expected Outcomes
	Expected Outputs
	Trust Fund
	Grant Amount ($)
	 Confirmed Cofinancing

($) 

	 1 - Biodiversity conservation in the production landscape through community-based sustainable resource use and management of natural resources 
	
	1.1- Biodiversity conservation on community land enhanced on > 300,000 ha of the Cerrado and 100,000 ha of the Caatinga ecosystems
	1.1.1 - Sustainable land and resource use management plans developed and implemented (>15 plans)  

1.1.2- Sustainable management, harvesting and marketing of wild resources (>800 families, each obtaining >US$900 of income annually)

1.1.3 - In-situ conservation  initiatives for endangered native species implemented

(50 plant species and 25 animal species)

1.1.4 - Commercial network for Cerrado and Caatinga bio-products operational (>15,000 families participate)

1.1.5 – Entrepreneurship training program and business management and marketing for sustainable biodiversity products delivered (>120 community members) 

	
	1,607,000
	1,600,000

	 2 – Maintenance of carbon stocks through avoidance of land use change and improved agriculture and forest management at the community level
	
	2.1 - Carbon stocks increased through Caatinga and Cerrado ecosystems restoration

- 500 ha restored in Caatinga and 500 ha restored in Cerrado, equivalent to 18,200 and 37,400 tCO2e sequestred respectively

2.2 - Sustainable agriculture and forest management avoiding conversion to pasture and monoculture and maintaining environmental services

> 80,000 ha equivalent to 4,370,400 tCO2e avoided

	2.1.1 – Community reforestation program with native species or assisted natural regeneration implemented

(>30 initiatives covering 1000 ha)

2.1.2 - Baseline information for LULUCF and carbon stocks collected and periodic monitoring performed

2.2.1 – Sustainable forest management on community lands implemented (>20 initiatives covering >40,000 ha)

2.2.2 - Sustainable agriculture program implemented (>15 initiatives on >15,000 ha)

2.2.3 – Fire prevention training and implementation programs delivered (>5 initiatives on >25,000 ha)

	
	1,607,000
	1,600,000

	 3 – Implementation of sustainable land management techniques that prevent land degradation, restore agro-ecosystem services, and improve livelihoods of local communities
	
	3.1 - Innovative soil management techniques for sustainable land management adopted by communities

> 200 ha in Caatinga and 400 ha in Cerrado;

3.2 - Adoption of innovative water management techniques at community level, benefiting 2,000 ha with improved ecosystem services

	3.1.1 – Replication of successful agroecological management techniques (>1,200 families);

3.1.2- Soil erosion control with native and adapted species implemented (>40 initiatives);

3.2.1 – Water management and conservation implemented including rainwater harvesting

(>1,200 families)     

	
	814,824
	800,000

	 4 - Capacity development and knowledge management to help communities deliver global environmental benefits
	
	4.1- Community leaders proficient in project design and management and aware of global environmental issues (>150 leaders)

4.2- Knowledge produced by the projects codified and available to enable replication and up-scaling of successful interventions 

4.3- Information from projects available to other communities, government institutions and development practitioners at the local, national and international levels as feedback to policy implementation

	4.1.1 Training program on global environmental issues, project design, implementation, monitoring and evaluation delivered

(>3 workshops for 150 trainees)

4.2.1- Knowledge management strategy formulated and implemented with at least 3 knowledge products 

4.2.2 - Publications on lessons learnt on biodiversity conservation,  climate change mitigation, and sustainable land and forest management prepared and disseminated

(>6 publications)

4.3.1- Production and dissemination of at least 2 yearly thematic reports

	
	285,000
	350,000

	 5 - Monitoring and evaluation
	
	5.1 - Adaptive management and accountability achieved through monitoring and evaluation of the country programme and grant portfolio
	5.1.1 – Regular monitoring of all supported projects performed;

5.1.2 - Mid-term review and final independent evaluation of country program conducted

	
	290,000
	250,000

	      
	
	     
	     
	
	     
	     

	      
	
	     
	     
	
	     
	     

	      
	
	     
	     
	
	     
	     

	      
	
	     
	     
	
	     
	     

	      
	
	     
	     
	
	     
	     

	Subtotal
	
	4,603,824 FORMTEXT 

4,603,824

	4,600,000 FORMTEXT 

4,600,000


	Project management Cost

	
	396,176
	450,000

	Total project costs
	
	5,000,000 FORMTEXT 

5000000

	5,050,000 FORMTEXT 

5050000



C. sources of confirmed Cofinancing for the project by source and by name ($)

	Sources of Co-financing 
	Name of Co-financier (source)
	Type of Cofinancing
	Cofinancing Amount ($) 

	
	UNDP
	
	100,000

	
	UNDP
	
	1,000,000

	
	Grantees
	
	800,000

	
	Grantees
	
	800,000

	
	ISPN
	
	2,350,000

	
	     
	
	     

	
	     
	
	     

	
	     
	
	     

	
	     
	
	     

	
	     
	
	     

	Total Co-financing
	5,050,000 FORMTEXT 

5,050,000



D. GEF/LDCF/SCCF/NPIF Resources Requested by agency, Focal Area  and country1 
	GEF Agency
	Type of Trust Fund
	Focal Area
	Country Name/

Global
	(in $)

	
	
	
	
	Grant Amount (a)
	Agency Fee (b)2
	Total c=a+b

	
	
	
	Brazil
	2,000,000
	160,000
	2,160,000 FORMTEXT 

2,160,000


	
	
	
	Brazil
	2,000,000
	160,000
	2,160,000 FORMTEXT 

2,160,000


	
	
	
	Brazil
	1,000,000
	80,000
	1,080,000 FORMTEXT 

1,080,000


	
	
	
	     
	     
	     
	0 FORMTEXT 

0


	
	
	
	     
	     
	     
	0 FORMTEXT 

0


	
	
	
	     
	     
	     
	0 FORMTEXT 

0


	
	
	
	     
	     
	     
	0 FORMTEXT 

0


	
	
	
	     
	     
	     
	0 FORMTEXT 

0


	
	
	
	     
	     
	     
	0 FORMTEXT 

0


	
	
	
	     
	     
	     
	0 FORMTEXT 

0


	Total Grant Resources
	5,000,000 FORMTEXT 

5,000,000

	400,000 FORMTEXT 

400,000

	5,400,000 FORMTEXT 

5,400,000



E. Consultants working for technical assistance components:
	Component
	Estimated Person Weeks
	Grant Amount
($)
	Cofinancing
 ($)
	Project Total
 ($)

	Local consultants*
	1,106.00
	757,980
	500,000
	1,257,980 FORMTEXT 

1,257,980


	International consultants*
	0.00
	0
	0
	0 FORMTEXT 

0


	Total
	
	757,980 FORMTEXT 

757,980

	500,000 FORMTEXT 

500,000

	1,257,980 FORMTEXT 

1,257,980



*  Details to be provided in Annex C.
F. Project management cost
	Cost Items
	Total Estimated Person Weeks/Months
	Grant Amount
($)
	Co-financing
 ($)
	Project Total
 ($)

	Local consultants*
	416.00
	209,717
	280,000
	489,717 FORMTEXT 

489,717


	International consultants*
	0
	0
	0
	0 FORMTEXT 

0


	Office facilities, equipment, vehicles and communications*
	
	130,000
	100,000
	230,000 FORMTEXT 

230,000


	Travel*
	
	38,038
	30,000
	68,038 FORMTEXT 

68,038


	Others**
	Communication costs:
	16,521
	37,845
	54,366 FORMTEXT 

54,366


	
	Miscellaneous (Bank and exchange fees):
	1,900
	2,155
	4,055 FORMTEXT 

4,055


	Total
	
	396,176 FORMTEXT 

396,176

	450,000 FORMTEXT 

450,000

	846,176 FORMTEXT 

846,176



* Details to be provided in Annex C.                    ** For others, to be clearly specified by overwriting fields *(1) and *(2).
G. Does the project include a “non-grant” instrument?                      
     (If non-grant instruments are used, provide in Annex E an indicative calendar of expected reflows to your Agency 
       and to the GEF/LDCF/SCCF/NPIF Trust Fund).           
H. describe the budgeted m &e plan:  

•
Final Evaluation: A final evaluation will be done for each project. The Country Program Manager should validate the terms of reference for these evaluations and vet the evaluation consultant. The cost of this evaluation will be part of the grant budget.

	•
Small grants Audit: The GEF-SGP Country Program Manager will organize audits to selected grantee organizations on a risk basis. The cost of these audits will be charged to the grant project budget.



Table 1: Monitoring and Evaluation Workplan And Budget
	Type of M&E activity
	Responsible Parties
	Budget US$

Excluding project team staff time
	Time frame

	Country Programme Level

	Inception Workshop and Report
	· SGP Country Programme Manager and team

· NSC

· UNDP Communities TA and CO
	No cost to project budget


	Within first three months of project start up



	Measurement of Means of Verification of project results.
	· Country Programme Manager will oversee the hiring of technical assistance 
	Indicative cost: 3,000$
Cost included in BD and CC Components
	To be finalized during the first project year and annually if required.

	Measurement of Means of Verification for Project Progress on output delivery and implementation 
	· Oversight by SGP Country Program Manager

· Technical Assistance


	Indicative cost : 2,000$

travel - $12,000 , car rent – $3,000

And included in BD and CC Components
	Annually, prior to APR/PIR and to the definition of annual work plans 

	APR/PIR
	· UNDP Communities TA 

· SGP Country Programme Manager

· UNDP CO
	No cost to project budget

Annual visit by COMMUNITIES TA – travel cost from IA fee
	Annually 

	Periodic status/ progress reports
	· SGP Country Programme Manager and team 
	Indicative cost : 2,000$

Costs included in other project lines
	Quarterly

	SGP Global Database update
	· SGP Country Programme Manager and team

· Technical Assistance 
	Indicative cost :

Costs included in other project lines
	Quarterly

	Mid-term Evaluation  
	· SGP Country Programme Manager and team

· UNDP STA

· External Consultants (i.e. evaluation team)
	Indicative cost :

$15,000

Travel – $3,000, car rent – $1,000
	At the mid-point of project implementation. 

	Country Programme Manager experience exchange workshops with other countries
	· SGP Country Programme Managers

· GEF SGP CPMT
	Indicative cost of country team participation in upgraded countries exchange workshop: $10,000
	At the mid-point of project implementation.

	Final Evaluation


	· SGP Country Programme Manager and team 

· UNDP CO

· UNDP Communities TA

· External Consultants (i.e. evaluation team)
	Indicative cost: 

$ 22,000 

Travel - $5,000, car rent – $2,000
	At least three months before the end of project implementation

	Project Terminal Report
	· SGP Country Programme Manager and team 

· UNDP CO

· Consultant 

· Publication editing, layout and printing
	Indicative cost:

 $10,000 for consultant 

Editing, layout and printing - Included in KM Component   
	At least three months before the end of the project

	
	
	
	

	SUB-TOTAL


	US$ 90,000
	


	Individual grant level 

	Type of M&E activity
	Responsible Parties
	Budget US$
	Time frame

	Selection Process
	· SGP Country Programme Manager and team 

· NSC members

· Local consultants
	Indicative cost: 2,320 $

No cost for the project budget
	After each call for proposals in years 1, 2 and 3 of project’s execution

	Training  Workshops for selected grantees
	· SGP Country Programme Manager and team 

· NSC members
	Indicative cost: 12,000$

Included in KM Component   
	After selection of grants in years 1, 2 and 3 of project’s execution

	Field monitoring visits
	· SGP Country Programme Manager and Technical Assistance 

· Eventually NSC members
	Indicative cost: 

Travel $135,000

Car rent $11,000
	At least once in the lifetime of project. Additional visits on a risk basis

	Monitoring of and technical support to community application of M&E methods and tools 
	· SGP Country Programme Manager and Technical Assistance

· NSC members


	Costs included in other project lines
	Half-yearly

	Progress reports
	· Beneficiary organization

· SGP Country Programme Manager
	Indicative cost: 8,280$


	Half-yearly

	Final report
	· Beneficiary organization

· SGP Country Programme Manager
	Indicative cost: 

No cost
	End of project

	Final grant evaluation
	· SGP Country Programme Manager

· National consultant

· Beneficiary organization
	Indicative cost: 

National consultant -  $12,700
	End of project

	Audit
	· SGP Country Programme Manager

· Beneficiary organization
	Indicative cost: 

Partly included in project grant budget and partly national consultant – $12,700

Travel – $5,000, 

car rent – $1,000
	Risk based

	SUB-TOTAL COST

M&E of approx 120 projects. 
	 US$ 200,000 
	

	TOTAL indicative COST

(Country Programme level + individual grant level)
	 US$ 
	290,000



part ii:  project JustiFication

A. Description of the consistency of the project with:

A.1.1.  The GEF focal area/LDCF/SCCF strategies/NPIF Initiative:  

Funding for the upgraded Brazil GEF-SGP Country Program will be drawn from the Biodiversity, Climate Change and Land Degradation focal area STAR allocations, and thus GEF-SGP will focus on objectives and outcomes consistent with GEF 5 objectives for these focal areas. In the Biodiversity focal area, it will support the second GEF strategic objective: Mainstreaming biodiversity conservation and sustainable use into production landscapes, seascapes, and sectors. GEF-SGP grants will generate global benefits by leveraging community-based efforts to conserve biodiversity through its sustainable use. To support sustainable use of biodiversity, the GEF-SGP Brazil will promote the mainstreaming of biodiversity friendly practices in the production landscape, assist small farmers and local people harvesting wild species to reach markets for sustainably produced goods, improve sustainability of community-based resource use of non-timber forest products, promote capacity-building and peer-to-peer learning to improve production quality and sustainability, and encourage discussions about relevant legislation and policies supportive of conservation.

Brazil’s upgraded GEF-SGP Country Program will be consistent with and supportive of the fifth strategic objective of the Climate Change focal area for GEF-5. GEF-SGP will promote conservation and enhancement of carbon stocks through sustainable management of land use, land-use change and forestry. 

For the Land Degradation focal area, GEF-SGP in Brazil will support the first GEF-5 objective: Maintain or improve the flow of agro-ecosystem services to sustain livelihoods of local communities. GEF-SGP will support initiatives such as sustainable land management, dissemination of water conservation practices, restoration of degraded land, and restoration of vegetation cover.

The project will address GEF-5 capacity development objectives, specifically CD-2 and CD-5 through knowledge management and capacity development to strengthen the capacities of local NGOs and CBOs to develop community projects capable of contributing to generate global environmental benefits in biodiversity conservation, climate change mitigation, and sustainable land management. The project will work with stakeholders to develop and apply monitoring and evaluation systems that strengthen accountability and adaptive management.

In accordance with the decisions of the GEF-GEF-SGP Steering Committee meeting that took place in Washington DC on 3 March 2010, a maximum of 20% of the STAR allocations may be used to support demand-driven community-based International Waters and Chemicals project proposals where synergies with the STAR focal areas can be found. GEF-SGP-funded IW and Chemicals proposals will be aligned with the following objectives:

•
IW Objective: Support transboundary water body management with community-based initiatives. GEF-SGP Brazil will strive to identify community demo initiatives that contribute to the implementation of the agreed San Francisco Basin Strategic Action Program (SAP), consistent with IW outcome 3.2 and output 3.2.



•
Chemicals Objective: Promote and support phase out of POPs and chemicals of global concern at community level.  It is not possible to select a priori the GEF-5 outcomes and outputs for the POPs focal area, but these will be identified as and when grant proposals in this focal area are approved by the GEF-SGP National Steering Committee.

A.1.2.   For projects funded from LDCF/SCCF:  the LDCF/SCCF eligibility criteria and priorities:


Not applicable 

A.1.3   For projects funded from NPIF, relevant eligibility criteria and priorities of the Fund:

        Not applicable


A.2.   National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e.  NAPAS, NAPs, NBSAPs, national communications,  TNAs, NIPs, PRSPs, NPFE, etc.:
Brazil is a Party to multiple multilateral environmental agreements, including the Convention on Biological Diversity, ratified in March 1998 (Decree nº 2,519), the Framework Convention on Climate Change, ratified in May 1994, and the Convention to Combat Desertification, ratified in 1997. The GEF-SGP is directly relevant to, supportive of, and consistent with Brazil’s national priorities and policies related to these conventions and to national development priorities, in particular, policies and programs targeting biodiversity conservation and sustainable use in the Cerrado and Caatinga biomes (the geographical focus of this project), as well as those designed to maintain carbon stocks, improve land management and prevent land degradation. The following are the most relevant strategies and plans.

National Biodiversity Strategy and Action Plan (NBSAP). Published in 2002 and modified in 2003 by the Ministry of Environment, the NBSAP identified the Cerrado and Caatinga biomes as priority conservation areas. GEF-SGP Brazil also acts directly on a key NBSAP objective i.e., the sustainable use of native species.

National Program for Cerrado Biome Conservation and Sustainable Use (Sustainable Cerrado Program), published by the Ministry of Environment in 2005, the first major effort to protect the Cerrado biome. It created the Sustainable Cerrado Program National Commission (CONACER) that promotes civil society participation. Three grantees, one GEF-SGP NSC member, as well as ISPN, are participating in the commission, which will ensure that GEF-SGP project activities will be consistent and supportive of the Cerrado Program.

The Action Plan for Prevention and Control of Deforestation and Burning in the Cerrado Biome (PPCerrado) was prepared in 2009 through several public consultations in which ISPN participated, and signed in September 2010. GEF-SGP activities are lined up with the objectives of the Plan. The main actions foreseen in the Plan, which can help consolidate important strategic actions of GEF-SGP grantees, are to support sustainable use of Cerrado species (especially pequi and babaçu palm), recovery of degraded land, and fire prevention and fire fighting. The Plan also includes technological innovation to stimulate sustainable agriculture, strengthening traditional livelihoods and access to natural resources by communities and small farmers. The Plan will be monitored by civil society through the Sustainable Cerrado Programme National Commission (CONACER).

National Policy on Traditional Peoples and Communities, published in 2007 and coordinated by the Ministry of Environment and the Ministry of Social Development and the Fight Against Hunger, recognizes the identities and specificities of traditional social groups and provides for a Social Agenda of Traditional Peoples and Communities. The Cerrado region is home to 38 ethnic groups, with a population of approximately 45,000 people. These groups include the Krahô, Xavante, Xerente, Bororo, Karajá, Kayapó, and Canela. GEF-SGP will strive to ensure that traditional peoples benefit from the project in accordance with the policy. 

National Plan for Promotion of Sociobiodiversity Product Chains – the plan, published in 2008, focuses on the promotion of income generation through added value, sustainable management, and consolidation of appropriate marketing for ten native non-timber forest products, which include important Cerrado species. The initiatives comprise:

· Inclusion of biodiversity products in the National Guaranteed Minimum Price Policy, which establishes a minimum price for each product and pays the difference if it is sold below this price. The most important species recently included in this policy are Brazil nut and açaí from the Amazon biome and pequi, babaçu palm, baru nut and mangaba from the Cerrado.

· Promotion of local value chains (of many native non-timber forest products) focusing on indigenous and quilombola (Afro-descendent) communities. 

Two recent policies related to food security are also relevant to GEF-SGP’s sustainable land management and conservation work with Caatinga and Cerrado farmers: (i) the Food Acquisition Programme from Family Agriculture (PAA), coordinated by the Ministry of Agriculture, that focuses on distribution of farming products for people in situations of food insecurity and on formation of strategic food stocks. The main purpose is to support farmers through acquisition of their production through a simplified process. The products are bought through farmer associations and cooperatives and are destined for public stocks or for donation to people in situations of food and nutritional unreliability. The purchase is made directly by the Ministry, which pays fair prices, respecting regional peculiarities, dietary habits and local market situations; and (ii) the National School Food Programme (PNAE), coordinated by the Ministry of Agriculture, that determines that at least 30% of the schools’ food supply has to be bought directly from small farmers in the region. This policy benefits GEF-SGP grantees as it creates a local and secure market for wild and cultivated products sustainably managed.

The Ministry of Environment is preparing the Plan for Deforestation Prevention and Control in the Caatinga. The GEF-SGP expansion to the Caatinga biome is lined up with the new policies of the Ministry of Environment, and can contribute to its implementation and improvement.

The National Action Programme to Combat Desertification and to Mitigate the Effects of Drought (NAP), published in 2004, focuses on poverty reduction; sustainable expansion of productive capacity; conservation and sustainable management of natural resources; as well as institutional strengthening in areas that are defined as susceptible to desertification, like the Caatinga biome. The GEF-SGP project will contribute to the NAP through supporting sustainable land management projects in line with NAP priorities such as helping to improve harvesting of wild products and their marketing, agroecological techniques, and enrichment of degraded areas.

The National Climate Change Policy (Law nº 12.187, published in 2009), contains the Brazilian commitment of 38.9% emissions reduction by 2020. It foresees actions to reduce deforestation in all Brazilian biomes and includes actions to reach the target, such as creation of protected areas, homologation of indigenous territories, improvement of the deforestation monitoring system and incentives for sustainable production activities. Brazil has also a National Plan on Climate Change, published in 2008 and currently being revised through debates at the Brazilian Forum of Climate Change and Inter-ministerial Commission on Global Climate Change. At a global level, Brazil voluntarily presented at COP 15 the national goals for reduction of emissions by 2020, now including the Cerrado, in addition to the Amazon. Government actions on climate change mitigation in the two regions will constitute the baseline for GEF-SGP CC actions through local communities. However, until the plan is approved, it is not possible to provide more detailed information in the PIF about baseline projects and investments. Brazil is currently developing a national REDD + strategy. ISPN is participating in the working group established by the government to obtain input of civil society organizations.

It is important to note that many other policies relevant to GEF-SGP Brazil are being developed by state and municipal governments, such as a state law that regulates golden grass harvest or one that determines free access to babaçu palm areas for traditional harvest. GEF-SGP’s work will take into consideration all these policies

B. Project Overview:
B.1. Describe the baseline project and the problem that it seeks to address:  

Brazil is known worldwide as one of the most important countries in terms of biological diversity. The Amazon, the Atlantic Forest and, on a smaller scale, the Pantanal have received the most international attention. On the other hand, the Cerrado, the Caatinga and the Southern Grasslands have been practically ignored in Brazil and internationally until recently. 

The Cerrado is the most biodiverse savannah in the world, with an area of more than 2 million square kilometers (some 21% of the Brazilian territory). It comprises a great variety of unique ecosystems that are particularly rich in species, and that are important for maintaining carbon stock and water resources. The Cerrado landscape is characterized by extensive savannah formations crossed by gallery forests and stream valleys. The number of vascular plants is estimated at around 10,000 species of which 44% are endemic, and herbaceous species are almost entirely endemic. Over 1,600 species of mammals, birds and reptiles have been recorded. The number of freshwater fish species is 800 of which 25% are endemic. Many large mammals that range widely throughout South America have the Cerrado as one of their principal habitats. One of the best known of these species is the maned wolf (Chrysocyon brachyurus), while two of the most unusual species are the giant armadillo (Priodontes maximus) and the giant anteater (Myrmecophaga tridactyla), which is the largest anteater in the world and can grow up to 1.9 meters in length. The Cerrado biome is still poorly represented in the protected areas system of Brazil with only 5.5% of the total land area protected, and only around 28,500 km² (1.4%) under IUCN categories I to IV.

The Caatinga – the only biome that is exclusively Brazilian, occupies 850,000 square kilometers in 10 states of northeast Brazil (over 10% of the national territory). The Caatinga is the largest dry forest region in South America and certainly one of the richest dry forests in the world. Biotic interchange over evolutionary time with surrounding biomes – i.e, Cerrado, Atlantic Forest and Amazon, has led to significant biodiversity. Although Caatinga’s biota is poorly known, studies so far have identified at least 1,200 species of vascular plants, 185 fish species, 44 lizards, 9 amphisbaenians (worm lizards), 47 snakes, 4 turtles, 3 crocodylia, 49 amphibians, 350 birds, and 80 mammals. The percentage of endemics is very high among vascular plants (around 30%). Two of the ten most threatened birds in the world, the indigo macaw (Anodorhynchus leari) and little blue macaw (Cyanopsitta spixii) are found here. Distinctive and endemic plant species include Godmania dardanoi, Cordia globosa, Billbergia fosteriana, Cereus jamacaru, Melocactus oreas, Pilosocereus gounellei, Copernicia prunifera, and Ziziphus joazeiro. Other examples of endemics include the spiny rat (Proechimys yonenagae), and several lizards, Tropidurus amathites, Tropidurus divaricatus, and Tropidurus cocorobensis.

In spite of its biodiversity significance, less than 1% of the Caatinga biome is protected. There are, however, some efforts underway to establish new protected areas such as the 26,715- hectare São Francisco Natural Monument in the Caatinga.

Threats to the Cerrado and Caatinga biomes

Among the various threats faced by the Cerrado and Caatinga biomes, land use change - where native vegetation and traditionally community-managed areas are substituted by large-scale cropland, eucalyptus monoculture, and pasture - is the most serious. Land use change in the Cerrado is the biggest single source of GHG emissions in Brazil.

The Cerrado is being cleared rapidly, with 47% of the area already deforested and about 14,000 square kilometers cleared per year, far more than the rate of deforestation in the Amazon. According to FAO 2005, the annual forest cover change in Brazil is 3,103,000 hectares, which means land use change in the Cerrado accounts for almost 50%. The main driver of this deforestation is Brazilian public policies that have historically favored or stimulated the expansion of the agricultural frontier towards the center and north of the country. These policies have resulted in enormous crop production in the Cerrado region, mostly for export, from very large farms and ranches. In 2000, the Cerrado was responsible for 35% of all crop production in Brazil, including for 58% of the country’s total soy production. In addition, there are nearly 40 million head of cattle in Cerrado. Steady growth in the agriculture and cattle sectors is projected. While agricultural expansion in the Cerrado has had a positive impact on the Brazilian economy, the negative effects on the environment and local communities are now significant. The land use change process of conversion to monoculture or pasture has lead to deforestation and landscape fragmentation, dislodging and isolating rural communities. Many traditional territories are surrounded by monocultures, such as Xingu Indigenous Park, which impedes community access to natural resources on which they traditionally depend. Several afro-descendent communities have lost their water courses or had them contaminated by agricultural inputs. In addition to the loss of biodiversity resulting from forest clearing and degradation, the agriculture system used by large-scale farms – which includes a period where the soil stays uncovered – causes soil erosion, increases rainwater runoff, carrying sediments and pollutants to water courses, and decreases soil infiltration capacity. The silting up of water courses aggravates water scarcity during the dry season and floods during the rainy season. Large-scale agriculture also causes loss of traditional crop seed varieties and genetic erosion. Local communities are emigrating and selling their lands. Cerrado communities cannot compete with large-scale farms and cattle ranches in national or international markets. According to the 2006 Brazilian Agriculture Census, 69% of all rural properties in the Cerrado are still owned by small farmers, representing 9% of the total area (some 180,000 square kilometers). Unless local communities receive support, concentration of land in large farms is likely to continue, increasing land use change.

Land use change in the Caatinga is also quite significant with an estimated 56% of the area’s native vegetation already destroyed or significantly altered by human activities. One of the most populated semi-arid areas in the world, Caatinga has 27 million inhabitants and is located in the poorest region of Brazil; only 4.6% of the municipalities have HDI equal to or higher than 0.5. The annual rainfall average of 600 mm characterizes a semi-arid climate, which makes most of the region unfit for large-scale agriculture and cattle ranching, except for areas with irrigation schemes. Irrigation policies are, however, concentrating land and water in the hands of major companies, while the small farmers who depend on agriculture for their basic subsistence are not profiting as much from it. As in the Cerrado, land property concentration is high, with 89% of the properties/farms owned by small farmers, but covering 37% of the total area only. 
Extensive goat and sheep raising, the main economic activity for local communities, has been practiced in the region for centuries with rudimentary management techniques, which means animals feed on the natural vegetation, eliminating new plants and shoots, affecting the natural regeneration of disturbed areas. A large area of the Caatinga is ranked today as highly threatened by desertification.

Besides the reduction of their territories, communities are facing water scarcity, soil erosion, and impoverishment, which are the main reasons for rural exodus in the Caatinga and for unsustainable use of natural resources. Other threats to the biome are eucalyptus and crop plantations, wood extraction for charcoal and fuel, forest fires and hunting. At least 28 animal species in this threatened ecosystem are endangered. Many plant species from this biome are used both for commercial and subsistence purposes. For example, people from this area are greatly dependent on palms such as babaçu, carnaúba, tucum and macaúba, from which lauric and oleic oils are extracted. Many trees are also used for lumber, including species such as Anadenanthera macrocarpa, Ziziphus joazeiro, Amburana cearensis, Astronium fraxinifolium, Astronium urundeuva, Tabebuia impetiginosa, Tabebuia caraiba, and Schinopsis brasiliensis, Cedrela odorata, Dalbergia variabilis, Didymopanax morototoni and Pithecellobium polycephalum.

Besides deforestation, fire is a significant cause of GHG emission in Brazil. In the Cerrado and Caatinga, fire is traditionally used by local inhabitants to open new areas for small-scale agriculture and to promote pasture re-growth during the dry season. In some cases, it is also used to manage plants of economic interest, like golden grass. However, it is common for fire to go out of control and spread to other areas, causing loss of biomass and nutrients and the deaths of animals and trees. The use of fire is being intensified, so the frequency of fire in natural areas is also higher, increasing the scope for damage.

Barriers to communities’ contribution to biodiversity conservation, sustainable land management and maintenance of carbon stocks in the Cerrado and Caatinga biomes. 

Multiple barriers need to be overcome if communities are to contribute to the preservation of the remaining areas of Cerrado and Caatinga and to take advantage of the enormous potential of these ecosystems to generate income and improve quality of life. GEF-SGP will support communities to address the following barriers: 

Implementation challenges for alternative, environmentally friendly and economically viable community livelihood options: While traditional communities and local farmers know about the potential or actual uses of many wild species, there are significant challenges involved in establishing sustainable production practices that would also be economically viable. Sawyer (2009) identified more than 100 barriers to the sustainable use of biodiversity in Brazil of which some of the most critical are the following:

· Policy and regulatory barriers: Small farmers and traditional communities find it very difficult to comply with existing regulatory frameworks, including sanitary and fiscal legislation, which was designed for other products and in a different context. These regulatory frameworks impede community access to markets and credits for the harvesting and transformation of non-timber forest products. Despite this negative context, in the last 10 years several government policies, especially those from the Ministry of Environment, Ministry of Science and Technology, Ministry of Agrarian Development and Ministry of Agriculture are focusing on sustainable use of biodiversity by small farmers and local communities. Most of these policies, see section A.2 above, are relatively new instruments and are not yet consolidated. There is a need to help implement these policies and give feedback to the relevant entity to improve them and to enable their effective application at the community level.

· Financial barriers and difficulties for production at scale: Credit lines are not available in Brazil for small-scale non-timber forest products enterprises, and there is still little interest in the private sector in investing in sustainable harvesting and marketing of wild species and related products in the Caatinga and Cerrado regions. Remoteness and dispersion of communities also create organizational, transport and other challenges to achieving sufficient quantities of products for certain markets.

· Educational barriers: The two regions where GEF-SGP Brazil is focusing have serious social problems, such as weak health and educational assistance. Most local communities are distant from urban centers and road conditions are correspondingly bad. This makes it difficult for small farmers and traditional communities to succeed in managing projects and marketing their production because they are not used to developing business plans, dealing with bureaucracy, accounting, reporting, etc. In rural Brazil it is uncommon to find people with entrepreneurial skills and there are few development practitioners who understand communities’ specificities and are willing to live in remote places. Moreover, local communities cannot obtain certification for their products because they are unable to meet the required standards or they cannot cover the cost to obtain the certificates.

 Community level constraints to sustainable land and forest management and maintenance of carbon stocks: 

· Insufficient data or access to existing data to methods for carbon stocks monitoring at the community level: There is no adequate baseline data readily available for estimating, measuring, monitoring and reporting on changes to carbon stocks and greenhouse gas emissions from LULUCF in the Cerrado and Caatinga. It is necessary to extrapolate generic data to different sites and situations. There is a need to consolidate information from different sources to establish a better baseline for LULUCF and carbon in the Cerrado and Caatinga. Furthermore, communities may not have capacity to monitor carbon stocks, considering the basic educational problem in Brazil and the rather esoteric nature of quantifying carbon.

· Lack of community access to information and training for agroecological production and sustainable land and water management: Small farmers and communities in agrarian reform settlements do not receive agricultural extension support to implement environmentally friendly agricultural practices that are suitable to local climate and soil conditions. This leads to low productivity and high indebtedness. On the other hand, indigenous groups and traditional communities’ production methods are no longer adapted to present conditions. Most of them live in smaller territories than the original ones, surrounded by deforested land, which causes changes in crop production and dietary tradition. They need to update their knowledge to adapt to the new reality. Agroecological techniques can help these groups improve their food production methods adapted to local conditions, aligned with ecosystem functions and increasing food security, but information and training on these techniques is not readily available to these communities.

GEF-SGP experience

Since its inception the geographic focus of GEF-SGP Brazil has been the Cerrado where it has supported 318 projects in 14 states. The strategy has been to promote conservation of biodiversity through sustainable use of natural resources within production landscapes that combine native vegetation and agriculture. Community projects supported by GEF-SGP Brazil have primarily focused on providing smallholders the economic incentives for conservation through income generation from sustainable use of non-timber forest products such as native fruits, nuts and seeds harvested from the wild or from cultivation. GEF-SGP has also promoted beekeeping, the cultivation or harvesting of medicinal plants, sustainable wildlife management (e.g. rheas, turtles and wild pigs) for food security of indigenous and other local communities, and handicraft production using local native fiber species, flowers and leaves. The objective has been to improve production and marketing conditions to make these activities sustainable, with an emphasis on sustainable cultivation and harvest management practices, entrepreneurship skills development, product management and marketing. A study of the GEF-SGP experience with sustainable use of biodiversity in Brazil was done for the UNDP Latin America and Caribbean regional project on the economics of biodiversity. Successful experiences across the Cerrado over the last 15 years show that sustainable use of native biodiversity resources can become an engine of growth for rural communities, creating jobs and diversifying economic activities, which in turn will halt or reverse land use change and the rural exodus.

Other GEF-SGP projects in the Cerrado focused on restoration of degraded areas, particularly those affected by deforestation, erosion and drought. GEF-SGP also learnt about the importance of enabling local communities to establish networks and creating opportunities for civil society participation in policy debates at local, sub-national and national levels. While there are many success stories, work in the Cerrado must continue to provide opportunities to many other communities in this vast region and to consolidate previous work that is now bearing fruit, with many new supportive policies being developed. Experiences such as these must be replicated by ever-larger numbers of communities for production at scale and to achieve vertical integration in the chains of production. Expanding GEF-SGP action to the Caatinga region will allow replicating the Cerrado experience in this poor but biodiversity rich region.

B. 2. incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:   

The project approach

The project objective is to contribute to the conservation of the Cerrado and Caatinga biomes of Brazil through community initiatives promoting sustainable use of biodiversity, maintenance or enhancement of carbon stocks and an increase in area under sustainable land management. Land use change is the main cause of biodiversity loss, ecosystem fragmentation and degradation, and depletion of carbon stocks in community-managed areas in these two biomes. The project strategy is to address the main drivers of land use change on small farms and traditional community lands. 

The project will focus on removing the principal barriers impeding sustainable land and resource use by local communities. During GEF-5 GEF-SGP-Brazil will consolidate and up-scale its previous work in the Cerrado and will expand its coverage to the Caatinga biome, one of the poorest regions of Brazil, where it expects to replicate successful techniques and approaches.

The global environmental benefits that will be delivered through this project are the following:

· 300,000 hectares of Cerrado and 100,000 hectares of Caatinga ecosystems with enhanced biodiversity conservation on community lands;
· 500 hectares of Caatinga forest ecosystem restored and 500 hectares restored in the Cerrado, equivalent to 37,400 tCO2e sequestered in Cerrado and 18,200 tCO2e in Caatinga;

· 80,000 hectares with sustainable agriculture and forest management  avoiding conversion to pasture and monoculture and maintaining environmental services equivalent to 4,370,400 tCO2e avoided;

· 200 hectares in Caatinga and 400 hectares in Cerrado with innovative soil management techniques adopted by communities;

· 2,000 hectares maintaining innovative sustainable water management techniques
Brief description of each planned component: 

Component 1 - Biodiversity conservation in the production landscape through community-based sustainable resource use and management of natural resources – This component fosters biodiversity conservation in the production landscape mosaic by enabling families to make a living from the sustainable community-based management of habitat and ecosystems that would otherwise be converted to crop or eucalyptus monocultures or pasture. GEF-SGP will work with community-based organizations in the Cerrado and Caatinga biomes to develop land and resource use management plans, which will be the foundation for establishing a mosaic of legal sustainable resource use practices on community-owned as well as government lands that still harbor significant biodiversity but have no protected status. More than 800 families will receive training and support in sustainable harvesting techniques for a variety of wild species; this may provide significant economic benefits which will act as an incentive to manage the harvest process sustainably and thus guarantee the continuity of the species and that of the ecosystems where they are found. To optimize economic benefits, GEF-SGP will strengthen existing or establish new commercial networks for Cerrado and Caatinga bio-products. It will also deliver an entrepreneurship training program to community grantees with partner organizations specialized in business management and marketing of bio-products as a means of developing community business skills. Such business skills are essential to ensure sustainability of project outcomes. GEF-SGP will also support in-situ conservation initiatives for endangered and other native species. The number of species - 50 plant and 25 animal species - has been established taking into consideration successful past experience, available financial resources and the large number of threatened or near threatened plant and animal species in both biomes. The National Steering Committee will develop specific criteria at project inception to facilitate the selection of the species by communities and will ensure that relevant proposals by communities are appropriately designed and monitored to ensure sustainable management. 

Outcome 1.1 - Biodiversity conservation enhanced on > 300,000 ha of community lands in the Cerrado and 100,000 ha of the Caatinga biomes

Community projects under Outcome 1.1 will focus on enabling and supporting the sustainable use of native species in the Cerrado and Caatinga biomes. This approach is based on conserving biodiversity through improvements to livelihoods and income, a strategy that has been proven to work over the last 16 years of GEF-SGP in Brazil. The outputs will be achieved through community-based initiatives for the sustainable management and conservation of endangered and other species considered important for livelihoods. 

Baseline:

The Cerrado biome is poorly represented with officially established protected areas - only 5.5% of the total land area is protected, of which only around 28,500 km² (1.4%) under IUCN categories I to IV, and less than 1% of the Caatinga area is protected. Nonetheless, both biomes contain an abundance of areas that conserve endangered species, for example, in Indigenous and Community Conserved Areas (ICCAs), in land reform settlements and on legal reserves on small farms. There is almost no information on effective strategies and methods of conserving endangered and other species in-situ, and even less so with regard to sustainable use. Community capacity to manage species sustainably is weak or mixed, at best. Moreover, communities and the public at large lack awareness about the conservation and livelihoods value of many species as well as the financial, fiscal and legal incentives for conserving species. 
While Brazil government policy has promoted the design of national and state level land planning instruments such as Agroecological Zoning and Ecological and Economic Zoning, as well as zoning guidelines for specific crops such as sugarcane, these instruments are difficult to implement and enforce in practice, particularly at the community or landscape levels. What’s more, landscape or community-level resource management plans, especially for non-timber forest products (NTFP), are quite rare since they can be expensive and technically demanding processes considered inaccessible to the vast majority of smallholder and traditional communities. In the Caatinga, forest management plans for wood and charcoal, involving both small and large scale farmers, are more common, but they generally consist of vegetation suppression, not management of standing forest. In the Cerrado there is almost no experience of forest management. Despite these obstacles, GEF-SGP Brazil’s experience thus far has shown that reconciling conservation with sustainable livelihoods is facilitated by development of a mosaic approach to land and resource use planning that enables sufficient production to at least meet basic needs while also conserving biodiversity and creating potential synergies between agricultural zones and conservation areas. Land use planning at the community, sub-watershed or landscape level can provide an important decision making framework for optimizing resource use and enabling these synergies.

Many local communities both from the Cerrado and Caatinga biomes have ancestral knowledge regarding the use and management of native species. Only recently, though, have some of these groups begun harvesting and managing these species on a wider scale, especially pequi (Caryocar brasiliense), babaçu (Orbignia phalerata), buriti (Mauritia flexuosa) and baru (Dipteryx alata) in the Cerrado and carnaúba (Copernicia prunifera), umbu (Spondias tuberosa) and licuri (Syagrus coronata) in the Caatinga. In the Cerrado, GEF-SGP has been supporting and contributing to improve native species management practices over the past 16 years through more than 150 grants. More recently, with European Commission co-financing, SGP Brazil published good management practices booklets for six species of the Cerrado and Caatinga and two guides for the full use of two species of the Cerrado. 

Marketing products based on native Caatinga and Cerrado species has proven to be a crucial piece of the strategy for improving livelihoods and conserving ecosystems. Smallholders in both the Cerrado and Caatinga face daunting challenges to access markets for products made from wild resources, due to logistical constraints, regulatory hurdles and a lack of marketing capacity. There are currently two legally established networks committed to helping local communities market their Cerrado and Caatinga products. The Caatinga-based Bodega network was founded by the NGO Agendha, which was the implementing agency of the World Bank-GEF Caatinga project and also receives support from the Brazilian Service of Support to Very Small and Small Entreprises (SEBRAE) and the Ministries of Environment and Agrarian Development. The Cerrado Central is a cooperative of cooperatives initially  supported by the GEF-SGP Brazil starting in 2008 and now supported by the Banco do Brasil Foundation. Together, these two networks benefit 75 small-scale enterprises, many of which are GEF-SGP Brazil grantees, involving 6,000 families (3,000 through Caatinga Bodega and 3,000 through Cerrado Central). Their main role has been to seek out markets for member communities by promoting products in fairs and events, although they have also helped to enhance communities’ production and marketing skills through capacity development activities such as workshops and seminars. These networks also play a central role in policy debates and in raising awareness about the shortcomings of the Brazilian fiscal and sanitary legislation, which are not suited to the reality of small-scale entrepreneurs and difficult to comply with. Supporting Caatinga Bodega and Cerrado Central will therefore contribute to overcoming some of these regulatory barriers while also helping smallholders access markets and increase the scale of their green businesses. Besides enabling small-scale enterprises in the Cerrado and Caatinga to draw together in finding solutions for common problems, these networks also play an important role in publicizing products made from native Cerrado and Caatinga plants that are not well known by the public at large. 

Communities lack skills in basic business development, including commercialization of production, and thus may fail to achieve the best prices and resulting income needed to most effectively motivate them to practice sustainable management. Value-added processes are equally rare and as a result, full market value is not realized. As well, individual community production may be insufficient to supply emerging local or sub-regional markets on a consistent basis, and the commercialization of particular products by many communities may result in destructive competition, resulting in lower prices.

To upscale sustainable harvest and marketing, the regulatory framework needs to be more attuned to smallholder conditions and interests, and the government needs to create incentives to enable smallholders to legally harvest, process, and market their goods. Sustainable harvest of these species also entails adopting practices and technologies that are seldom part of approaches used by official extension services, thus smallholder communities generally lack access to innovative technologies. Moreover, there are only a few legal instruments defining sustainable management practices for species of economic interest in the Cerrado and Caatinga. 

Alternative: 
GEF-SGP Brazil will support community initiatives that integrate biodiversity conservation into community-level planning and production of non-timber forest products. It will stimulate the development of economic incentives for sustainable biodiversity management by assisting communities to develop species management plans for in situ conservation, including sustainable harvest rates, identify and develop value-added processing of key products, strengthen commercialization networks for NTFPs, and train community entrepreneurs in business skills and strategy.   

Initiatives funded under this Outcome will also assist in overcoming the barriers to up-scaling sustainable use of native species by contributing to the formulation of guidelines to manage native species based on traditional and scientific knowledge and successful experiences supported by GEF-SGP, coupled with innovative technologies developed or adapted by the communities themselves. Project experiences will provide key inputs and knowledge that could significantly influence the legal framework to render it more suitable to smallholder conditions and interests. 

· Achievement of this Outcome will be defined by the following indicators:

· Over 15 community land/resource use management plans 

· USD 900 generated per family per annum for 800 families from sustainable use and marketing of wild resources

· In situ conservation of 50 plant and 25 animal species

· Commercial networks for bioproducts for 15,000 families

· Entrepreneurship training program operational with 120 trainees graduated

Outputs envisaged to achieve this outcome include:

1.1.1 Sustainable land/resource use management plans developed and under implementation

The community initiatives to be supported under this output will focus on the participatory drafting and implementing of no fewer than 15 community land/resource use plans. Projects will use innovative tools and methods to facilitate participation of key stakeholders, map critical resources and processes in the landscape, identify and agree on landscape outcomes, identify and agree on measures and priorities for action and determine barriers to implementation and steps to overcome them. A fundamental part of this process is the participatory definition of landscape and/or other indicators to determine progress, as part of community monitoring and evaluation of the implementation of the management plans. 
1.1.2 Sustainable management, harvesting and marketing of wild resources 

Community initiatives supported under this output will develop, improve or adopt best management practices for species important to local livelihoods through the implementation of at least 18 community based initiatives on approximately 80,000 hectares of certified production landscape. At least 800 families will obtain approximately US$ 900 in income annually through the management of species such as pequi (Caryocar brasiliense), babaçu (Orbignia phalerata), buriti (Mauritia flexuosa) and baru (Dipteryx alata) in the Cerrado and carnaúba (Copernicia prunifera), umbu (Spondias tuberosa) and licuri (Syagrus coronata) among many others used by the local communities. Key partners under this output include academic institutions and researchers who will provide essential information regarding species biology and ecosystem function. 
1.1.3 - In-situ conservation initiatives for endangered native species or others considered important for livelihoods implemented in the Cerrado and Caatinga biomes

To address these barriers, the projects supported under this output will generate specific information about the importance of endangered and other species important to livelihoods which are found outside official protected areas. Community initatives will contribute to the conservation of 50 plant and 25 animal species in situ in the Caatinga and Cerrado with tailored management and conservation plans. The selection of the specific species to be conserved will be made at the community level as part of proposal development and validated by the National Steering Committee with expert assistance, as appropriate.
Community projects will also support the establishment of ICCAs, local level areas under conservation that are not officially recognized as such. The formal designation of appropriate areas as ICCAs will provide incentives for communities to protect the natural vegetation and fauna there – this will increase potential community access to public and international funding mechanisms for biodiversity conservation. 

Each of the community initiatives supported under this output will define clear targets and indicators to be monitored through community-based surveys designed in collaboration with academic and other specialists; these surveys will provide information on the maintenance of species’ populations or resurgence of species that were previously considered rare in a particular micro-region where the project is taking place.  

1.1.4 - Commercial network for Cerrado and Caatinga bio-products strengthened

and 

1.1.5 – Entrepreneurship training program including business management and marketing implemented

Outputs 1.1.4 and 1.1.5 are closely integrated and are thus described together here.

GEF-SGP support will help to build the capacities of local entrepreneurs, improving the quality of their products and increasing market access. By involving new entrepreneurs with new products, it will strengthen the commercial networks in both biomes by helping them to expand their membership base and secure new partners. GEF-SGP support for these two networks will benefit more than 15,000 families and the training program will directly benefit around 120 leaders of green businesses. 

Initiatives supported under this output will build the capacities of the two networks – Cerrado Central and Caatinga Bodega to more effectively support sustainable, community-generated products from wild resources: participate in events and fairs to market and promote goods; provide support for exporting and certifying products; design and purchase packaging and labels; improve communication and organize meetings and assemblies, as well as provide support for general organizational strengthening.

The entrepreneurship training program will be supported through three projects, which will carry out capacity development activities focusing on sales skills, marketing, accounting, good production practices, product development, and improving production processes for entrepreneurs, associations, cooperatives, and small-scale enterprises working with native species from the Cerrado and Caatinga biomes that participate in these networks or have the potential for doing so. Training manuals aimed at strengthening the capacity of entrepreneurs in these networks will be drafted and widely circulated.

Component 2: Maintenance of carbon stocks through avoidance of land use change and improved agriculture and forest management at the community level. 
This component will involve implementation of community based initiatives involving: a) community reforestation with native species and/or farmer managed natural regeneration. The main techniques to be applied by GEF-SGP grantees are direct seed planting - a cheaper and more effective technique because it does not require establishing nurseries - and assisted natural regeneration of degraded areas, through planting seedlings in strategic spots or sowing seeds, and fencing the area to avoid cattle damage. Conventional seedling production in large nurseries will not be promoted by GEF-SGP Brazil because past experiences have been negative. On the other hand, family seedling production has been successful. b) Sustainable forest management on community lands. GEF-SGP will explore the application of national or international certification standards to community based forest management. c) Fire prevention training and implementation programs. Despite its enormous negative effects, in many places, fire is the only option for managing biomass and is less damaging and less expensive than using heavy machinery. Local communities are interested in improving their capacity to control fire and minimize its negative effects, but there are few initiatives aiming in this direction. d) Sustainable agriculture techniques such as conservation agriculture, zero-tillage, and agro-forestry that improve vegetation cover and reduce use of fire will be determined on the basis of soil and climatic conditions, and community preferences. The NSC will also develop criteria for grant selection at the inception of the Full Size Project.
For estimating carbon emission reductions GEF-SGP used as a reference the Second National Communication and the IPCC 2006 Best Practice Guidance. GEF-SGP will work with specialized organizations to validate this data at the local level at the inception of the project and to determine a method by which it will be able to monitor carbon stocks throughout the life of the project. An option that is being explored is to use the tool set being developed by the GEF Carbon Benefits Project. If successful, GEF-SGP may also be able to monitor carbon emissions reduction resulting from its biodiversity and land management initiatives (components 1 and 3). Below is a table presenting the data used for estimating CO2e benefits.

	 Location
	Ecosystem type
	Activity
	Hectares
	Actual stocks tCO2e/ha
	Potential Total tCO2e at Forest Maturity

	Caatinga
	Dry forest (<600 mm rainfall)
	Reforestation
	500
	54.63
	27,317

	Cerrado
	Savannah
	Reforestation
	500
	172.70
	86,350

	Caatinga
	Dry forest (<600 mm rainfall)
	Avoided conversion
	80,000
	54.63
	4,370,400


	Location
	Ecosystem
	Activity
	Hectares
	Annual tCO2e/ha/yr
	Source
	Four Year Total tCO2e

	Caatinga
	Dry forest (<600 mm rainfall)
	Reforestation
	500
	9.10
	IPCC
	18,200

	Cerrado
	Savannah
	Reforestation
	500
	18.70
	National Communication
	37,400


Outcome 2.1 - Carbon stocks increased through ecosystem restoration - 500 ha restored in the Caatinga and 500 ha restored in the Cerrado, equivalent to 18,200 and 37,400 tCO2e sequestered respectively
Projects and activities under Outcome 2.1 will focus on the ecosystem restoration of 1,000ha to increase carbon stocks and ensure their sustainability by benefiting local communities through improved livelihoods. It will aim at dissemination of low-cost technologies and the corresponding capacity-building for their application. GEF-SGP Brazil used estimates of above ground carbon based on the Second National Communication and the IPCC 2006 Best Practice Guidance. For GEF5, GEF-SGP will partner with specialized organizations to validate this data at the local level and to determine methods by which it will be able to monitor supported projects. One means of achieving this goal might be the GEF Carbon Benefits Project. If carbon monitoring is successful under this Outcome, GEF-SGP Brazil may consider monitoring carbon emissions reductions resulting from its biodiversity and land management initiatives (Components 1 and 3). 

Baseline:

One of the main causes of carbon emissions in Brazil is deforestation. 47% of the Cerrado and 56% of the Caatinga are already deforested, and the annual rate of deforestation has remained high in both biomes. Forests in many communities are already deforested or degraded from the expansion of monocultures, which has left less land available for smallholders. While there are policies and programs such as agricultural extension and rural credit designed to encourage more sustainable agricultural practices and recovery of degraded lands, particularly among smallholders, most traditional communities and smallholders lack access to such programs and do not have adequate technical assistance. 

High quality information about LULUCF and the measurement and monitoring of carbon stocks in the Cerrado and Caatinga biomes is not available. These ecosystems were not deemed a priority for government climate change policies until 2010, when the Cerrado was included in the national goals for reducing emissions by 2020. The Caatinga has still not been considered a priority. The Cerrado biome comprises a mix of ecosystems ranging from savanna, forests, human-managed pastures and croplands, which makes it difficult to determine or apply a single estimate of carbon amounts per hectare. Another obstacle is the lack of information about carbon dynamics, especially regarding belowground carbon. Some recent studies show that the largest portion of carbon in the Cerrado and Caatinga is found in the soil and not above ground, which sets these biomes apart from the Amazon, for instance, and entails adjustments to monitoring methods in Brazil. 

Although SGP Brazil has not worked with a specific climate change focus with the aim of measuring carbon sequestration and emissions, it has, over 16 years of working in the Cerrado, supported many initiatives promoting the recovery of native vegetation and the implementation of best soil and water management practices.  The results of these initiatives have benefited the accumulation and storage of both above and belowground carbon.

Alternative:
GEF-SGP Brazil will support traditional communities and smallholders to reforest degraded lands on their properties by planting native species among crops, thus increasing the provision of environmental services while also enhancing livelihood benefits. Moreover, supporting communities involved in low-impact extractive and production activities such as beekeeping, for instance, will encourage them to assist natural regeneration processes and purposefully protect species for their honey-producing properties that might otherwise be destroyed.

To address the lack of adequate technical assistance GEF-SGP supported projects will be highly encouraged to hire qualified technical assistance services and to involve technical staff from government agencies in training activities on sustainable farming and management of natural resources, for instance, as a means of making their extension services more suited to conservation-oriented practices and to the needs of traditional communities and smallholders. This approach will also enable extension agencies to work with farmers in developing locally adapted land use technologies that reconcile livelihoods strategies with conservation. For example, while some farmers employ conventional methods of tree planting, others may adopt simpler and cheaper technologies that oftentimes reap better results, as demonstrated in previous GEF-SGP projects in Brazil. Such technologies include: direct seed planting, as well as planting seedlings strategically and fencing off areas to keep the cattle out and assist natural regeneration (farmer-managed natural regeneration – FMNR). Replicating these technologies will entail significant savings in scarce funding because they forego building nurseries and the high costs associated with planting and caring for thousands of seedlings, thus increasing the value-for-money of these projects and giving rise to numerous opportunities of innovative and locally adapted techniques that can be replicated in situations with similar conditions.  

Local communities will also be assisted to overcome hurdles in the regulatory framework by enabling them to comply with environmental regulations under the National Forest Code, which requires permanent protection of sensitive areas such as riverbanks, springs, hilltops, and steep slopes, while also requiring that all rural properties set aside a certain percentage of their land (which varies according to the region) for protection as Legal Reserves.

The project will support the measurement of carbon stocks in areas designated by communities for reforestation and natural regeneration. It will support periodic monitoring of these forests to ensure stability of carbon stocks and to assist in generating more specific information on carbon accumulation over time.

Achievement of this Outcome will be defined by two key indicators:

a. At least 30 initiatives demonstrating innovative community based reforestation using native species, encompassing 500 hectares of Cerrado and 500 hectares of Caatinga biome.

b. Baseline LULUCF information collected; information from periodic monitoring of carbon stocks

Outputs envisaged to achieve this outcome include:

2.1.1. Community-based reforestation program implemented based on native species using planting methods or assisted natural regeneration 

The target of this output is to recover 1,000 ha of native vegetation (split between the two biomes) by supporting approximately 30 community initiatives. Community organizations will select lands to be reforested either through deliberate planting methods or through farmer-managed natural regeneration (FMNR). Special attention will be paid to community level processes of identification and application of low-cost technologies and capacity building of participating organizations. Awareness by communities of the relevant regulatory frameworks in the National Forest Code will also be addressed in the identification and design phase of each Project. While grants will go to CBOs, key partners will provide technical assistance and include NGOs and appropriate government agencies

2.1.2 - Baseline information for LULUCF and carbon stocks collected and information from periodic monitoring compiled

This output aims to quantify the contribution of the supported projects to the maintenance of carbon stocks through avoidance of land use change and improved agriculture and forest management practices. As a result, communities will be positioned to seek out Payment for Ecosystem Services, particularly through mechanisms that recognize their role in mitigating the effects of climate change.

This output is closely related to the other outputs of Component 2 since it aims to improve the capacity for monitoring the effects on carbon stocks of other actions aimed at sustainable land and forest management. A limited number of targeted initiatives will be financed under this output and technically capable NGOs or other institutions. Initiatives will define parameters and methodologies for measuring carbon stocks and sequestration rates for main forest types in the Cerrado and Caatinga biomes. Capacity development activities will be financed to raise community awareness about climate change, climate change mitigation and carbon stocks, PES and linkages with sustainable land use practices. Key partners will be NGOs and other institutions, including academia and potentially the private sector, as well as the GEF Carbon Benefits Project.

Outcome 2.2 - Sustainable agriculture and forest management avoiding conversion of forest to pasture and monoculture and maintaining environmental services > 80,000 ha equivalent to 4,370,400 tCO2e avoided 

Close to 70% of greenhouse gas emissions in Brazil stem from land use change, mostly as a result of habitat conversion or degradation associated with agriculture, cattle ranching and forestry. Projects and activities under this Outcome will focus on overcoming information and capacity barriers to the sustainable management of forest and agricultural ecosystems. Projects and activities will motivate communities to adopt sustainable management practices, techniques and systems by ensuring that sustainable management leads to an increase in food security and/or income as well as to improved ecosystem functions and carbon stocks. Projects will revive, maintain and/or adapt traditional and indigenous practices that promote sustainable land use as well as integrate them with conventional scientific knowledge, particularly in regard to fire management. Project selection will be coherent with the land/resource use management plans developed under Output 1.1.1.  

Baseline:

Throughout the dryland forests of the Caatinga and in many regions of the Cerrado, trees are harvested indiscriminately to make charcoal for domestic purposes or to fuel industries. While smallholder and traditional communities are increasingly seeking out ways of managing forests sustainably, they often lack knowledge of best management practices and legal requirements as well as the basic social organization needed to minimally process and store goods and access markets for non-timber forest products. Their low access to capital and technological alternatives also leads them to depend on slash and burn farming practices that further degrade already depleted soils and diminish biodiversity.

Technical assistance and rural extension services are generally inadequate and not suited to the reality of smallholders. Despite recent progress in government programs targeting smallholders, technological solutions and rural development policies are still mainly geared towards large-scale mono-crop systems and are generally incapable of working with small-scale farmers to develop innovative solutions locally that meet their needs while also enabling conservation of sensitive ecosystems.

Fire is widely used by large-scale farmers, ranchers and smallholders alike as a cheap, cost-effective way of clearing biomass from land for farming in the Caatinga and Cerrado. Farmers often fail to control such fires from spreading and consuming adjoining habitat. Many farmers resort to this practice because they do not have access to adequate resources (financial, technical, human) and are driven by the need for short-term returns. As well they lack the knowledge to enable them to adopt alternative methods. Additionally, the government does not provide enough support or incentives to replace the use of fire with more sustainable practices for managing croplands and pastures, and the capacity of local governments is also extremely limited. 

GEF-SGP Brazil has over the past 16 years of working in the Cerrado supported many initiatives promoting sustainable forest management and agriculture based on the premise that communities will be motivated to conserve land and water resources if they can perceive some economic benefit from doing so. GEF-SGP has accumulated a great deal of experience in supporting communities to generate NTFPs and agricultural products sustainably and the knowledge it has developed is codified in a long series of publications. 
Alternative: 

The project will contribute to overcoming obstacles to sustainable forest management by training communities and supporting them to implement appropriate forest management practices such as selective logging, harvesting of non-timber forest products, enriching secondary forests by replanting native species intercropped with high-value fruit trees and annual crops, as well as conserving primary forests. Projects may also support the construction and operation of processing and storage facilities that will enable communities to add value to forest products and empower them to continue these activities beyond the lifespan of the projects. 

These initiatives will be implemented in tandem with sustainable agriculture activities and the sustainable management, harvesting and marketing of wild resources through integrated approaches to the sustainable use of land/resources that create synergies between agriculture, forest management and livelihoods by adopting practices such as agroforestry and ecological agriculture near forest areas. Some of these initiatives may implement the relevant portions of the land and resource use management plans supported under output 1.1.1 and the Satoyama Initiative. The project will support community initiatives that provide technical training and encourage the development of innovative agricultural techniques at the local level and replicate successful experiences from other farmers in similar situations, thus helping them to increase yields and production capacity sustainably. Ultimately, this will help farmers to remain on their lands and contribute to avoiding conversion of community lands to large-scale monocultures, thereby avoiding further carbon emissions. This output will also help to increase food security by reviving, maintaining and/or adapting traditional and indigenous practices considered environmentally friendly, while also generating income for poor families.

The project will also support initiatives that contribute to overcoming capacity and knowledge barriers to improved fire management. Projects will provide training on sustainable land management techniques that maintain soil fertility, thereby reducing the need to clear more habitat as is normally done when agricultural soils are exhausted. Where the use of fire may be unavoidable for economic or other reasons, farmer organizations will be trained on the use of fire to minimize risk of fire spreading to other habitat. Carbon in above ground biomass, as well as soil carbon, will be conserved as a result.   

Achievement of this Outcome will be defined by the following indicator:

· Over 80,000 hectares of land brought under sustainable management, thus avoiding the emission of 4,370,400 tCO2e from land use change; this will include 40,000 hectares of land under sustainable forest management, 15,000 hectares of land under sustainable agriculture, and 25,000 hectares of land no longer subjected to burning
Outputs envisaged to achieve this outcome include:

2.2.1 – Sustainable forest management on community lands performed

The target for this output is to support approximately 20 initiatives aimed at managing 40,000 hectares of forests sustainably. Key partners will be NGOs and private sector entities that are knowledgeable and experienced in sustainable forest management, value-added processing and commercialization. 

2.2.2 - Sustainable agriculture program designed and implemented

This output is closely related to Output 3.1.1 – Replication of successful agroecological management techniques. Projects will focus on the adoption and dissemination of agro-ecological principles and sustainable agriculture practices such as agroforestry, zero-tillage, crop rotation, crop-livestock integration, among others. Projects funded under this output will build capacities of farmer organizations through peer-to-peer exchanges and the dissemination of technologies and practices that enhance and conserve soil carbon. The target for this output is at least 15 initiatives covering 15,000 ha.

2.2.3 – Fire prevention training and implementation programs delivered. 

This output will impact at least 25,000 ha through five initiatives. Community initiatives will build the capacity and awareness of local farmers regarding fire prevention and control, implement alternative agricultural technologies that forego the use of fire, and disseminate fire control and dissemination of alternative technologies.

Component 3: Implementation of sustainable land management techniques that prevent land degradation and restore agro-ecosystem services and that improve livelihoods of local communities.
Throughout the Cerrado and Caatinga, the vulnerability of smallholders and traditional communities is increasing due to water scarcity, soil erosion and impoverishment and loss of habitat for species that are important for local livelihoods. These vulnerabilities are aggravated by climate-related stresses such as extended droughts or flooding during the rainy season. Component 3 will focus on the implementation and replication of sustainable land management techniques that prevent land degradation and restore agro-ecosystem services while also improving livelihoods of local communities.  GEF-SGP Brazil will promote replication of sustainable land and water management techniques that have been proven to work in the Cerrado. Production practices, such as agroforestry systems, organic practices, in-situ conservation of crop genetic resources and other agroecological techniques, will be supported. They are important to the maintenance of ecosystem services, food security and income generation. To avoid soil erosion GEF-SGP will support practices that improve rainfall water infiltration and reduce torrential water runoff and erosion. Water infiltration improves seasonal stability of water courses and consequently increases opportunities for small-scale irrigation. Other rainwater harvesting techniques will be demonstrated to improve community access to water, particularly in the Caatinga. GEF-SGP will also fund community initiatives that use native and adapted species for erosion control on their farmlands.

Outcome 3.1 - Innovative soil management techniques for sustainable land management adopted by communities > 200 ha in Caatinga and 400 ha in Cerrado

This outcome will focus on the replication of sustainable land management techniques that have proven to be successful in the Cerrado under previous SGP-supported projects. In OP5, the GEF-SGP will support projects that adopt and disseminate agro-ecological practices, such as agroforestry systems, organic practices, in-situ conservation of crop genetic resources and other techniques important to the maintenance of ecosystem services, food security and income generation. To reduce soil erosion, GEF-SGP will support locally adapted solutions that improve water infiltration, enhance groundwater recharge and reduce runoff and erosion, such as reforestation and use of native and adapted species for erosion control, cultivation along contour lines, ground cover, among others.

Baseline:

Indigenous groups and traditional communities’ production methods are less and less adapted to present conditions, increasing their vulnerability to climate change as well as changes in ecosystem services brought about by massive transformations in land use. Small farmers and communities in agrarian reform settlements do not receive adequate technical assistance to implement environmentally friendly agricultural practices that are suitable to local climate and soil conditions. Community innovations are not systematized, codified or disseminated. Micro-financing for pilots, demonstrations or replication of successful practices is generally unavailable. 
On the policy front, the Cerrado Network and the GEF-SGP Brazil are participating in the formulation of the National Policy for Agroecology and Organic Production Systems under the Ministry of Agriculture. This new policy will support replication of agroecological technologies among local communities, and GEF-SGP expects to continue feeding into this policy debate by drawing from lessons learned through projects in this outcome. 

Alternative:

GEF-SGP Brazil will provide community organizations with technical assistance and financial resources to engage agroecological and soil conservation experts to guide and train them in identifying and adapting recommended techniques, practices and systems to their specific conditions. Communities will learn to document the innovations they produce and test them in the field. Information and knowledge generated by these experiences will be systematized and codified for subsequent dissemination to CSO networks throughout the two biomes.

Achievement of Outcome 3.1 will be defined by the following indicators:

· 200 hectares in the Caatinga and 400 hectares in the Cerrado under sustainable land management using a suite of agroecological and soil conservation techniques and practices

Outputs envisaged to achieve this outcome include:

3.1.1 – Agroecological management techniques replicated

Under this output, GEF-SGP will support initiatives that support the field replication and adaptation of appropriate practices and innovations; undertake peer to peer exchanges and training of smallholder organizations; inventory, compile and disseminate best agroecological management practices; and participate in policy dialogues regarding land degradation and agroecological systems. This output will benefit 1,200 families on 600 hectares of land in the Caatinga (200) and Cerrado (400) biomes. Key partners will be specialized NGOs with agroecological skills and abilities, as well as government extension agencies.

This output is closely related to output 2.2.2 - Sustainable agriculture program implemented. 

3.1.2 - Soil erosion control implemented with native and adapted species 

The projects and actions in this output, which is closely related with output 3.2.1 below, will focus on restoring degraded lands and providing ecosystem services in the two biomes as well as on preventing land degradation by supporting the adoption of technologies that increase rainfall water infiltration and reduce runoff and soil erosion. One such technology, increasing ground cover resulting from intercropping of wild and adapted species, generates multiple environmental benefits, such as carbon capture, soil conservation, habitat for wildlife, moisture retention and improved microclimates., will also help the maintenance of local communities in rural areas. The projects in this output will contribute to overcoming major barriers such as the low access to technical solutions among smallholders and extension workers as well as sources of funding and other incentives in public polices to help communities cope with the effects of land degradation and vulnerabilities associated with soil erosion.  This output will consist of approximately 40 initiatives.  Key partners for this initiative will be specialized NGOs and government extension agencies.

Outcome 3.2 - Adoption of innovative water management techniques at community level, benefiting 2,000 ha with improved ecosystem services

The outcome will focus on supporting projects that promote water management in order to maintain environmental services and improve livelihoods. GEF-SGP will support projects that implement rainwater harvesting techniques, such as the construction of above and below ground reservoirs. This technology promotes water infiltration improving seasonal stability of streams, creeks, and springs, thus improving community access to water particularly in the Caatinga and drier regions of the Cerrado. 

Baseline:

Currently, the government provides little effective technical assistance regarding water management at the community or local landscape level.  Accepted practices, technologies, techniques, methods – all must be locally adapted to the micro-conditions prevailing at the community or landscape levels. Financial resources are generally unavailable to cover the costs of even the most straightforward of technologies, and the knowledge and capacities of how to construct simple water storage devices are weak. 

Over the past 16 years, GEF-SGP has successfully promoted the development and adaptation of  water management and harvesting programs at the community level in different areas and with different communities of the Cerrado. As a result, it has gained extensive experience and knowledge of what works, why and how.    

Alternative:

The projects supported under this outcome will implement rainwater harvesting and infiltration strategies designed to reduce runoff and silting of water courses, improving the seasonal stability of rivers, thus increasing access to water and small-scale irrigation among smallholders. Water harvesting techniques tested and applied in GEF-SGP Brazil projects have proven to be successful in reviving springs and streams that had stopped flowing previously because of land degradation, compacted soils or overgrazing, among other factors. Such innovative techniques will be tested and applied extensively in communities that are vulnerable to water shortages. 

The strategy is to replicate the most widely used technologies such as:

· Reservoirs (Barraginhas): small reservoirs designed in a sequence along catchments to capture and store runoff thereby increasing groundwater recharge.

· Barraginhas subterrâneas (Underground reservoirs): to increase groundwater recharge, trenches about 100m long are dug perpendicularly to water courses and the hydraulic flow of drainage basins.  Usually, a tarp is used to line the walls of the trench and then buried so as to dam the water and increase infiltration, although stones, clay and bricks can also be used in this low-cost technique. 

· Barraginhas-calçadão (paved catchments) – a paved catchment of approximately 50m² is build to collect rainwater and store it in a large tank or cistern. 

· Cisterns – reservoirs built to store rainfwater harvested off the roof of the family home using gutters, which usually store around 16,000 liters per home. The water harvested during the rainy season can be used for drinking, cooking and other domestic purposes throughout the dry season. 

Achievement of this Outcome will be defined by the following indicators:

· No fewer than 1,200 families benefit from application of water management techniques;
· Water management and conservation techniques are applied permanently to no fewer than 2000 hectares of Caatinga and Cerrado biomes

The Output envisaged to achieve this outcome is:

3.2.1 - Water management and conservation, including rainwater harvesting.

At least 1,200 families and 2000 hectares, especially from the Caatinga biome and transition zones between the Cerrado and Caatinga, will benefit from the projects under this output.  Community groups will be supported to implement water management and harvesting techniques; peer-to-peer exchanges will be arranged to provide proponent communities with direct knowledge and information from the experience of other communities with successful water harvesting practices. Local adaptation of these best practices will be pursued and successful innovations will be recorded for later dissemination through subregional CSO networks.

Component 4: Capacity development and knowledge management to help deliver global environmental benefits. 
Grantees are generally unaware of or often fail to understand global environmental issues, and have difficulty in managing their projects and assessing lessons learned. In GEF 5, there will be a number of capacity-building workshops on project design, implementation and management, accounting, indicators, budget, and participatory monitoring and evaluation methodologies. Communities will have the opportunity to learn about relevant public policies, better understand environmental problems and discuss the different means to address these. In addition to the workshops, important lessons learned by communities and CBOs regarding biodiversity conservation, climate change mitigation, and sustainable land and forest management will be systematized through publications and widely disseminated to stimulate replication of innovative ideas and promote up-scaling. The most relevant documents will be translated into English to enable other GEF-SGP Country Programmes as well as other practitioners to benefit from GEF-SGP Brazil experiences. Two thematic reports will be produced annually and made available in electronic or print version to government agencies and practitioners at the local, regional and international level. These reports will pay particular attention to issues that require policy decisions. UNDP and the NSC can then help mainstream these issues in national policy dialogue and processes.

Baseline: 

GEF-SGP Brazil’s support to community initiatives over the last 16 years has helped to strengthen the capacities of a large number of CBOs and NGOs in the Cerrado biome. This increased capacity is one of the singular achievements of the GEF-SGP programme, as has been reflected in evaluations, case studies and programme reviews. However, efforts to systematically generate and capture knowledge from the experiences of community initiatives and their innovations have been limited. The design, implementation, monitoring and evaluation methodologies of community initiatives are weakly oriented towards knowledge generation and the identification of good practice. At the same time, the dissemination of knowledge and lessons learned is insufficiently systematic nor strategically targeted to contribute as fully as it could to leveraging a tipping point in resource management among communities. 

In the same vein, the portfolio-wide aggregate impacts of the community initiatives supported by GEF-SGP Brazil to strengthen sustainable land and resource management, conserve biodiversity and sequester carbon above and below ground have also not been adequately systematized and codified. While significant evidence exists of success in using biodiversity sustainably, conserving biodiversity, promoting sustainable use and building and strengthening community capacities, this evidence has not been systematically compiled, analyzed and reported, nor distributed as such to communities, donors, government agencies or other stakeholders.

Alternative:

In order to build capacity to help communities manage their projects and better understand global environmental issues, workshops will be held for GEF-SGP grantees aiming to benefit approximately 150 community leaders. There is a strong need for communities to improve their skills in project management to enable them to raise funding from other international sources and from the Brazilian Government and execute their own projects. GEF-SGP Brazil, based on 16 years of experience, will conduct workshops for grantees selected in each call for proposals using accessible methodologies and an approach that promotes intense exchange among grantees and personalized attention to each project in terms of contributing to the improvement of work plan and budget.
There is a great array of information and lessons learned derived from projects supported by GEF-SGP that is important to systematize and disseminate. Aiming to promote the best strategy to disseminate this information, focusing both on influencing policies and making information available to local communities, a knowledge management strategy will be developed at the beginning of project execution. This Outcome will produce publications in accessible language to inform local communities of relevant issues related to biodiversity conservation, climate change mitigation, and sustainable land and forest management. 

There is large store of information and lessons learned derived from GEF-SGP supported projects that can be systematized and disseminated, aiming to influence government policies as well as development practitioners at all levels. This Outcome will promote the systematization of relevant information that can be used by communities, but also publicized on other levels with the aim of influencing policy analysis and debate. 

Activities under this component are designed to support achievement of three Outcomes:

· Community leaders proficient in project design and management and aware of global environmental issues 

· Knowledge produced by the projects codified and available to enable replication and up-scaling of successful interventions 

· Information from projects available to other communities, government institutions and development practitioners at the local, national and international levels as feedback to policy implementation
Achievement of these Outcomes will be defined by the following indicators:

· More than 150 community leaders trained in project design, implementation and monitoring and evaluation methodologies. 

· Three publications on lessons from community based initiatives on biodiversity conservation, sustainable land and forest management and restoration of degraded lands.

· Two thematic reports yearly highlighting best practices resulting from GEF-SGP supported initiatives.

· At least 4000 community-level resource users and managers receive GEF-SGP knowledge products as part of community CSO networks.  

· Replication of successful conservation and sustainable use approaches in at least 30 new grants by year 4
Outputs envisaged under the three Outcomes in this component include:
· Output 4.1.1 Training program on global environmental issues, project design, implementation, monitoring and evaluation delivered

· Output 4.2.1- Knowledge management strategy formulated and implemented with at least 3 knowledge products 

· Output 4.2.2 - Publications on lessons learnt on biodiversity conservation,  climate change mitigation, and sustainable land and forest management prepared and disseminated
· Output 4.3.1- Production and dissemination of at least 2 yearly thematic reports
Component 5: Monitoring and evaluation. 
The country portfolio will continue to be closely monitored through visits, reports and frequent contacts by telephone and email. The field visit is an essential monitoring instrument to understand local reality, to inform people that are not involved in project management, to check project execution, and to build relationships with the communities. There will be a mid-term review and an independent final evaluation. The mid-term review will be run as a participatory adaptive management tool, aiming to improve project execution, at the grant and country portfolio levels. Achievement of outputs and progress towards outcomes will be assessed. The GEF-SGP will apply the Global GEF-SGP Tracking Tool that is being developed. It will also be subject to the yearly UNDP GEF Project Implementation Review process. Activities related to Monitoring and Evaluation and their costs have been described in Part I. 

Sustainability of outcomes and of capacity developed. Achieving sustainability of project outcomes is central to GEF-SGP. Project proponents are required to build measures into their project design that increase the likelihood of outcome sustainability. The screening of project proposals by the National Steering Committee includes a systematic assessment of whether such measures are sound and based on realistic assumptions. Project logical frameworks include outcome indicators that are monitored periodically. Project monitoring activities are designed to verify that initial assumptions hold, and that the required elements for outcome sustainability are in place. Most grants include a capacity development component and a sustainable livelihoods component to ensure that achievements will be sustained at the smallholder and resource-user level. Proactive adaptive management is applied throughout the life of the projects by the National Coordinator who works with GEF-SGP grantees to take corrective action whenever there are indications that project outcomes may be compromised or may not be sustained after the project ends. GEF-SGP does not generally support the creation of new organizations but rather strengthens existing CBOs and NGOs. Although most communities continue applying acquired skills in their day-to-day work GEF-SGP ensures retention of new skills through various means: inviting leaders or members of former grantee organizations to new training; using former GEF-SGP grantees as trainers for other communities and projects; continuing as much as possible monitoring former grantees and trouble-shooting when required; and establishing mentoring and peer-to-peer support among communities so that they can practice their skills and gain self-confidence.
The GEF-SGP provides support to local communities to achieve global environmental benefits at the local level. The current baseline scenario in the Cerrado and Caatinga biomes, where significant carbon stocks are being lost at a fast pace, consists of communities degrading and abandoning or selling their small farms, which in turn gives way to large scale agriculture, eucalyptus monocrops and extensive ranches; this scenario would most likely remain the status quo without GEF-SGP support. Such conditions, if not addressed, will continue to contribute to loss of ecosystem services and increasing rural poverty levels.

Brazil´s efforts to address global environmental challenges in an innovative and community-driven manner are underfunded by orders of magnitude in relation to the potential need. Many of the communities supported by GEF-SGP are located in remote or marginalized areas not targeted by large-scale national development efforts. It is no exaggeration to say that Brazilian government programs cannot deliver the type of support GEF-SGP provides because compliance with their rules and requirements is almost impossible for poor communities. GEF-SGP can reach isolated communities in the Cerrado and Caatinga regions that have no experience in managing projects and are neglected by the majority of development efforts.

GEF-SGP Brazil, with its integrated and bottom-up approach to address global environmental issues, fills a critical niche in environmental efforts in Brazil. For example, communities that are becoming isolated in the middle of thousands of hectares of eucalyptus plantations in Minas Gerais state, or indigenous people´s lands that are being threatened by soybean expansion count on GEF-SGP to support their struggle against these problems. GEF small grants and capacity development work enable communities to access and manage larger funds once they have completed their initial project. Other donors and the Brazilian Government may offer larger amounts of money, but their access entails extremely complex procedures beyond the reach of small rural communities.

B.3. Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF). As a background information, read Mainstreaming Gender at the GEF.":  

The premise of the project is that sustainable livelihoods derived from intact ecosystems provide the incentives that lead to decreased deforestation and habitat fragmentation and to the long-term sustainability of conservation-compatible, climate resilient and productive community landscapes. Through this project GEF-SGP will allocate some 150 grants to support an equal number of communities (while the maximum grant amount is $50,000, the average grant size in Brazil is $28,000). These grants may benefit more than 7,000 men, women and children in some of the poorest rural communities of Brazil. Small grant projects will achieve global environmental benefits by also supporting activities that improve the communities’ quality of life (e.g., affecting food security, water quantity and quality), generate income, and enable them to stay on their land. Individual and organizational capacities will be strengthened through training, learning-by-doing, and peer-to-peer learning, producing social capital that will benefit community initiatives in other spheres (e.g. health, education). Women will be particularly favored by this project and will be explicitly targeted for support given their role in agriculture and the harvest of non-timber forest products. GEF-SGP will monitor gender indicators and will ensure equity in women’s participation in the projects and benefit sharing.
B.4 Indicate risks, including climate change risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks to be further developed during the project design: 
47. The following are the major risks identified:

	RISK
	RISK RATING
	MITIGATION MEASURES

	Under performance risks due to project management capacity limitations of CBOs


	Low 
	GEF-SGP Brazil will help develop CBO capacity through workshops that will bring together representatives of all approved projects to discuss project management including: responsibilities, work plan and budget revision, financial and activity reports, participatory monitoring, indicators, etc. Also the workshops will enable exchange among grantees for peer-to-peer learning processes. The NHI constant and close monitoring of the projects is also an effective strategy to mitigate execution risks. 

	Geographical expansion to the Caatinga biome may pose logistical and capacity challenges to the GEF-SGP team 
	Low
	To minimize this risk, ISPN has already made contact with important stakeholders and networks in the Caatinga to support GEF-SGP’s work and help mobilize co-financing. ISPN has already invited a representative from Semi-Arid Articulation (a well-known local NGO) to participate in the NSC, as well as other specialists who will join the NSC at the beginning of the project. For the first call for proposals in 2011, an ISPN communication assistant will work for a six-month period disseminating information about the GEF-SGP programme and announcing the call for proposals in the Caatinga.

	Access to markets for sustainably produced goods and services
	Medium
	As mentioned in Section B, there are significant challenges involved in marketing and obtaining a fair price for sustainably produced goods and services.

	Difficulty in assessing and monitoring carbon stocks
	Medium
	GEF-SGP is assessing the possibility of partnering with the GEF Carbon Benefits Project to use the tools and methods being developed for measuring and monitoring carbon. At the beginning of the project, a consultant will assist in establishing baseline information for the two ecosystems and will advise the country team in the monitoring method. It will use official data and consider the specificities of different kinds of projects in the Cerrado and Caatinga biomes.

Project beneficiaries will be trained on the application of the method to enable them to collect the information. During the project’s monitoring, the ISPN team will assess the quality of information provided by the beneficiaries.

	Communities´ resistance to change current agricultural or natural resource use practices
	Medium
	Resistance to change is a common human trait. GEF-SGP will address this issue by inviting previous grantees to share their experience and to demonstrate the environmental and socio-economic benefits achieved. It will also work with young leaders within the communities who are often more open to engage in new activities and to take moderate risks.


      B.5. Identify key stakeholders involved in the project including the private sector, civil society organizations, local and indigenous communities, and their respective roles, as applicable:  
48. Key stakeholders are the communities who will design and implement small grants projects. GEF-SGP partners are associations, cooperatives and NGOs that represent or assist local communities from the Cerrado and Caatinga biomes. The Cerrado Network (Rede Cerrado) and the Semi-Arid Articulation (ASA) organization are special stakeholders because they congregate hundreds of CBOs and NGOs present in these biomes. They will be represented in the NSC and will contribute to disseminate information about GEF-SGP. Other important stakeholders are the Cerrado Central and the Budega da Caatinga, which are networks that congregate about 30 initiatives each, working with marketing of Cerrado and Caatinga products. Cerrado Central was created as a result of the GEF-SGP Brazil work, and was formalized as a cooperative in 2010, being able to access formal markets and new possibilities of financial support. The Budega da Caatinga is one of the main results of the Caatinga GEF FSP, which had actions in several regions involving more than 30 community groups. The Budega is helping these groups to improve their marketing capacity. It will have a special role in publicizing locally GEF-SGP calls for proposals and assisting the communities to prepare their project proposals, considering that GEF-SGP will be intervening in the Caatinga for the first time.

 ISPN has a close relationship with the University of Brasília, which is especially important for GEF-SGP’s knowledge management activities and products. Through the Florelos Project, supported by the European Commission, ISPN grants scholarships to students that are focusing their research on local communities and Cerrado conservation. Partnerships with the private sector are being explored, especially in cosmetics. Cooperation with local and national government institutions is fundamental to turn pilot experiences into public policies.

B.6. Explain how cost-effectiveness is reflected in the project design:  
Given the advanced alteration and fragmentation of the Cerrado and Caatinga biomes and the loss of carbon stocks due to land use change, working with communities to avoid their outmigration and continued deterioration of ecosystem services is a very cost effective approach. Addressing biodiversity, climate change mitigation and sustainable land management in a geographically focused manner is cost-effective because it creates opportunities for synergies among various grants, optimizing resources for capacity development, and monitoring and evaluation. It also creates ideal conditions for replication, upscaling and mainstreaming. Cost-effectiveness is a necessary ingredient for the success and sustainability of community livelihood activities because market conditions will prevail over time and continued subsidies to communities will not be possible or advisable. The project builds on existing institutional structures and prior GEF-SGP work, which contributes to cost effectiveness. The NSC will assess cost-effectiveness of individual grant proposal against possible alternatives to obtain the same outcomes.
B.7. Outline the coordination with other related initiatives: 
Over the years, GEF-SGP Brazil has maintained close dialog with the World Bank and the various stakeholders of the Pilot Program to Conserve the Brazilian Rainforest. Building on this experience, mainly in the Amazon, the many lessons learned can now be applied to initiatives in other biomes. GEF-SGP has followed the implementation of the Amazon Region Protected Areas project (ARPA), a large GEF FSP, to learn about ways to demarcate areas for sustainable use, in addition to strict conservation. GEF-SGP Brazil contributed to and participated in the preparation of the Sustainable Cerrado Plan, which was the basis for the World Bank FSP called Sustainable Cerrado Initiative, for US$13 million, signed with the Ministry of Environment, two state governments, FUNBIO and the Chico Mendes Institute (ICMBio) in 2010. Because of the different geographical foci and since there is no small grants component in the WB FSP, there will be no duplication. When possible, cooperation will be sought with WB project activities in the states of Goiás and Tocantins, the only two states directly involved in the project. GEF-SGP can contribute to the implementation of the subcomponents on strengthening civil society organization and on traditional knowledge.

The GEF-SGP National Coordinator participated in two events of the UNEP sponsored The Economics of Ecosystems and Biodiversity (TEEB) project, including meetings with its coordinator, and will continue in the Brazilian version. He participates in the Brazilian Panel on Climate Change supported by UNEP. For the future, discussions are under way with UNEP on how to incorporate work on chemicals.

As shown above, GEF-SGP Brazil works with many institutions and programs in the geographic and focal areas relevant to the GEF-SGP to ensure coordination and avoid duplication with other government or donor funded initiatives. GEF-SGP also builds on or seeks linkages with other relevant GEF MSPs and FSPs implemented in the same geographic areas. During GEF-5, GEF-SGP will explore the feasibility of implementing demonstration actions to support the implementation of the Sao Francisco Strategic Action Program, financed by GEF. GEF-SGP has collaborated with the UNDP GEF MSP on private nature reserves (RPPN) in the Cerrado, carried out by FUNATURA. There has been and there will be further exchange with the UNDP FSP in Northwestern Mato Grosso. 

Below are some relevant initiatives/programs some of which quite recent, with which GEF-SGP will collaborate.

	Initiative/Institutions
	Relationship/linkage with GEF-SGP Brazil

	National Cerrado Commission (CONACER)
	GEF-SGP Brazil will keep the government and non-governmental members of the Commission informed of its activities in the Cerrado, with a view to mainstream its experiences in the work of the Commission.

	Brazilian REDD + Strategy
	Participation in the consultations during the formulation of the REDD + Strategy and contribution to its implementation.

	European Commission project on Ecological and Social Links in Brazilian Forests through Sustainable Livelihoods in Production Landscapes (FLORELOS)
	Collaboration on knowledge management concerning sustainable livelihoods in various biomes, with broad visibility in government, civil society and the public.

	Sustainable Cerrado Initiative (GEF FSP)
	Contributions to strengthening civil society organizations and traditional knowledge.

	Environmental Caucus of the National Congress (FPA)
	Participation in debates and initiatives regarding national legislation with a viewpoint based on GEF-SGP experience.

	Brazilian Panel on Climate Change (PBMC)
	Contributions to the Brazilian equivalent of IPCC and authorship of parts of national report regarding mitigation, introducing perspectives of communities from the Cerrado and Caatinga.

	Amazon Fund
	Consultation on mechanisms for support from donor countries to local initiatives in other biomes in which emissions are increasingly significant.


	C. GEF Agency information:
C.1   Confirm the co-financing amount the GEF agency brings to the project:
UNDP is commited to mobilize at least US$ 1,000,000 in cash cofinancing for the project, and will contribute US$ 100,000 to the project in in-kind cofinancing consisting of staff time, both professional and general service, to assist the GEF-SGP project on programmatic and administrative matters. The professional staff time includes UNDP’s representation in the GEF-SGP National Steering Committee during the 4-year period as well as technical assistance by a socioeconomic expert for the establishment of community-based enterprises, development of business plans and marketing of community produced goods; an environmental specialist with experience in PA and natural resource management; an energy specialist; and a risk management expert. 
C.2  How does the project fit into the GEF agency’s program (reflected in documents such as UNDAF, CAS, etc.)  and staff capacity in the country to follow up project implementation:  
The current UN Development Assistance Framework (UNDAF) for Brazil covers the period 2007-2011. The priorities in the UNDAF and its five expected results were derived from the findings of the Common Country Assessment (CCA) of 2005. The GEF-SGP Brazil project has been designed to contribute to the Fifth UNDAF Result “Efficient use of natural resources to ensure equitable and environmentally sustainable economic development”. By targeting women’s groups as well as traditional and indigenous communities, GEF-SGP Brazil also contributes to the second UNDAF expected result “Gender, racial and ethnic inequalities reduced, taking into consideration the impact of territorial differences”. The main target beneficiaries of the GEF-SGP are indigenous communities, small farmers, and other traditional populations such as afro-descendants, wild species collectors, artisans, rubber tappers, and Brazil nut and babaçu collectors that depend on ecosystem services for maintaining their livelihoods. GEF-SGP Brazil’s strategy is also aligned with goal seven of the Millennium Development Goals on environmental sustainability, a UNDP priority in Brazil.



part iii:  institutional coordination and support
A. institutional arrangement:  
B. project implementation arrangement:  

The project will be executed under the NGO (Non-Governmental Organization) modality by Instituto Sociedade População e Natureza (ISPN). The Project is co-financed with primary funding from the GEF, and UNDP acts as the GEF Implementing Agency. ISPN, which has been the National Host Institution for GEF-SGP in Brazil before its upgrading, will be the executing agency, taking over the previous execution role played by UNOPS, and will be responsible for the day-to-day management and implementation of project activities with the support of a full time Country Programme Manager (CPM) and under the leadership of the National Steering Committee (NSC). The project will be implemented with UNDP support, and UNDP will ensure that the project receives technical and managerial support, as needed, from the UNDP Country Office, and from the regional team, as well as the global team responsible for project oversight for all GEF-SGP upgraded Country Programme projects.

National Steering Committee (NSC): the NSC will act as the Project Board, responsible for taking appropriate management decisions to ensure that the project is implemented in line with the GEF-SGP Operational Guidelines and the agreed project design and is consistent with national and state development policies and priorities. The NSC will meet at least twice a year, and for special meetings as needed, to provide the required oversight of the project and also ensure the overall coordination of the programme. The membership of the National Steering Committee, which shall be non-governmental in majority in keeping with the GEF-SGP Operational Guidelines, will be constituted by UNDP in consultation with the Executing agency, and others, as appropriate, with process validation to be done by the UNDP-GEF assigned manager for upgraded GEF-SGP Country Programmes. The NSC includes the UNDP, the Brazilian Cooperation Agency (ABC), the Ministry of Agrarian Development (MDA), the Ministry of Environment (MMA), the Cerrado Network, the Semi-Arid Articulation (ASA), the Amazon Work Group (GTA), the Brazilian Forum of NGOs and Social Movements for the Environment and the Development (FBOMS) as well as a specialist in environment issues and a specialist in social issues. The Chairperson can also invite specific technical experts or others to the NSC meetings on an ‘as-needed’ basis. The CPM shall act as the Secretary to the NSC. The NSC shall determine the strategic criteria for project eligibility within the overall framework provided by the GEF-SGP Operational Guidelines and the Project Document, shall decide which grants to approve after receiving the reviews of all projects by the Technical Advisory Group. At the project level,, it shall play a crucial role in quality assurance and accountability by ensuring adequate project monitoring and evaluation and approval of the Annual Work Plan (AWP). The NSC ensures that required resources are committed and arbitrates any conflicts related to the project or negotiates a solution to any problems with external entities. Representatives from the agencies providing co-financing to the project may also be invited to participate in the NSC meetings as appropriate.

In addition to approval of GEF-SGP grants, the NSC’s activities will include strategic efforts in line with the Project and GEF strategic priorities that will enable aggregation of community-driven impacts for global environmental benefits, local-to-global strategic portfolio learning and capacity development, dissemination of best practices, and network building for GEF-SGP portfolio grantees. This approach will support the GEF-SGP’s and GEF’s catalytic roles by contributing to replication and up scaling of good practices.  

Country Programme Management Unit (CPMU): The CPMU will be the administrative hub for the project and will be the responsibility of ISPN as the executing agency for the Small Grants Program. The CPMU will serve as the Secretariat to the NSC and will be responsible for the day-to-day implementation of project activities. The CPMU will be responsible for the overall coordination of the project, including operational planning, supervision, administrative and financial management and the adaptive management of the project based on inputs from the Project Monitoring and Evaluation plan. The CPMU will be responsible for (1) managing and executing project components; (2) coordinating financial resource management and acquisitions; (3) reporting on the use of GEF resources and on results achieved; (4) preparing management reports for the NSC, and UNDP; (5) promoting institutional coordination among all involved stakeholders from government and non-governmental organizations participating in the project; and (6) monitoring, evaluating and disseminating project results.

The CPMU will constitute a full time Country Programme Manager (CPM), a Project Assistant and relevant support and technical staff. The team will work under the guidance of ISPN as executing agency, will be supported by the  UNDP Country Office on all matters related to project implementation and will coordinate with all grantees. 

Project Assurance and other functions: UNDP will perform the Project Assurance function by providing independent feedback (through periodic monitoring, assessment and evaluation) on progress towards project milestones and how they are managed and completed. UNDP will provide assistance in Country Program execution services and maintain project budget and project expenditures, assist in recruitments and contracting project personnel and provide technical consultant services, assist in equipment procurement, and provide any other assistance upon request of the CPM, based on the AWP approved by the NSC. The Combined Delivery report (CDR) prepared by UNDP will be verified and certified by ISPN. The executing agency will ensure, and UNDP Country Office will also monitor, project implementation and achievement of the project outputs, guaranteeing the proper use of GEF/UNDP funds. Financial transactions, reporting and auditing will be carried out in compliance with UNDP rules and procedures. UNDP will assign a Programme Officer, who will be responsible for the project assurance function.

Technical support to the project:  The project will solicit the support of experts and specialists in different thematic areas to extend technical support to project partners and grantees, as needed. A roster of experts will be created at the national levels who will be engaged on a periodic basis for special capacity needs of the partner agencies and grantees. 
Audit Arrangements: The audit will be conducted, in accordance with the established UNDP procedures set out in the programming and finance manuals, by a legally recognized auditor. 

Use of Institutional Logos on Project Deliverables: Visibility of GEF financial support will be ensured through application of the global GEF GEF-SGP branding to all relevant electronic and printed materials, both by the GEF-SGP country program and by GEF-SGP grantees. GEF-SGP will also apply the following UNDP-GEF policy: “The GEF logo should appear on all relevant project publications, including amongst others, project hardware and other purchases with GEF funds. Any citation in publications regarding projects funded by GEF should also acknowledge the GEF. Logos of the Implementing Agencies and the Executing Agencies will also appear on all publications. Where other agencies and project partners have provided support (through co-financing) their logos may also appear on project publications”.
Part IV: Explain the alignment of project design with the original PIF
The CEO endorsement document is fully aligned with the original PIF with the exception of the project’s implementation arrangements; in the PIF the UN Office for Project Services was named as project executing agency, in this document the Instituto Sociedade População e Natureza (ISPN) is the designated executing agency, given its more than 15 years of experience as the SGP National Host Institution.

PART V: Approval/endorsement by gef operational focal point(s) and gef agency(ies)
A. Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): ): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

	Name
	Position
	Ministry
	Date (MM/dd/yyyy)

	Mrs. Claudia Veiga da Silva
	GEF OPerational Focal Point
	Ministry of Planning, Budget and Management
	06/06/2011

	     
	     
	     
	     

	     
	     
	     
	     


B.  GEF agency(ies) certification

	This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for CEO endorsement/approval of project.


	Agency Coordinator, Agency Name
	Signature
	Date 
(Month, day, year)
	Project Contact Person
	Telephone
	Email Address

	Yannick Glemarec

UNDP GEF Executive Coordinator
	[image: image1.jpg]



	09/17/2012
	Nick Remple
	212-906-5842
	nick.remple@undp.org

	     
	
	     
	     
	     
	     


ANNEX A:  PROJECT RESULTS FRAMEWORK
	
	Indicator
	Baseline
	Targets 

End of Project
	Source of verification
	Risks and assumptions 
	COMMENTS

	Objective: Conservation of the Cerrado and Caatinga biomes of Brazil through community initiatives on sustainable resource use, and actions that maintain or enhance carbon stocks and increase areas under sustainable land management


	Increased area in production landscapes meeting sustainability standards

with enhanced biodiversity conservation
	200,000 hectares managed sustainably as a result of SGP support in OP4


	Additional 300,000 ha sustainably managed in the Cerrado ecosystem 

100,000 ha in the Caatinga ecosystem

Sustainability criteria and standards developed and adapted to social and environmental conditions of Cerrado and Caatinga 

 
	Final reports and independent evaluations


	Market forces will be favorable for conservation and sustainable land-use practices 
Public rural development policies will be conducive to conservation-oriented and sustainable natural resource use initiatives

Community-based organizations and partner institutions will have sufficient capacity to comply with and implement sustainability criteria and standards 
SGP Brazil and/or partners will have sufficient financial and human resources to carry out certification on the ground 
	

	
	Carbon stocks maintained or increased through maintenance and expansion of habitats 
	Deforestation rate in the  Caatinga biome is 276,300 ha/p.a and 1,418,000 ha/p.a in the Cerrado 
	500 hectares of Caatinga ecosystem restored, equivalent to 18,200 tCO2e sequestered

500 hectares of Cerrado ecosystem restored, equivalent to 37,400 tCO2e sequestered during life of project

80,000 hectares with avoided conversion to pasture or monoculture and environmental services maintained, equivalent to 4,370,400 tCO2e of emissions avoided during the life of the project 
	Independent monitoring reports on sample of projects 


	Community-based organizations and partners institutions will have sufficient capacity to comply with and implement carbon monitoring and measuring procedures

Communities are open to adopting habitat restoration practices

Technical assistance will be available at the local level through NGOs or government agencies

Market conditions (commodity prices, etc.) do not increase pressures on habitat conversion far beyond current levels 
	

	
	Increased area of sustainable land management techniques that sustain the flow of environmental services in agro-ecosystems by communities supported by SGP 
	2200 ha (as a result of SGP support in OP 4)
	An additional 200 hectares in Caatinga and 400 hectares in the Cerrado in which communities apply innovative soil management techniques

2,000 hectares with improved ecosystem services as a result of community adoption of innovative water management techniques
	Final reports and independent evaluations


	Communities are open to adopting sustainable land and water management practices

Technical assistance will be available at the local level through NGOs or government agencies 


	

	Sustainable use and management of natural resources by communities to enhance conservation of biodiversity in the production landscape
	Number of sustainable land use plans or resource use plans developed, as well as plans for conservation of endangered species
	There are no existing plans in targeted communities 


	15  plans developed by stakeholders
	Land use and species conservation plans and project reports
	Communities are open to adopting sustainable resource use and biodiversity management practices

Technical assistance available at the local level through NGOs or government agencies 

Communities have market access for selling their goods 


	

	
	Number of native plant and animal species considered endangered or important for sustainable livelihoods conserved in-situ and sustainably used
	29 endangered plant species, 6 endangered and 16 vulnerable animal species in project areas supported previously by SGP in Cerrado and 0 plant and animal species in Caatinga 
	50 plant species and 25 animal species, including Cerrado and Caatinga 
	Projects submissions, monitoring and final reports, final independent evaluation
	
	Please include a list of species in an Annex

	
	Number of families participating in Caatinga and Cerrado bio-products marketing networks 

	6,000 families currently participate
	8,000 additional families participate
	Project submissions, monitoring and final reports, final independent evaluation
	
	

	
	Number of hectares with forest cover under regeneration in community lands 

	612 hectares currently under regeneration 


	1000 additional hectares under natural regeneration practices


	Projects submissions, monitoring and final reports, final independent evaluation
	
	

	Carbon stocks maintained through avoiding land use change and improved agriculture and forest management at the community level
	Number of hectares under sustainable forest management in community lands 
	36,190 ha under sustainable forest management (in projects supported in OP4)
	40,000 additional hectares under sustainable forest management


	Project submissions, monitoring and final reports, final independent evaluation
	Tools for monitoring carbon stocks will be applicable at the community level 

Communities are open to adopting sustainable land use practices

Technical assistance will be available at the local level through NGOs or government agencies 
	

	
	Area under ecological agriculture management
	250 hectares (est.)

	15,000 hectares under ecological agriculture management
	Project submissions, monitoring and final reports, final independent evaluation
	Communities are open to adopting sustainable land and water management practices

Technical assistance will be available at the local level through NGOs or government agencies 

Sustainable management techniques are tailored to the livelihoods needs and contexts of communities 
	

	
	Area on which smallholders apply fire control techniques or avoid use of fire 
	Smallholders do not currently apply fire control techniques or avoid the use of fire 
	Smallholders apply fire control techniques or avoid the use of fire on at least 25,000 hectares 
	Projects submissions, monitoring and final reports, final independent evaluation
	
	

	
	Number of families adopting sustainable water management techniques and sustainable land management techniques 
	517 families have adopted sustainable water management techniques and SLM techniques as a result of SGP support in OP4.
	1200 additional families  have adopted sustainable water management techniques and SLM techniques
	Project submissions, monitoring and final reports, final independent evaluation
	
	

	Sustainable land management techniques preventing land degradation, restoring agro-ecosystem services, and improving livelihoods of local communities implemented
	Area with erosion in grantee farmlands
	2400 ha of grantee farmland undergoing erosion, to be confirmed through project submissions
	Reduction of  erosion in 1200 ha as a result of SGP interventions 
	Projects submissions, monitoring and final reports, final independent evaluation
	Communities are open to adopting sustainable land and water management practices

Technical assistance will be available at the local level through NGOs or government agencies 

Sustainable management techniques are tailored to the livelihoods needs and contexts of communities 
	

	
	Area under sustainable water  and soil management 
	1,200 ha in Cerrado 
	2000 ha (including Caatinga and Cerrado) 
	Projects submissions, monitoring and final reports, final independent evaluation
	
	

	Communities deliver global environmental benefits through capacity development and knowledge management
	Percentage of project reports that receive a “very good” score, according to SGP Brazil project assessment method 
	51% very good 
	70% of project reports  “very good”
	Project monitoring reports 
	Grantee project teams have or acquire sufficient capacity to manage projects

Project teams establish strategic partnerships at the local level that enable effective project implementation and knowledge management 

SGP Brazil staff will continue to have an influence on key policymaking processes
	

	
	Number of community leaders aware of global environmental issues 
	30 community leaders
	150 additional community leaders
	Training activity reports
	
	

	
	Number of policy inputs or recommendations provided to policymakers based on lessons learned
	10 inputs or recommendations as a result of SGP support in OP4 
	10 additional inputs or recommendations 
	Documents, reports, emails, personal communications 
	
	


ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

Comments from France

	Suggestions for improvements to be made during the drafting of the final project proposal:
	UNDP Responses to comments

	We regret that the PIF lack of an assessment of previous SGP supports, successes and failures and the current capacity building status and needs of the Brazilian grant beneficiaries. There is some general and very broad information on the Brazilian SGP program activities p12, but little if no detailed outcomes statistics and numbers on the results: how much sustainable activities generated? Sustainable income generated? How much SGP grantees have sufficient capacities, are now leveraging funds on their own and are no more SGP “clients” compared to how much grantee have benefited from 2, or 3 or event 4 successive SGP grants? Etc.

Globally the Brazilian 5th Operational Phase of the GEF Small Grants Program is well informed and seems based on sound experiences. 

Some of the questions raised for the global project 4541 apply to the Brazilian SGP program:

- The description of the socioeconomic benefits to be delivered by the Project is not convincing (p16). It states that: “Small grant projects will support activities that improve the communities’ quality of life (e.g., food security, improved water quantity and quality), generate income, and enable them to stay on their land while also achieving global environmental benefits” but doesn’t explicitly demonstrate if those activities are profitable and can last beyond SGP support or if those activities can only be maintained with grants from the SGP (and need to be subsidized to be sustainable over the long term). The Brazilian SGP (using its previous experience in country) should provide precise information on the amount and sustainable amount of income generating activities which can be developed with the SGP, and clearly state if those activity are not profitable and need subsidize over the long term by SGP, or if they are profitable and self sustainable. In this regard, the chapter in p11 and 12 about “Barriers to communities’ contribution to biodiversity conservation, sustainable land management and maintenance of carbon stocks in the Cerrado and Caatinga biomes” let think that most of the incomes generating activities supported by SGP are probably not sustainable without permanent subsidizing from SGP. Some clarifications are needed on the objective of the SGP in this matter.
- Because of the above difficulty (and like the global SGP 4541), the purpose of this Brazilian SGP remain unclear between a long term assistance to all CBOs/CSOs project in the two biomes (without clear phasing out strategies or capacity improvement process with clear steps) or the purpose of creating sustainable and long lasting capacities amongst CBOs/CSOs beneficiaries (then with a clear purpose of steps by step improvement and capacity building goal). 

Opinion: favourable, if the sustainability of activities supported and clear goals to bring some Brazilian CBOs/CSOs in capacity to continue to work without SGP assistance are addressed during project development.
	Page 16 of this document include information on the experience, successes and failures in previous SGP phases.

Precise quantitative information on profitability would depend on ex-post economic evaluations, which are very expensive and are not supported by SGP. Since the issue is dealt with through program policy, there is little or no need for such data.

In the first place, the proposals submitted to SGP are selected by the NSC precisely on the basis of their potential for sustainability and for widespread replicability without dependence on large and long-lasting subsidies, be they from SGP or from any other source. Many lessons have been learned about this over the past 17 years. It is clear that the only way to have broad impact is to develop sustainable livelihoods that do not depend on large and continuous grants from government or donors. That is the very essence of the program, which emphasizes production and marketing of environmental goods, not just environmental services, which would create dependence.

If a grantee comes back requesting further support without showing capability of sustainability, such support is denied. That is a matter of policy. There are always many new applicants to choose from, with no need for sequential grants, which would send out the wrong message.

Sustainability of projects like those supported by SGP does not necessarily mean total absence of outside funding over time. Some level of subsidy is almost always necessary when there is provision of socioenvironmental services, not pure profit. The goal of the program is to reduce such funding to a minimum. One of the main goals of SGP in Brazil is precisely to prepare communities to get access to other sources of funding. This is done through capacity development, both by means of practical experience and direct technical assistance and preparation and distribution of manuals on marketing and financial management.




ANNEX C:  CONSULTANTS TO BE HIRED FOR THE PROJECT USING GEF/LDCF/SCCF/NPIF RESOURCES

	Position Titles
	$/

Person Week*
	Estimated Person Weeks**
	Tasks To Be Performed

	For Project Management
	
	
	

	Local

	Administrative Support Assistant
	627
	208
	Local consultant that will give full support for the Country Programme team regarding office management, such as reception, telephone, e-mail, mail, other communiciation, appointments, meetings, materials, travel logistics, organization of workshops

	Accountant
	380
	208
	Permanent responsability for accounting, tax payments, reporting, filing and other procedures to guarantee a proper compliance with fiduciary standards and the Brazilian legislation, which is complex and subject to frequent changes and reinterpretations

	     
	     
	     
	     

	     
	     
	     
	     

	     
	     
	     
	     

	International

	     
	     
	     
	     

	     
	     
	     
	     

	     
	     
	     
	     

	     
	     
	     
	     

	     
	     
	     
	     

	Justification for travel, if any:      


	For Technical Assistance
	
	
	

	Local
	
	
	

	Country Programme Manager
	1,125
	208
	The Country Programme Manager will be responsible for the overall management of the project during its duration in 4 years (52 weeks/year). He/She has the responsibility to guarantee a coherent and high quality grant portfolio and keep project on track to deliver overall results for projects supported by GEF and other co-financing donors, NSC substantive support and secretariat, troubleshooting, donor and partner relations, resources mobilization and reporting, organization and superfision of the selection process, workshops organization, grantee monitoring and evaluation through progress report review and in situ visits, technical assistance to grantees and coordination of production of country programme knowledge products and communications materials.

	Project Assistant
	500
	208
	Financial planning and budget control, disbursements to grantees, record keeping in files and intranet, ATLAS input, administration and procurement, audit support, quality control of grantee MOAs, grantee financial oversight, preparation of financial report, support for the organization of workshops

	Technical assistance in project monitoring and indicators measurement
	875
	164
	local consultant to support baseline data gathering, grants monitoring and evaluation through progress reports and in situ visits, systematization of results and indicators measurement throught reports information as well as field data, assist in the production of country programme knowledge products

	Technical assistance in database update and results management
	875
	44
	local consultant to give support in database updating including the main projects' results and indicators, especially in moments of high volume of information input, such as grants starting and finalization, mid-term review and project termination

	ICT support
	439
	208
	local consultant who will give full support for the Country Programme team regarding computers, software, guidance, troubleshooting, updating, database, data processing, backups, as well as website and intranet design and maintenance

	International
	
	
	

	Assistant general services
	188
	208
	The assistant will perform tasks related to printing, photocopying, price surveys, purchases of supplies, deliveries, bank, post office, notary, library and driving

	- Mid-term review
- Final Evaluation

	1500

1466.67

	10

15

	MTR: Local consultant with great experience in projects evaluation to perform an independent Country Programme Mid-term review, in order to determine progress being made toward the achievement of outcomes and identify course corrections, as needed. Findings of this review will be incorporated as recommendations for enhanced implementation during the second half of the project’s term. FE: local consultant with great experience in projects evaluation to perform an independent Country Programme Final Evaluation, three months prior to the expected project end date. The final evaluation will look at impact and sustainability of results. Given the pilot nature of the first group of upgrading SGP Country Programmes, the final evaluation should also undertake an assessment of costs and benefits of the upgrading process, summarize lessons learned, and provide recommendations to the GEF Secretariat and the Global SGP concerning the upgrading of other Country Programmes

	- Consultant for Project Terminal Report
- Consultants for final grant evaluation and small grants audit

	1666.67

1814.29

	6

14

	1. local consultant to work in collaboration with the Country Programme Manager to prepare the project termination report in order to summarize the results achieved (outcomes and outputs), lessons learned, problems met and areas where results may not have been achieved. He/she will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and help replication of project results. 2.local consultant to perform final grantee evaluation and audit on a risk basis, aiming at reducing programme’s risk of low reporting performance 

	Baseline definition for LULUCF & C stocks at Cerrado and Caatinga
	1,818
	11
	expert to perform a baseline assessment of carbon stocks and establish a carbon monitoring system compliant with IPCC guidelines for the Cerrado and Caatinga, capacity-building on carbon monitoring to country team and individual grantees working on LULUCF, and provision of technical support to country team during  project lifetime

	Consulting for certification procedures development and establishment 
	1,500
	10
	expert to design a strategy for the country programme to deliver results on certified landscapes, considering the specificities of the public and what is already applied in Brazil

	Justification for travel, if any:      



       *  Provide dollar rate per person week.    **  Total person weeks  needed to carry out the tasks.

Annex d:  status of implementation of project preparation activities and the use of funds
A.  explain if the ppg objective has been achieved through the ppg activities undertaken.  
	     


B.  describe findings that might affect the project design or any concerns on project  
         implementation, if any:  
	    


C.  provide detailed funding amount of the ppg activities and their implementation status in the 
        table below:

	Project Preparation Activities Approved
	Implementation Status
	GEF/LDCF/SCCF/NPIF Amount ($)
	Cofinancing

($)

	
	
	Amount Approved
	Amount Spent Todate
	Amount Committed
	Uncommitted Amount*
	

	     
	
	     
	     
	     
	     
	     

	     
	
	     
	     
	     
	     
	     

	     
	
	     
	     
	     
	     
	     

	     
	
	     
	     
	     
	     
	     

	     
	
	     
	     
	     
	     
	     

	     
	
	     
	     
	     
	     
	     

	     
	
	     
	     
	     
	     
	     

	     
	
	     
	     
	     
	     
	     

	Total
	
	0 FORMTEXT 

0

	0 FORMTEXT 

0

	0 FORMTEXT 

0

	0 FORMTEXT 

0

	0 FORMTEXT 

0



      *  Any uncommitted amounts should be returned to the GEF Trust Fund.  This is not a physical transfer of money, but achieved  through 
             reporting and netting out from disbursement request to Trustee.  Please indicate expected date of refund transaction to Trustee.     
� It is important to consult the GEF Preparation Guidelines when completing this template


� Project ID number will be assigned by GEFSEC.


� Refer to the �HYPERLINK "http://www.thegef.org/gef/sites/thegef.org/files/documents/document/GEF5-Template%20Reference%20Guide%209-14-10rev11-18-2010.doc"�Focal Area/LDCF/SCCF Results Framework� when filling up the table in item A.


� This is the cost associated with the unit executing the project on the ground and could be financed out of trust fund or  cofinancing sources.


� Same as footnote #3.





PAGE  
GEF5 CEO Endorsement-Approval-August 2011.doc                                                                                                                                   


 1

