request for

Project Type:

Type of Trust Fund:

part i: project information

| Project Title: GEF SGP Fifth Operational Phase--implementing the program using STAR resources I |  |  |  |
| --- | --- | --- | --- |
| Country(ies): | 16 countries (see Annex I) | GEF Project ID: | 4541 |
| GEF Agency(ies): |  | GEF Agency Project ID: | 4561 |
| Other Executing Partner(s): | UNOPS | Submission Date: | 2012-02-08 |
| GEF Focal Area (s): |  | Project Duration(Months) | 48 months |
| Name of Parent Program (if applicable): - For SFM/REDD+ |  | Agency Fee ($): | 1,633,135 |

- Focal Area Strategy framework

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | Trust Fund | Grant Amount ($) | ### Cofinancing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | 1.1 | 1.1; 1.2 |  | 5,658,632 | 5,660,000 |
|  | 2.1 | 2.3 |  | 5,658,632 | 5,660,000 |
|  | 1.1 | 1.1 |  | 2,962,442 | 3,000,000 |
|  | 4.2 | 4.2; 4.3 |  | 2,962,442 | 3,000,000 |
|  | 5.1 | 5.2 |  | 2,962,442 | 3,000,000 |
|  | 1.3 | 1.2; 1.3; 1.5 |  | 2,801,510 | 2,810,000 |
|  | 3.2 | 3.2; 3.4 |  | 2,801,510 | 2,810,000 |
|  | 1.1 | 1.3 |  | 1,843,401 | 1,850,000 |
|  | 2.1 | 2.3 |  | 1,843,401 | 1,850,000 |
|  | 1.1 | 1.1.1 |  | 3,686,801 | 3,700,000 |
|  | 1.1 | 1.6 |  | 1,843,401 | 1,850,000 |
|  | 5.1 | 5.4; 5.5 |  | 1,843,400 | 1,850,000 |
|  | Others |  |  |  |  |
| Subtotal |  |  |  | 36,868,014 | 37,040,000 |
| Project management cost |  |  |  | 3,960,351 | 3850000 |
| Total project costs |  |  |  | 40,828,365 | 40,890,000 |

- Project Framework

| ### Project Objective: Global Environmental Benefits secured through community-based initiatives and actions |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Grant Amount ($) | ### Confirmed Cofinancing ### ($) |
| Conservation of Globally Significant Biodiversity Through Community-based Initiatives and Actions |  | 1. Improved sustainability of protected areas and indigenous and community conservation areas through community-based actions 2. Mainstreamed biodiversity conservation and sustainable use in production landscapes, seascapes and sectors through community initiatives and actions | At least 113 community and civil-society based projects funded supporting biodiversity conservation in indigenous and community conservation areas At least 113 community and civil-society based projects funded supporting biodiversity conservation through mainstreaming |  | 11,317,264 | 11,320,000 |
| Reduction or Avoidance of GHG Emissions While Building Climate Resilience at the Community-level |  | 3. Demonstration, development and transfer of low-GHG technologies at the community level 4. Increased energy efficient, low-GHG transport at the community level 5. Conservation and enhancement of carbon stocks through sustainable management and climate proofing of land use, land use change and forestry | At least 59 community and civil-society based projects funded supporting the transfer of low-carbon technologies At least 59 community and civil-society based projects funded supporting low-GHG transport At least 59 community and civil-society based projects funded supporting conservation and enhancement of carbon stocks |  | 8,887,326 | 9,000,000 |
| Reverse and Prevent Desertification/Land Degradation and Mitigate the Effects of Drought in Affected Areas Through Community-based Initiatives and Actions |  | 6. Maintenance or improvement in flow of agro-ecosystem and forest ecosystem services to sustain livelihoods of local communities 7. Reduction of pressures at community level from competing land uses (in the wider landscapes) | At least 56 community and civil-society based projects funded supporting maintenance or improvement of flow of ecosystem services At least 56 community and civil-society based projects funded supporting reduction of pressures from competing land uses |  | 5,603,020 | 5,620,000 |
| Sustainable Management of Transboundary Water Bodies at the Community-level |  | 8. Communities support the implementation of Strategic Action Programmes (SAPs) in trans-boundary surface and groundwater basins; 9.Communities support the implementation of Strategic Action Programmes (SAPs) in large marine ecosystems management | At least 36 community and civil-society based projects funded supporting community initiatives for sustainable management of transboundary surface and groundwater basins; At least 36 community and civil-society based projects funded supporting community initiatives for sustainable management of large marine ecosystems management |  | 3,686,802 | 3,700,000 |
| Reduce and Eliminate the Release of Harmful Chemicals into the Environment Through Community-based Initiatives and Actions |  | 10. Phase out of POPs and chemicals of global concern at community level | At least 72 community and civil-society based projects funded supporting the phase out of POPs and chemicals of global concern |  | 3,686,801 | 3,700,000 |
| Enhance and Strengthen Capacity of Communities and Civil Society to Address Global Environmental Challenges, primarily focusing on biodiversity, climate change and land degradation focal areas, while also covering international waters and POPs |  | 11. Enhance and strengthen capacities of community-based and civil society organizations (CSOs) to engage in consultative processes, apply knowledge management to ensure adequate information flows, and implement convention guidelines 12. Enhance capacities of CBOs and CSOs to monitor and evaluate environmental impacts and trends | GEF SGP National Steering Committees and National Focal Groups (both groups on voluntary services to GEF SGP) actively engaged with GEF national consultative processes Learning and knowledge management platform established to share lessons learned among CBOs and CSOs across all SGP countries At least 731 CBOs and CSOs as SGP partners with strengthened capacities |  | 3,686,801 | 3,700,000 |
| Subtotal |  |  |  |  | 36,868,014 | 37,040,000 |
| Project management Cost |  |  |  |  | 3,960,351 | 3,850,000 |
| Total project costs |  |  |  |  | 40828365 | 40890000 |

- sources of confirmed Cofinancing for the project by source and by name ($)

| Sources of Co-financing | Name of Co-financier (source) | Type of Cofinancing | Cofinancing Amount ($) |
| --- | --- | --- | --- |
|  | Multiple |  | 5,900,000 |
|  | Multiple |  | 500,000 |
|  | UNDP |  | 2,400,000 |
|  | Multiple |  | 1,500,000 |
|  | Multiple |  | 1,500,000 |
|  | Multiple |  | 3,000,000 |
|  | Multiple |  | 3,000,000 |
|  | Multiple |  | 1,000,000 |
|  | Multiple |  | 1,000,000 |
|  | Multiple |  | 9,545,000 |
|  | Multiple |  | 9,545,000 |
|  | Multiple |  | 1,000,000 |
|  | Multiple |  | 1,000,000 |
| Total Co-financing |  |  | 40,890,000 |

- GEF/LDCF/SCCF/NPIF Resources Requested by agency, Focal Area  and country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
|  |  |  | Global | 40,828,365 | 1,633,135 | 42,461,500 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 40,828,365 | 1,633,135 | 42,461,500 |

- Consultants working for technical assistance components:

| ### Component | ### Estimated Person Weeks | ### Grant Amount ($) | ### Cofinancing ($) | ### Project Total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* |  |  |  | 0 |
| ### International consultants* |  |  |  | 0 |
| ### Total |  | 0 | 0 | 0 |

*  Details to be provided in Annex C.

- Project management cost

| ### Cost Items | ### Total Estimated Person Weeks/Months | ### Grant Amount ($) | ### Co-financing ($) | ### Project Total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* |  |  |  | 0 |
| ### International consultants* |  |  |  | 0 |
| ### Office facilities, equipment, vehicles and communications* |  |  |  | 0 |
| ### Travel* |  |  |  | 0 |
| ### Others** | Specify "Others" (1) |  |  | 0 |
|  | Specify "Others" (2) |  |  | 0 |
| Total |  | 0 | 0 | 0 |

* Details to be provided in Annex C.                    ** For others, to be clearly specified by overwriting fields *(1) and *(2).

- Does the project include a “non-grant” instrument?

(If non-grant instruments are used, provide in Annex E an indicative calendar of expected reflows to your Agency 
       and to the GEF/LDCF/SCCF/NPIF Trust Fund).

- describe the budgeted m &e plan:

Strengthening of monitoring and evaluation will be an important focus area for GEF SGP during the fifth operational phase (OP5). The most recent global evaluation of the GEF SGP recognized a range of good practices in M&E across the SGP portfolio, but also recommended that M&E could be further improved. An GEF SGP paper following up on the global evaluation submitted to the GEF Council in May 2008 (GEF/C.33/5) further noted a number of specific areas for improvement, including the upgrading of the SGP database through the inclusion of country programme outcomes, and reporting on indicators. During GEF-5, GEF SGP will implement a comprehensive M&E plan as included in Annex F to this document. The GEF’s results and program implementation progress reporting requirements are outlined in the GEF Annual Monitoring Review Guidelines. GEF SGP’s M&E plan is designed and developed to address how GEF SGP will meet all reporting requirements, which also contribute to and support GEF SGP’s knowledge management approach and activities that emphasizes the importance of effective sharing of lessons and good practices to consistently strengthen and improve GEF SGP’s contribution to the generation of Global Environmental Benefits. As appropriate, M&E reports and information within GEF SGP countries will be shared with national GEF focal points and convention focal points, which can then be incorporated in national convention reporting. All M&E activities outlined in the M&E plan will be undertaken as necessary and appropriate to ensure cost-effectiveness, with M&E carried out as appropriate relative to the size of any given project and other associated factors such as complexity and risks involved. GEF SGP will include a robust monitoring and evaluation system fully in-line with GEF and UNDP monitoring and evaluation policies and minimum standards, including consistency with UN Evaluation Group standards and norms. The GEF SGP monitoring and evaluation plan complies with all GEF M&E minimum standards, including: SMART indicators for implementation and results, baseline information, identification of required programme reviews and evaluations, specified roles and responsibilities, and a budget allocated to support M&E activities. At the global level, SGP will continue to improve the GEF SGP database, and facilitate the tracking of outcomes across the portfolio. The SGP Results Framework is attached as Annex A to this document. The indicators identified in this results framework are the global level indicators designed to meet reporting on GEF-5 strategic objectives. At the country and project levels appropriate additional focal area specific results-oriented indicators are applied to ensure projects achieve expected results, and to track successful approaches, including socio-economic outcomes where possible. To support results reporting linked to the GEF-5 results framework, GEF SGP will continue to improve indicators and mechanisms, including tracking tools, for reporting on these indicators. Further revision and development of results indicators may include capacity development indicators, as appropriate. GEF SGP recognizes the importance of identifying and documenting results beyond the output level, and will undertake approaches to move current reporting further down the results chain, toward documentation of impact. M&E activities will include partnerships with relevant organizations and stakeholders that can positively contribute to GEF SGP’s work in this area. GEF SGP’s M&E resources are not implemented on a per country or project basis however, as there is a significant need for M&E support at the regional and central/global levels as well. Due to the continuous programmatic nature of the GEF SGP, M&E activities in OP5 will need to cover the ongoing activities from previous operational phases. The GEF Evaluation Office and UNDP Evaluation Office will be responsible for the next global evaluation of the GEF SGP, anticipated to take place between 2012-2013.

part ii:  project JustiFication

- Description of the consistency of the project with:

A.1.1.  The GEF focal area/LDCF/SCCF strategies/NPIF Initiative:

The objectives and expected outcomes of the GEF SGP (for the purpose of this document, SGP is referred as the country programmes in the 16 pure STAR countries) for the 5th Operational Phase (OP5) directly support the GEF’s strategic priorities for GEF-5. In the area of biodiversity conservation, GEF SGP will support the first two GEF biodiversity objectives: 1) Improving the sustainability of protected area systems, and 2) Mainstreaming biodiversity conservation and sustainable use into production landscapes, seascapes, and sectors.  To date, in the countries covered by this document, GEF SGP has provided 1,510 community-based biodiversity conservation projects with $32 million, generating an additional $62 million in cash and in-kind co-financing. GEF SGP grants in OP5 will generate global benefits by leveraging community-based efforts to conserve biodiversity through improving the effectiveness and sustainability of community conservation areas and indigenous protected areas, which make up a critical component of the global protected areas system, even if they are not always recognized as such. To support sustainable use of biodiversity, the GEF SGP will promote the mainstreaming of biodiversity friendly practices in production landscapes and seascapes, through measures such as organic certification for community level and small-scale producers of biodiversity-based products; improved community-based resource use of non-timber forest products; and community level enforcement measures in near shore fisheries.  With GEF SGP’s support, civil society and community-based organizations will develop the capacity to improve conservation and sustainable use efforts and ensure benefits for community livelihoods, contributing to long-term sustainability.

GEF SGP objectives will be consistent with and support the first, fourth and fifth climate change strategic objectives for GEF-5, which are the most relevant, in the context of GEF SGP’s civil society and community-based focus, of the six GEF climate change objectives. To date, GEF SGP has provided 703 community-based climate change projects with $15 million, generating an additional $17 million in cash and in-kind co-financing in the countries covered by this document. In line with the first GEF strategic objective, for OP5 GEF SGP will provide grants to promote the demonstration, development and transfer of innovative low-carbon solutions at the community level, such as micro-solar power and fuel-efficient stoves.  In line with the fourth GEF strategic objective for climate change, SGP will promote energy efficient, low carbon transport at the community level, for example with support for low-emission and energy efficient motor scooters and small boat motors, which make up the majority of individual motorized transport in rural areas.  Also in the climate change focal area, GEF SGP will support the conservation and enhancement of carbon stocks through sustainable management and climate proofing of land use, land use change and forestry, which is consistent with the fifth GEF strategic objective.

To address land degradation, GEF SGP will support two objectives, both of which are consistent with the GEF land degradation strategic priorities for GEF-5.  To date, GEF SGP has provided 355 community-based land degradation projects with $6 million, generating an additional $7 million in cash and in-kind co-financing.  The first SGP objective for OP5 is directly linked to the first strategic objective of the broader GEF for the land degradation results framework:  GEF SGP will seek to maintain or improve the flow of agro-ecosystem and forest ecosystem services to sustain community livelihoods.  Second, GEF SGP will work with community partners to reduce pressures on natural resources from competing land uses at the community level.

While the GEF SGP is consistent with GEF strategies for each focal area, the GEF SGP is a strategic programme of the GEF that addresses environmental issues in an integrated manner through all focal areas. When possible and relevant, the GEF SGP supports integrated and synergistic multi-focal area approaches. Because the grants to be provided by the SGP in the 5th Operational Phase have yet to be selected, in each country GEF SGP can support a strategic approach by ensuring funding only for community-level grants that are in line with global GEF priorities.  Since the STAR funds come from specific focal areas, the majority of the funds will be used to deliver projects addressing STAR focal area issues, while other non-STAR focal area components may be included in the projects. To continue GEF SGP's multifocal area approach and leverage existing partnerships and experiences related to non-STAR focal areas (international waters and chemicals), up to 20% of the STAR funds can be used to support international waters and chemicals projects.  10% of STAR grant funds will be used for capacity building activities.

In international waters, the GEF SGP will support transboundary water body management with community-based initiatives, including community-level linkages for implementation of SAPs, in partnership with other GEF initiatives. This GEF SGP objective is consistent with the first, second and third GEF strategic objectives for the international waters focal area. To date, SGP has provided 237 community-based international waters projects with $3 million, generating an additional $5.7 million in cash and in-kind co-financing.

GEF SGP will also promote and support the phase out at the community level of POPs and chemicals of global concern, for example through the introduction of POP substitutes and promotion of environmentally friendly practices in pesticide management.  This is consistent with the first strategic objective of the chemicals focal area for GEF-5. To date, GEF SGP has provided 49 community-based POPs projects with $0.8 million, generating an additional $0.7 million in cash and in-kind co-financing in the countries covered by this document.

Capacity development is a cross-cutting issue that GEF SGP will continue to address. This is also in line with GEF focal area strategies in GEF-5 that include capacity development aspect in every focal area strategy.  10% of project funds will be used to promote capacity development.  Given the sources of the STAR funds, the capacity development activities will primarily focus on biodiversity, climate change and land degradation, while also covering international waters and chemicals focal areas.  An integrated multi-focal area approach to capacity development will be undertaken to strengthen the capacity of CSOs and CBOs in project development, implementation, monitoring and evaluation in alignment with GEF policies and requirements that will result in global environmental benefits.  GEF SGP will continue developing capacity of civil society organizations (CSOs), with priority for community-based organisations (CBOs) and indigenous peoples organisations in the areas such as engagement through consultative process; generation, access and use of information and knowledge; supporting participatory processes in policy and legislation development; and monitoring and evaluation of environmental impacts and trends.  This is consistent with the GEF’s long-standing programmatic support for capacity development, as outlined in the GEF-5 programming document.

This document covers the STAR funds contribution made by Country Programmes with no core grant allocation, while the non-grant component (staffing cost and country operating budgets) will be drawn from both global core funds and STAR management budgets. In each GEF SGP Country Programme, funding may be drawn from the national STAR allocations. GEF Council Document GEF/C.36/4 specified various funding criteria for different categories of Country Programmes.  Specifically, "Countries which have an indicative overall STAR country allocation of more than $15 million will no longer be able to access the SGP’s core funding and will need to finance their projects from their STAR allocations. A maximum cumulative amount of up to $3.6 million, with an average up to $900,000 per year can be allocated." (GEF/C.36/4).

Sixteen GEF SGP countries with more than $15 million STAR, have no access to the global core funds for grants, and it is critical for these countries to obtain sufficient STAR funds to sustain the Country Programmes' grant-making activities. This document is intended to obtain STAR funds to cover the grant allocation of these sixteen GEF SGP Country Programmes, so that GEF continues to channel funds to CBOs and CSOs in these countries. Additionally, while GEF SGP running costs remain more or less stable, higher STAR funds (mainly used for grants) will contribute to achieving optimal GEF SGP cost efficiency globally.

A.1.2.   For projects funded from LDCF/SCCF:  the LDCF/SCCF eligibility criteria and priorities:

A.1.3 For projects funded from NPIF, relevant eligibility criteria and priorities of the Fund:

A.2.   National strategies and plans or reports and assessments under relevant conventions, if  applicable, i.e.  NAPAS, NAPs, NBSAPs, national communications,  TNAs, NIPs, PRSPs, NPFE, etc.:

The GEF SGP is a country-driven programme in that Country Programme policies and priorities are developed and owned by in-country stakeholders to benefit the global environment while bringing in local sustainable development results. National strategies and plans, along with GEF’s policies and strategies, form the basis for GEF SGP’s programming and operation. Almost all national policies and strategies such as NBSAPs, NAPs, NIPs and others emphasize the importance of engaging the widest possible array of stakeholders (including CSOs and other groups) in achieving the objectives, and in particular the community-based approaches to environmental protection. Hence, GEF SGP’s community-based approach that targets small-scale local actions is very relevant to the implementation of these national policies and strategies. The GEF SGP operates in countries where specific requests to initiate the programme have been received from the appropriate national authorities, represented by the GEF Operational Focal Point. By first requesting and subsequently supporting implementation of the GEF SGP, a government commits to GEF SGP being a country-driven and owned initiative supporting community-level and civil society environmental projects. National priorities are reflected through the constitution of the GEF SGP National Steering Committee (or National Focal Group for sub-regional programmes), which guides implementation of the SGP in each respective country. NSC members are leading national government and civil society representatives in the environmental field, who provide strategic guidance and oversight for the programme, and ensure its focus on and coherence with national priorities as they apply to and are relevant for community-level needs and priorities. GEF SGP Country Programme strategies are governing documents for GEF SGP programming and operation in-country. The development and updating of the strategies are based on national policies and action plans, such as NBSAPs, NAPs, NIPs and other national key documents, which are directly linked to GEF focal area strategies and priorities. GEF SGP’s Country Programme strategies are developed and updated to reflect national priorities, while ensuring alignment with GEF policies and priorities. Each of the strategies draws on priorities and activities included in these national policy documents, particularly those that are suitable for communities and CSOs small-scale interventions.

- Project Overview:
B.1. Describe the baseline project and the problem that it seeks to  address:

International attention has been focused on global environmental issues for decades (including nearly 20 years of existence of the GEF and GEF SGP), and there have been some positive steps in that time. Yet, the scale and scope of these problems are such that they remain critical areas for ongoing investment and require a wide range of simultaneous, integrated and multi-focal approaches. The GEF SGP is predicated on the idea that community-driven, stakeholder owned, civil society led initiatives that generate local as well as global benefits are among the most effective ways to address global environmental challenges, and this model has repeatedly achieved success. In effect, GEF SGP operationalizes the maxim “think globally, act locally,” and has, based on its effectiveness at the community-level, become the “public face” of the GEF. The GEF SGP supports community-level initiatives across the range of global environmental issues addressed by the GEF, and participation, democracy, flexibility, and transparency are cornerstones of the GEF SGP approach. The communities targeted by GEF SGP are often the poorest and most vulnerable, and typically have low levels of capacity to adequately address global environmental problems. Providing support for community-based and civil society initiatives is an effective and necessary component of comprehensively addressing global environmental problems, and the GEF SGP plays a critical role in channeling this support. There are few resources targeted towards and available for community-level actions, and stakeholders at this level often lack the capacity to access national or international donors. GEF SGP has a proven track record of effectively engaging with and leveraging community and civil society based initiatives, and this support must continue, as well as be scaled-up, to achieve a sustainable future. The Third Global Biodiversity Outlook, presented in May 2010, reflecting the most recent state of knowledge of the status of global biodiversity, found that “there are multiple indications of continuing decline in biodiversity in all three of its main components – genes, species and ecosystems.” The Millennium Ecosystem Assessment (MA) showed that the most important drivers of biodiversity loss are habitat change, climate change, invasive alien species, overexploitation, and pollution. Throughout OP4, the GEF SGP contributed to the strengthening of almost 12 million hectares of protected areas. According to the most recent Intergovernmental Panel on Climate Change synthesis report, “global GHG emissions due to human activities have grown since pre-industrial times, with an increase of 70% between 1970 and 2004.” While the majority of current global GHG emissions come from developed economies, 17.4% of GHG emissions come from the forestry sector (including deforestation), while 13.5% comes from agriculture. The 2007 “Stern Review” noted that deforestation and forest degradation are the main emission sources in many developing countries. The MA reported that drylands occupy 41% of the earth’s land area, and 10-20% of drylands are already degraded with a much larger percentage under threat from desertification. The MA identified the direct drivers of land degradation, including land use change, natural resources consumption and climate change, which are further highlighted in the 10-year (2008-2018) strategy of the UNCCD. In OP4, more than 600 SGP-supported projects generated models and good practices for sustainable agriculture, and rangeland and forestry management. The Fourth Overall Performance Study of the GEF (OPS4) found that “The conditions that gave rise to the GEF and creation of an international waters focal area have not abated, and there are rising challenges.” Key issues in this area include coastal pollution and erosion, unsustainable fisheries, nutrient transfer (particularly nitrogen) from the land to the sea resulting in eutrophication and algal blooms, unsustainable management of fresh water supplies, and invasive species. Previous SGP efforts have supported the rehabilitation of coastal habitats, sustainable fishing practices, and the reduction of land-based pollution. Persistent Organic Pollutants bio-accumulate in the environment and can lead to serious health effects for humans. The World Health Organization estimates that pesticides may cause 250,000 unintentional deaths a year (particularly among agricultural workers), and nearly three million people may suffer additional effects, mostly in developing countries. In Africa, it is estimated that more than 50,000 tons of obsolete pesticides have accumulated. Other key harmful chemicals are PCBs, dioxins and mercury. To contribute to resolving these challenges, the GEF SGP provides small-scale grants to community-based and non-governmental organizations for projects in-line with the strategic priorities of the GEF. Through its first 18 years, SGP has supported 2,907 community-level projects with over $64 million in funding, leveraging over $102 million in cash and in-kind co-financing in the countries covered by this document. Within the GEF SGP portfolio, 90% of projects have achieved outcome ratings in the satisfactory range, and 80% of projects are considered to have low risks to the sustainability of outcomes. Across GEF focal areas the GEF SGP empowers local communities to seek integrated multi-focal area solutions that can be replicated and scaled-up, and helps spark successful initiatives that grow beyond GEF SGP’s initial support. GEF SGP contributes to the building of networks, and strengthens civil society to unlock local capacity for solutions to these critical environmental problems. More than 60% of SGP grants target poor communities in participating countries, which have the greatest need for assistance. Indigenous peoples, who have the knowledge and experience to create sustainable solutions to environmental challenges, are also targeted by at least 15% of GEF SGP grants. More than a quarter of GEF SGP grants specifically support women, another priority target group. The GEF SGP approach leverages shifts toward environmentally sustainable livelihood options, and increases education and awareness on environmental issues. While the GEF SGP seeks solutions integrated across focal areas, the specific strategic objectives below are designed to address the global environmental problems described above. These strategic objectives are in-line with the GEF-5 strategic priorities, and are the means to long-term impact level results. For GEF-5, it is anticipated that the SGP STAR funding will support at least 737 projects (should the maximum grant amount of $50,000 be utilized) to as many as 1,474 projects (at the average grantmaking of $25,000 per project).

B. 2. incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:

| The GEF SGP provides support to achieve global environmental benefits at the community level. The current baseline scenario, partly described in Section II.A. above, would remain the status quo in a business-as-usual scenario without GEF support. On the one hand, community-level stakeholders in remote and marginalized areas have the least access to technical and financial resources to address global environmental issues, and the GEF SGP is a critical partner to assist communities tackling environmental challenges. At the same time, over its initial 18 years the GEF SGP has developed an efficient and effective system while building a growing portfolio of demonstrated community-based approaches. The programme is a critical resource for GEF SGP’s partner organizations and communities, without which their available support channels would be reduced and their ability to confront environmental issues limited. The GEF SGP strengthens the capacity of communities and non-governmental organizations, increases knowledge and awareness about environmental threats, and provides financial leverage to overcome short-term decision-making that negatively affects environmental resources. Short-term decision-making is often unavoidable in poor regions where individuals have to secure the basic elements for survival on a day-to-day basis, and therefore do not have the possibility to plan for long-term sustainable livelihoods ensuring environmental protection. Many of the communities where GEF SGP works are in remote or marginalized areas often not targeted by large-scale national development efforts. At the same time, these communities often have detailed knowledge of their local environment built up over generations, and should be primary partners in environmental conservation and sustainable development. Critical global environmental issues benefiting from the GEF SGP’s integrated multi-focal support are those addressed by the GEF: biodiversity conservation, climate change, land degradation, degradation of international water bodies, and the use and disposal of harmful chemicals. The baseline scenario without GEF support would therefore see: • Ongoing poverty and unsustainable practices in communities that depend on the environment for their livelihoods; • Continued degradation of ecosystem function due to biodiversity loss, deforestation and pollution; • Business-as-usual increasing GHG emissions, leading to negative environmental and human impacts from climate change and air pollution; • Further degradation and desertification of productive and non-productive land-use systems; • Continued negative environmental trends in international water bodies; • Unsafe use and disposal of environmentally harmful chemicals; and • Lower levels of capacity development and knowledge management related to key global environmental issues. Such conditions, if not addressed, will continue contributing to loss of ecosystem function, and the continuation or increase of corresponding poverty levels. The baseline scenario acknowledges that partners at local, national and international levels make an important contribution to addressing these issues, but that greater synergistic results to achieve incremental global environmental benefits will be secured with GEF SGP support, since GEF SGP brings together a range of diverse partners at the national level to address community-level issues. In addition, efforts to address global environmental challenges in an innovative and community-driven manner are underfunded by orders of magnitude in relation to the potential need, including currently limited funding for capacity development and knowledge management at the community-level. GEF SGP provides incremental added value by catalyzing new development models, improving knowledge flows, and informing policy. The 2007 Independent Evaluation of the GEF SGP found that some of GEF SGP’s greatest contributions are in the realm of national policy development, catalyzed by country-specific GEF SGP initiatives. Replication and scaling-up will continue to be key tenets of the SGP approach to achieve incremental benefits, and GEF SGP will work with key partners, such as the GEF NGO network, to disseminate good practices throughout global civil society and promote the GEF agenda. Furthermore, without GEF SGP there would be limited monitoring and reporting on environmental conservation efforts and environmental trends in targeted areas and communities, which is critical for data collection, documenting and disseminating good practices. With its integrated and scaled-up approach to addressing environmental issues at the community level, the GEF SGP fills a critical niche in environmental efforts to achieve impact-level results for global environmental benefits. |  |
| --- | --- |

B.3. Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF). As a background information, read Mainstreaming Gender at the GEF.":

GEF SGP is rooted in the belief that global environmental problems can best be addressed if local people are fully involved in project design and formulation, have strong ownership of the actitivities undertaken through a "demand-driven" approach, and that direct socioeconomic benefits will accrue to communities as a result of project implementation, a consequence that provides the incentives and motivation to sustain the projects after the end of grant funding. In contrast with "expert-reliant" development interventions, the emphasis in GEF SGP is on creative problem-solving and innovation by the communities themselves, often based on the comparative strengths of an intimate understanding of local circumstances. GEF SGP is premised on the principle that through the provision of relatively small amounts of funding, local communities can undertake cost effective activities that will make a significant socioeconomic difference in their own lives, whilst generating global environmental benefits. GEF SGP has always recognized the importance of socio-economic benefits to local communities, such as poverty reduction and livelihood, water and sanitation, health, education, and women’s empowerment, as essential to achieving sustainable global environmental benefits. One of the key elements of GEF SGP is that it considers the human needs of the communities it works with to be fundamentally tied to the use of natural resources to attain sustainable livelihoods. Some of the strategic considerations for project development are to increase productivity or generate new livelihood opportunities, as well as income and access to financial capital. GEF SGP understands that the sustainability of its projects will only be possible if there is a high level of ownership by the community and if it generates local benefits. GEF SGP projects help communities to improve their access to tools and machinery, land, and key infrastructure such as energy and water supply. But as important as having the right infrastructure is to enhance the social capital, institutional capacity and equity of the communities, GEF SGP places special emphasis on enhancing the institutional capacities of the communities, by providing training and expanding their networks, as well as by improving their ability to address global environmental issues. To do this, the programme invests in strengthening the human capital of the community, by enhancing the skills, knowledge and abilities necessary to implement and sustain the projects. In GEF-5, GEF SGP will further systematize its approach to local livelihoods by consolidating good experiences and identifying and securing strategic partnerships for funding opportunities. In the past, GEF SGP has raised co-financing to finance sustainable alternative livelihoods activities and address the community needs for community buy-in of the projects. For instance, the Community Water Initiative (CWI) funded by bilateral donors and implemented by GEF SGP has provided water supply and sanitation services to communities implementing GEF SGP projects, ensuring communities’ acceptance and support for SGP projects. Such an approach to combine and sequence GEF funding with non-GEF funding has proven to be mutually beneficial and re-enforcing. GEF SGP understands the importance of gender equality and women’s empowerment as essential elements to achieve sustainable development and project impacts for the GEF. As such, gender is mainstreamed throughout the GEF SGP programme and its associated portfolio of projects. Gender is one of the mandatory cross-cutting requirements in the GEF SGP grant-making criteria and is incorporated within the SGP project cycle. About 17 percent of GEF SGP projects supported world-wide have focused speciﬁcally on the engagement and empowerment of women. Although obstacles remain at the local and community level, GEF SGP has been able to support projects that have benefitted both men and women within the same communities. Many GEF SGP projects have been recognized for their success in promoting gender equality and womens’ leadership. GEF SGP Country Programme Strategies are required to include references to gender, and all GEF SGP staff members are encouraged to take the UNDP online gender training, as well as to take advantage of related opportunities offered by UN agencies. Gender is one of the key results of the GEF SGP National Coordinators’ annual Performance and Review Assessment (PRA) carried out by UNDP Country Offices and the Central Programme Management Team at the global level. GEF SGP has also established a global partnership with the Huairou Commission to pilot capacity building for women and dissemination of gender-related good practices between GEF SGP countries worldwide.

B.4  Indicate risks, including climate change risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks to  be further developed during the project design:

There are few new risks to be faced since the programme has been operating at the global level for nearly 20 years. Although this cohort of 16 countries includes mostly well experienced and mature GEF SGP country programmes, there are some that joined GEF SGP more recently than others (e.g. Argentina (2005), and Cuba, Ethiopia, Madagascar (2004)). Potential risks are known, and through the past experience of the GEF SGP risk mitigation measures are in place. There remains the challenge of working directly with community-based and non-governmental organizations that have a low level of technical and management capacity. Past performance of the GEF SGP portfolio has shown that 90% of GEF SGP grants achieve outcomes in the satisfactory range. To mitigate risks, especially in the small underperforming portion of the portfolio, the GEF SGP works with all grantees to help build capacity by identifying appropriate rates of disbursement, linking grantee partners to learn from each other, and working in a flexible manner that responds to the strengths and comparable advantages of grantees. Risks of underperformance due to capacity limitations will also be mitigated by consistent and comprehensive oversight and monitoring of the GEF SGP portfolio in each country by SGP CPMT and the UNDP CO. The GEF SGP also reduces risk by supporting replication of good practices that have proven to deliver on GEF strategic priorities at the community level. In each GEF SGP country, the National Steering Committee, with representation from civil society leaders, government institutions, and donors provides further support for effective design and implementation of GEF SGP projects. During GEF-5, the programme is expanding to include an even greater number of countries. As the programme expands, the overall level of effort for coordination and implementation at the central level increases. The SGP CPMT is undergoing a review of the internal management arrangements to ensure that efficient and effective structures and adequate financial and human resources are in place to meet the needs of a growing portfolio of countries. There is potential for climate effects to influence GEF SGP grant results, positively or negatively, particularly with respect to biodiversity and land degradation. For example, climate effects could have adverse impacts on agricultural biodiversity conservation through drought or flooding, and on the application of protected areas as a conservation measure due to geographically shifting ecosystems. Such risks are not specific to the GEF SGP, but to all GEF-supported interventions. At the community level, climate risks may however disproportionately affect SGP grantees: the poorest, most marginalized, least developed communities are the least able to finance climate resilience measures. Such communities, and associated organizations, are among the primary GEF SGP partners. Grants will be made keeping in mind the potential climate risks, and steps will be taken to minimize and adapt to effects when possible. Furthermore, methodologies on dealing with climate related risks have become available from GEF SGP projects in community-based adapation (CBA) coming from the GEF SPA-funded CBA pilots in nine countries as well from the AusAID-supported Mekong and Asia-Pacific CBA program. These will be disseminated to community and CSO proponents for integration as needed into the design of projects. In addition to the general risks the GEF SGP faces as a global programme, for the countries solely dependent on STAR funding in particular, there are risks related to government support, STAR funds availability and inadequate STAR amounts. In order to operate at an optimal level, SGP needs to ensure that sufficient funding is available to maintain the management cost/grant ratio at 10%, as well as to ensure effective grant-making in relation to the absorptive capacity within countries. In countries where STAR endorsed amounts are relatively low, GEF SGP will make efforts to mobilize additional resources and actively explore opportunities where GEF SGP can act as delivery mechanism for other donors/projects in order to continue to be cost efficient and effective. In the event that sufficient additional resources cannot be mobilized, GEF SGP will look at possibilities for reducing its costs by scaling down certain country programmes – for example by reducing staff to only one staff position per country – as well as the possibility to phase out certain country programmes once grant projects have been completed. Another possible risk related to reliance on STAR funds alone is that some governments may take the occasion to exert dominant influence in the Country Programme overall governance. To mitigate such risks, SGP strives to inform key stakeholders of the provisions of the GEF SGP Operational Guidelines, which mandate a civil society majority in national steering committees as a key GEF SGP principle. Its civil society driven approach has been one of the elements of success of the programme which has also ensured its transparency and helped to foster collaborative and supportive government/civil society relations. Finally, there remain possible exogenous risks to desired outcomes at the programme and project level, such as severe weather and other force majeure events, political instability, and global economic crisis. Exogenous risk factors will be systematically tracked and mitigation measures will be identified and implemented according to a need-based approach as appropriate..

B.5. Identify key stakeholders involved in the project including the private sector, civil society organizations, local and indigenous communities, and their respective roles, as applicable:

As an integral part of its decentralised system of national-level steering committees, GEF SGP operates through a multi-stakeholder approach engaging a range of stakeholders including NGOs, CBOs, indigenous people, the private sector, government, academia, and donor partners. During OP5, CSOs will be both beneficiaries and direct participants in GEF SGP through their inclusion in NSCs and National Focal Group, where non-governmental members must be in the majority, as well as by taking on the role as National Host Institutions and other key roles related to knowledge sharing and policy advocacy. Although GEF SGP grants are targeted specifically at community-based and non-governmental organizations, a broad range of stakeholders are engaged as active partners during grant implementation, including inter alia research institutes, local and municipal governments, international NGOs, as well as national and international volunteers. With regard to indigenous peoples and marginalised populations, GEF SGP follows a set of principles that advocate for a flexible, time sensitive, and simple project cycle in order to allow these "difficult to reach" groups to access GEF SGP support. The programme has pioneered numerous user-friendly modalities to work with poor and marginalized groups including alternative proposal formats such as participatory video, photo stories, and community theatre, and allowances are made for concept and project submission in local and vernacular languages. GEF SGP also allows for flexible disbursement terms to cope with indigenous peoples’ culture, customs and seasonal movements. Through stakeholders workshops, CSOs are able to learn of GEF SGP projects and activities and provide inputs on how to improve on them. B.6. Explain how cost-effectiveness is reflected in the project design: The project is to be delivered by a proved cost-effective mechanism of GEF SGP (Joint Evaluation of SGP 2007). GEF SGP relies heavily on voluntarism in country programme governance. In each SGP country, the National Steering Committee (NSC), with representation from civil society leaders, government institutions, and donors provides strategic, technical and policy support for effective design and implementation of GEF SGP projects. The NSC is further supported by a Technical Advisory Group with focal area experts.

B.7. Outline the coordination with other related initiatives:

The GEF SGP has formed mutually beneficial long-standing relationships with international, national and community-level initiatives and partners, and will continue to seek synergies in the coming operational phase. GEF SGP works with relevant stakeholders in the geographic and thematic areas supported by GEF SGP to ensure coordination of donor funding on relevant initiatives. GEF SGP will also seek linkages with other relevant GEF MSPs and FSPs whenever synergies can be found. The table below highlights selected key GEF SGP relationships with related global level initiatives relevant to the 5th Operational Phase. There are also numerous national and local level GEF SGP partnership initiatives (although, given their number, it is not possible to list them in the table below), and these will continue to be a priority for GEF SGP in the 5th Operational Phase. Table 1 Initiative Name; Organization(s); Relevance to SGP; Brief description of coordination, synergy with SGP. Mekong Asia-Pacific Community Based Adaptation programme (MAP CBA) and SIDS CBA; AusAID; Co-financing for community-based adaptation to climate change; Cost-sharing for project activities on resilience to climate change, including regional technical support and knowledge management components.. Community Management of Protected Areas Conservation (COMPACT); United Nations Foundation (UNF); Strategic aggregation of small grants at landscape scale; Cost-sharing from UNF for the targeted delivery of GEF grant funding to target World Heritage Sites and Biosphere Reserves. World Heritage ‘Local Ecological Entrepreneurship Programme’ (WH-LEEP); UNF & Conservation International Verde Ventures programme; Extension of COMPACT landscape approach; Cost-sharing from UNF and CI for support to SME and producer organisations through the provision of biodiversity-friendly loans.. Community Water Initiative (CWI); SIDA, Govt of Norway, and Govt of Luxembourg; Co-financing for water-related portfolio of projects; Cost-sharing for small project activities pertaining to water security and sanitation as complementary co-financing for sustainable development at the local level ..

C. GEF Agency information: C.1 Confirm the co-financing amount the GEF agency brings to the project: GEF SGP has a standing expectation of 1:1 co-financing (50% in cash and 50% in kind), thus for this project the expected co-financing would be $40,890,000. UNDP is committed to contribute $2.4 million as co-financing to this project. UNDP will directly contribute to this through its TRAC funds as well as from those that will be fund-raised with other bilateral and multilateral donors, foundations and the private sector. While there is yet no exact amount for the additional co-financing that will be fund-raised in the next four years of OP5, as this will be an on-going effort throughout GEF-5, UNDP has now established a post called “Senior Technical Adviser for Communities, Livelihoods and Markets” supported by a high level advisor. These posts are tasked to develop new initiatives to provide co-financing to GEF SGP. It should also be noted that UNDP Country Offices provide significant in-kind resources in their voluntary membership in the GEF SGP National Steering Committees, and in faciltating access to and helping negotiate with donors additional co-financing for GEF SGP Country Programmes and their projects..

C.2  How does the project fit into the GEF agency’s program (reflected in documents such as UNDAF, CAS, etc.)  and staff capacity in the country to follow up project implementation:

The SGP is consistent with UNDP policies and procedures applying to all countries where UNDP is present and the SGP is implemented. As the programme covers more than 120 countries, individual country-based planning framworks cannot be exhaustively listed. SGP contributes to UNDP's objective of fostering human development, as well as localising the achievement of the Millennium Development Goals (MDGs) agreed upon by the international donor community. As the development network of the United Nations system, UNDP has country offices in the vast majority of countries where SGP is located. In the case of SIDS in the Pacific, the UN Resident Coordinator system, led by UNDP, has put in place a 'Joint Presence' mechanism between UNDP, UNICEF and UNFPA which provides on-the-ground support. SGP country teams are responsible for implementing the programme within their respective countries, as well as to align with and complement the objectives of the UN Development Assistance Framework (UNDAF). At the global level, as captured in the UNDP Strategic Plan 2008-2011, the goal of the 'Local Pillar' of the Environment and Energy Group (EEG) is to strengthen national capacity to manage the environment in a sustainable manner while ensuring adequate protection of the poor. Four key result areas have been identified to achieve this goal: (1) mainstream environmental and energy; (2) catalyze environmental finance; (3) adapt to climate change; and (4) expand access to environmental and energy services for the poor: developing national capacity for service delivery. In addition, the SGP complements numerous other programmes identified in the UNDP Civil Society strategy approved in 2009.

The SGP online database is the tracking tool to capture project information and portfolio results.  The database will be further enhanced during GEF-5 and will feature a streamlined and simplified system of indicators. SGP will track its global environmental benefits and other socio-economic benefits through the mandatory inclusion of online indicators, and incorporate these indicators and targets in Country Programmes’ annual reports. SGP will strengthen its M&E framework to capture global environmental and socio-economic dimensions of projects.  Periodic portfolio reviews will also be systematically conducted to capture results and achievements as measured against indicators and targets.

part iii:  institutional coordination and support

- institutional arrangement:

UNDP continues to implement the GEF Small Grants Programme on behalf of the GEF partnership. The executing partner is UNOPS, and support is received at the country level from UNDP Country Offices. At the national level, the SGP country programme office is a stand-alone entity consisting of the National Coordinator and Programme Assistant, except in a limited number of countries in which there is a National Host Institution (NHI).

- project implementation arrangement:

The global SGP will continue operating in partner countries with the same implementation approach that has proven effective previously. In the Fifth Operational Phase, all aspects of the programme will continue to operate under the strategic direction of the SGP program document, and in accordance with the SGP Operational Guidelines (attached as Annex H to this document). Within each country a National Coordinator (NC), supported by a programme assistant (PA), operates the SGP Country Programme Office on a day-to-day basis. An updated Country Programme Strategy (CPS) in each country will outline the SGP priorities for use of allocated resources, and will articulate in detail how the SGP supports national and GEF strategic priorities. The voluntary National Steering Committee (NSC) of each SGP country programme, composed of government national leaders with majority non-governmental membership to reflect the programme’s mandated focus for CSO capacity building, will provide overall country guidance and provide direct linkages to national policy-making, development planning, knowledge dissemination, and leveraging SGP's catalytic role. The NSC is responsible for selecting and approving projects, and for ensuring their technical and substantive quality with support from a Technical Advisory Group that they can set up with expert volunteers that are willing to be on call. In addition, NSC members are expected to support the country programme in resource mobilization and in mainstreaming SGP lessons learned and successes in other national contexts. NSC members are encouraged to participate in pre-selection project site visits and in project monitoring and evaluation. The technical capacity of the individual NSC members is an important criterion in determining its composition. The primary function of the SGP Country Programme Office and NSC is the identification, review and approval of qualified grant proposals up to $50,000 that support the priorities outlined in the SGP Prodoc and CPS, and which are consistent with the programme’s guidelines. The NC assists CSOs (particularly CBOs and indigenous peoples) in project development and facilitates their direct and facilitative access to resources of SGP and its partners. The SGP Country Programme Office is also responsible for coordinating a country-driven approach for all required management aspects, in particular the work of the NSC, while also facilitating global coherence in programme implementation through its reporting links to the SGP Central Programme Management Team (CPMT). CPMT consists of the SGP Global Manager, SGP Deputy Global Manager, Programme Advisors responsible for matrixed country support and focal area guidance as well as for knowledge management and M&E, and Programme Associates. The CPMT manages th e global programme, and has overall responsibility for monitoring and supervising country programme performance and for the technical and substantive quality of SGP country portfolios. For this purpose, CPMT in consultation with NCs and NSCs, will also develop global guidelines and standards in the development of SGP projects with the objective of ensuring quality yet also facilitating the design of proposals. CPMT also supervises the SGP National Coordinators, and facilitates the start up of new country programmes. CPMT is supported by and coordinates the work of UNOPS which provides execution services. At the global level, strategic guidance is provided to SGP by a GEF SGP Steering Committee chaired by the GEF CEO. All GEF agencies and the GEF NGO Network are members of this Steering Committee. SGP will also continue to be supported by UNDP country offices, and will link with relevant GEF FSPs and MSPs when possible. In addition to the standard SGP grants, the Country Programme Office activities will include strategic efforts in line with the CPS and GEF strategic priorities that will enable aggregation of community-driven impacts for global environmental benefits, local to global strategic portfolio learning and capacity development, dissemination of best practices, or linkage and network building for SGP portfolio grantees. Knowledge management will be an important cross-cutting area of activity in which SGP will apply multiple tools to promote positive information flows. This approach will support the SGP and GEF catalytic role by contributing to replication and upscaling of good practices. Knowledge sharing is also critical in the wider capacity building of other communities and CSOs. SGP provides capacity building through a learning-by-doing approach and successful projects provide good models as well as disseminators/trainers for other community-based projects. Networking for Knowledge sharing facilitates the spread of capcity and further strengthens the sustainability of the programme. SGP grantee networks, local CSO networks, as well as thematically focused CSOs, will be provided appropriate SGP support or will be made participants to SGP-supported activities that build awareness of and skills in advocacy work related to the environmental conventions. SGP NCs and CSO members in the NSCs will facilitate links between national and international CSOs, particularly those that can initiate and sustain the linking process, so that local knowledge and lessons gained from SGP projects also input into the global discussions during convention Conference of the Parties and other international meetings. In all countries SGP will take necessary and appropriate actions to ensure adequate cost-effectiveness ratios with respect to management costs. Country programme operation in GEF-5 will depend on both Core and STAR allocated resources. Core resources alone would not adequately ensure cost-effectiveness ratios in all countries. In the pure STAR countries, 10% of the STAR contribution amount will be used to cover the non-grant component of country programme operation, such as knowledge management, monitoring and evaluation as well as other capacity development activities. The program will take all necessary measures to ensure the visibility of the GEF financing. Such measures will be in accordance with the need to give adequate publicity to the action being implemented as well as to the support from the GEF. Such communications and visibility policy has been presented and emphasized during the regional workshops and through various communications. CPMT will continue working with the country programme to ensure the implementation of such policy. This will include, inter alia, the compulsory use of the GEF logo on all material, publications, leaflets, brochures and newsletters, websites, business cards, signage, vehicles, supplies and equipment, display panels, commemorative plaques, banners, promotional items, photographs, audiovisual productions, public events and visits and information campaigns. Press releases, press conferences and press visits will follow the rules currently in place.

Part IV: Explain the alignment of project design with the original PIF

In principle, the programme design is fully consistent with the originally submitted PIF. One country programme included in the original PIF (Vietnam) has been taken out of this CEO endorsement request, because no endorsement letter has been received to date. On the other hand, one country programme (Argentina) has been included in this PIF following the request by the government and submission of endorsement letter. The responses to the STAP comments and the Council member comments from France received at the PIF stage are attached as Annex B to this document.

PART V: Approval/endorsement by gef operational focal point(s) and gef agency(ies)

- Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): ): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |

B.  GEF agency(ies) certification

This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for CEO endorsement/approval of project.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Mr. Yannick Glemarec |  | February 7, 2012 | Mr. Delfin Ganapin | (646) 781-4383 | Delfin.ganapin@undp.org |

ANNEX A:  PROJECT RESULTS FRAMEWORK

| SGP OP5 Objectives | SGP OP5 Outcomes | SGP OP5 Results Indicators | OP5 Target | Sources of Verification | Assumptions |
| --- | --- | --- | --- | --- | --- |
| SGP OP5 Immediate Objective 1: Improve sustainability of protected areas and indigenous and community conservation areas through community-based actions | SGP BD Outcome 1.1: Improved community-level actions and practices, and reduced negative impacts on biodiversity resources in and around protected areas, and indigenous and community conservation areas Category II Step-up: Good practices replicated and scaled up outside SGP supported areas, as appropriate SGP BD Outcome 1.2: Benefits generated at the community level from conservation of biodiversity in and around protected areas and indigenous and community conservation areas Category II Step-up: Sustainable financial mechanisms for benefit generation identified and piloted, as appropriate SGP BD Outcome 1.3: Increased recognition and integration of indigenous and community conservation areas in national protected area systems Category II Step-up: Information about recognition of indigenous and community conservation areas within national level protected area systems shared through an established network, as appropriate SGP BD Outcome 1.4: Increased understanding and awareness at the community-level of the importance and value of biodiversity Category II Step-up: Environmental education programs formally integrated in school curricula, as appropriate | Number and hectares of ICCAs and other PAs positively influenced through SGP support Number of community members with improved livelihoods related to benefits from protected areas Number of significant species with maintained or improved conservation status Number and hectares of significant ecosystems with maintained or improved conservation status | 110 ICCAs and PAs positively influenced through SGP support 3,000,000 hectares of ICCAs and PAs positively influenced through SGP support 45,000 community members with improved livelihoods related to benefits from ICCAs and PAs 110 significant species benefited 60 significant ecosystems with conservation aware communities resulting in their maintained or improved conservation status 55,000 hectares of significant ecosystems with maintained or improved conservation status | GEF SGP database, project reports and monitoring visits SGP case studies SGP grantee data from innovative monitoring approaches | Governments and international agencies commit to CBD obligations regarding local and indigenous populations |
| SGP OP5 Immediate Objective 2: Mainstream biodiversity conservation and sustainable use into production landscapes, seascapes and sectors through community initiatives and actions | SGP BD Outcome 2.1: Improved community-level sustainable use of biodiversity in production landscapes / seascapes through community-based initiatives, frameworks and market mechanisms, including recognized environmental standards that incorporate biodiversity considerations Category II Step-up: Market mechanisms and standards replicated and scaled-up, as appropriate SGP BD Outcome 2.2: Increased understanding and awareness of sustainable use of biodiversity Category II Step-up: Environmental education programs formally integrated in school curricula, as appropriate | Hectares of production landscapes / seascapes under improved sustainable use practices, leading, where possible, to certification through recognized environmental standards that incorporate biodiversity considerations (supported by SGP) Number of significant species with maintained or improved conservation status Number and hectares of significant ecosystems with maintained or improved conservation status | 55,000 hectares of production landscapes / seascapes under improved sustainable use practices, leading, where possible, to certification through recognized environmental standards that incorporate biodiversity considerations (supported by SGP) 110 significant species with maintained or improved conservation status 60 significant ecosystems with communities adopting sustainable use resulting in maintained or improved conservation status 55,000 hectares of significant ecosystems with maintained or improved conservation status | GEF SGP database, project reports and monitoring visits | Market differentiation of value-added labels sufficiently “scale-sensitive” to meet the needs of small producers |
| SGP OP5 Immediate Objective 3: Promote the demonstration, development and transfer of low carbon technologies at the community level | SGP CC Outcome 3.1: Innovative low-GHG technologies deployed and successfully demonstrated at the community level Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate SGP CC Outcome 3.2: GHG emissions avoided | Number of countries with demonstrations addressing community-level barriers to deployment of low-GHG technologies Number of national or international partners or agencies are aware of SGP practices and lessons | 16 countries with demonstrations addressing community-level barriers to deployment of low-GHG technologies At least 30 national or international partners or agencies are aware of SGP practices and lessons | GEF SGP database, project reports and monitoring visits SGP case studies | Progress will continue for complimentary initiatives by GEF and other development agencies to removing market barriers and improving energy access policies particularly at the local level. |
| SGP OP5 Immediate Objective 4: Promote and support energy efficient, low carbon transport at the community level | SGP CC Outcome 4.1: Low-GHG transport options demonstrated at the community level Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate SGP CC Outcome 4.2: Increased investment in community-level energy efficient, low-GHG transport systems SGP CC Outcome 4.3: GHG emissions avoided | Number of countries where community-level low-GHG transport options have been demonstrated Number of governments having been influenced by SGP demonstration practices | At least 6 countries with community-level low-GHG transportation demonstrations At least 3 governments (local or national) having been influenced in policy development and implementation | GEF SGP database, project reports and monitoring visits | Progress will continue for complimentary initiatives by GEF and other development agencies to removing market barriers and improving policies supporting low-GHG transportation, particularly at the local level. |
| SGP OP5 Immediate Objective 5: Support the conservation and enhancement of carbon stocks through sustainable management and climate proofing of land use, land use change and forestry | SGP CC Outcome 5.1: Sustainable land use, land use change, and forestry management and climate proofing practices adopted at the community level for forest and non-forest land-use types Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate SGP CC Outcome 5.2: Restoration and enhancement of carbon stocks in forests and non-forest lands, including peatland Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate SGP CC Outcome 5.3: GHG emissions avoided | Hectares under improved sustainable land management and climate proofing practices Hectares of forests and non-forest lands with restoration and enhancement initiated | 27,000 hectares under improved sustainable land management and climate proofing practices Restoration and enhancement of 15,000 hectares of forests and non-forest lands initiated | GEF SGP database, project reports and monitoring visits SGP case studies | Change is possible on the ground at the community level whether or not national and international policy measures are in place |
| SGP OP5 Immediate Objective 6: Maintain or improve flow of agro-ecosystem and forest ecosystem services to sustain livelihoods of local communities | SGP LD Outcome 6.1: Improved community-level actions and practices, and reduced negative impacts on agro-, and forest ecosystems and ecosystem services demonstrated to sustain ecosystem functionality Category II Step-up: Analysis of economic value of ecosystem services in target areas, as appropriate SGP LD Outcome 6.2: Community-based models of sustainable forestry management developed, and tested, linked to carbon sequestration for possible upscaling and replication where appropriate, to reduce GHG emissions from deforestation and forest degradation and enhance carbon sinks from land use, land use change, and forestry activities Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate | Hectares under improved agricultural, land and water management practices (by management practice) Number of national and international agencies or partners are aware of successful SGP demonstrations and innovative approaches Number of national/local governments or international policy making processes with SGP influence | 27,000 hectares under improved agricultural, land and water management practices (by management practice) At least 16 national or international agencies/partners have learned of SGP demonstrations and innovative approaches At least 3 policy-making bodies (governments or international agencies) having been influenced by successful SGP demonstration practices | GEF SGP database, project reports and monitoring visits SGP case studies | Government policy is in place and supportive of community-level sustainable land management practices |
| SGP OP5 Immediate Objective 7: Reduce pressures at community level from competing land uses (in the wider landscapes) | SGP LD Outcome 7.1: Improved community-level actions and practices, and reduced negative impacts in land use frontiers of agro-ecosystems and forest ecosystems (rural/urban, agriculture/forest) Category II Step-up: Partnerships with private sector, as appropriate | Number of community members with improved actions and practices that reduce negative impacts on land uses | At least 16,000community members having improved actions and practices that have reduced pressure on land uses | GEF SGP database, project reports and monitoring visits | Government policy is in place and supportive of community-level sustainable land management practices |
| SGP OP5 Immediate Objective 8: Support transboundary water body management with community-based initiatives | SGP IW Outcome 8.1: Effective and climate resilient community-based actions and practices supporting implementation of SAP regional priority actions demonstrated Category II Step-up: Scaling-up and replication of good practices and lessons learned, as appropriate SGP IW Outcome 8.2: Synergistic partnerships developed between SGP stakeholders and transboundary water management institutions and structures supporting implementation of SAP regional priority actions Category II Step-up: Scaling-up and replication of good practices and lessons learned, as appropriate | Number of SAPs to which SGP is providing implementation support Number of regional transboundary water management processes to which SGP is contributing good practices and lessons | 3 SAPs for which SGP is supporting on the ground implementation of regional priority actions 3 regional transboundary water management processes to which SGP is contributing good practices and lessons | GEF SGP database, project reports and monitoring visits | Regional water body management organizations are institutionally willing and able to engage with community-level stakeholders |
| SGP OP5 Immediate Objective 9: Promote and support phase out of POPs and chemicals of global concern at community level | SGP CH Outcome 9.1: Improved community-level initiatives and actions to prevent, reduce and phase out POPs, harmful chemicals and other pollutants, manage contaminated sites in an environmentally sound manner, and mitigate environmental contamination Category II Step-up: Scaling-up and replication of good practices and lessons learned, as appropriate | Tons of POPs waste avoided from burning Tons of obsolete pesticides disposed of appropriately Number of countries where SGP is contributing to the implementation of national plans and policies to address POPs, harmful chemicals and other pollutants | 50 tons of solid waste avoided from burning 10 tons of obsolete pesticides disposed of appropriately 3 countries where SGP is contributing to the implementation of national plans and policies to address POPs, harmful chemicals and other pollutants | GEF SGP database, project reports and monitoring visits | There are adequate opportunities for community-level stakeholders to address POPs, harmful chemicals, and other pollutants Community-level stakeholders develop the awareness and capacity to proactively address POPs, harmful chemicals and other pollutants |
| SGP OP5 Immediate Objective 10: Enhance and strengthen capacities of CSOs (particularly community-based organizations and those of indigenous peoples) to engage in consultative processes, apply knowledge management to ensure adequate information flows, implement convention guidelines, and monitor and evaluate environmental impacts and trends | SGP CD Outcome 10.1: Active participation of NSCs and NFGs in GEF focal areas at the national level SGP CD Outcome 10.2: Improved information flows to/from CBOs and CSOs in SGP countries regarding good practices and lessons learned, and application of such practices SGP CD Outcome 10.3: Increased public awareness and education at the community-level regarding global environmental issues SGP CD Outcome 10.4: Capacity of CBOs and CSOs strengthened to support implementation of global conventions SGP CD Outcome 10.5: Increased application of community-based environmental monitoring SGP CD Outcome 10.6: Evaluation of SGP projects and programs against expected results strengthened, including increased capacity of CBOs and CSOs to apply relevant evaluation methodologies | Number of SGP representatives participating in national GEF coordination meetings Quantity and quality of SGP knowledge base, and use of knowledge base; Quantity and quality of contributions to knowledge fairs, conferences, publications and research. Number of demonstrations and piloted examples of community-based environmental monitoring systems used in SGP projects Quantity and quality of evaluation documentation of expected project results, and unexpected effects Number of CBOs and CSOs demonstrating understanding of the role of evaluation through application of relevant evaluation methodologies | SGP National Steering Committees established and National Focal Groups in 16 countries actively participating in GEF National coordination mechanisms Knowledge platform established to share lessons learned among CBOs and CSOs across 100 SGP countries Capacities of 5000 CSOs and CBOs strengthened At least 85% of projects incorporate M&E activities in their design At least 70% of projects specify sufficient indicators which are covered in completion reports | GEF SGP database, project reports and monitoring visits SGP case studies | National coordination mechanisms are open to input and participation from community-level stakeholders |
| Cross-Cutting Results: Livelihoods and Gender | SGP’s Results Framework for OP5, as approved by the SGP Steering Committee, does not include specific objectives on livelihoods and gender. Nonetheless, SGP does produce positive results in these areas, which contribute to the overall achievement of Global Environmental Benefits through sustainable development. Generally, SGP seeks to improve livelihoods through increasing local benefits generated from environmental resources, and mainstream gender considerations in community-based environmental initiatives. | Percentage of projects that include gender analysis or incorporate gender relevant elements in a positive manner Percentage of projects with appropriate gender balance of participants and target beneficiaries Percentage of projects that include socioeconomic analysis Number of community members with sustained livelihood improvement resulting from SGP support | 100% of projects that include gender analysis or incorporate gender relevant elements in a positive manner (baseline TBD in OP5) 100% of projects with appropriate gender balance of participants and target beneficiaries (baseline TBD in OP5) 100% of projects that include socioeconomic analysis (baseline TBD in OP5) 100,000 community members with sustained livelihood improvement resulting from SGP support | GEF SGP database, project reports and monitoring visits SGP case studies | All SGP projects have sufficient scope to include gender mainstreaming |

ANNEX A.1.:	GEF SGP PROJECT PROPOSAL TEMPLATE

1. TABLE OF CONTENTS

2. COVER PAGE

Country:………………………..……………..Submission date…………………………………….

Project No.	________________ (For SGP Official Use. Do not write anything here)

Project Title:	_________________________________________________________________

(The title must capture the essence of project and aligns to GEF focal areas)

APPLICANT

Name of Organization: ___________________________________________________________________

Year established _________________ Number of members ______________________________________

Number of projects implemented___________________________________________________________

Mailing Address:	__________________________Physical Address:_______________________________

Telephone:		________________________________________________________________

Fax: 			___________________________ E-Mail: ______________________________

Principal Officer:	______________________________________________________ (Name and Position)

Project Contact/Manager: 	_______________________________________________ (Name and Position)

PROJECT

GEF SGP Classification

| Thematic/Focal Area (Tick one) |  |  | Project Category (Tick one) |  |
| --- | --- | --- | --- | --- |
|  | Conservation of Biodiversity |  |  | Demonstration Project |
|  | Climate Change |  |  | Capacity Development Project |
|  | Land Degradation and Sustainable Forest Management |  |  | Applied Research/Policy Analysis |
|  | International Waters |  |  | Information/Networking/Policy Dialogue |
|  | Chemicals (POPs) |  |  |  |
|  | Capacity development |  |  |  |

Proposed Start Date:_______________________   Expected Project Duration:______________________

FINANCES

Total GEF SGP Request:	[Local currency] _____________			  [US$ _______________]

Total from Other Sources:	[Local currency] _____________			  [US$ _______________]

Total project cost	:	[Local currency] ______________			  [US$_______________]

UN rate of exchange___________________________ (For SGP Official Use. Do not write anything here)

3. PROPOSAL

SECTION A: PROJECT RATIONALE AND APPROACH

1.1. Project Summary

1.2. Organizational Background and Capacity to implement the Project					1.3. Project Objectives and Expected Results

1.4. Description of Project Activities

1.5. Implementation Plan and Time-frame

1.6. Plan to Ensure Community Participation

1.7. Knowledge Management

1.8. Gender Mainstreaming

1.9. Communication of Results and Replication

SECTION B: PROJECT RISKS, MONITORING & EVALUATION

2.1. Risks to Successful Implementation

2.2. Monitoring, Evaluation Plan and Indicators

2.3. Sustainability of Results Achieved

SECTION C: PROJECT BUDGET

3.1 Financial Details

3.2 Projected Expenditures

3.3 Bank Details

ANNEX 1: INDICATORS

A. GEF SGP Project Indicators

B. SGP CBA Project Indicators

GEF SGP PROJECT PROPOSAL GUIDELINES

# GENERAL REQUIREMENTS

The Project Proposal should include the standard cover sheet, a one-page table of contents and should not exceed 15 pages of text (including any charts or diagrams).  The Proposal should be submitted in typed form.

Additional attachments (not more than 10 pages) may be submitted, including documents certifying the status of the organization, endorsements of the proposed project, funding commitments or other indicators of participation and support from other institutions, and evidence of community support and participation.

Please ensure that the project proposal and all attachments are legible. All supporting documents (attachments) should also have the name of the project on them. Submit one original copy of the Proposal (soft and hard copy) to the National Coordinator, GEF Small Grants Programme, [Full address of the SGP Offices]. Keep a copy of your proposal for your own records as the one you submit will not be returned.

PREPARING YOUR PROPOSAL

In preparing a Project Proposal, please follow the major points of the outline set forth below. Ensure that all bullet points included in the outline are addressed, as these cover the major issues which the National Steering Committee (NSC) will consider in reviewing the Proposal. It is suggested that the proposal does not exceed the total number of pages stipulated.

# TABLE OF CONTENTS

The table of contents should be prepared in a logical and consistent manner and following the format presented.

- COVER PAGE

The cover page provides an important summary of the project.  Each project will be assigned a project number by GEF SGP as appropriate to the country. The cover page should indicate the duration and start date of the project, provide the applicant’s details, identify the GEF focal area the proposal is targeting, , and include information on project finances specifying total requested support from the GEF and co-financing available and/or expected. The co-financing can be in kind, cash or parallel in nature.  The UN rate of exchange at the time of proposal submission by the grantee should be logged in by the National Coordinator (NC) regardless of the fact that projects may be evaluated and approved by the NSC at a later date.

- PROPOSAL

The proposal includes the following main sections: Project Rationale and Approach (Section A), Project Risks, Monitoring & Evaluation (Section B) and Project Budget (Section C).

# SECTION A: PROJECT RATIONALE AND APPROACH

This section provides the rationale and background of the project, as well as the proposed approach.

## 1.1 Project Summary

The Project Summary should describe the project context, including the key environmental problem to be addressed, and the proposed approach, including the rationale/justification for the project. This section should describe the project location, a profile of the project sites, as well as the target community (ies) involved. The relevance of the project to the GEF/SGP Country Programme Strategy should also be presented.

## 1.2 Organizational Background and Capacity to implement the project

This section should demonstrate that the proposing organization has the experience, capacity, and commitment to successfully implement the proposed project, or, is prepared to work with SGP to build its capacity to undertake the project. The issues to be covered in this section include:

- Nature of the proposing organization – is it an informal group of interested parties, a community-based organization (CBO), national or sub-national NGO, research or training institution

- Purpose and core activities of the proposing organization/group

- Organizational approach for project implementation, i.e. how does the organization or group intend to deliver the project?

- Length of existence and project management experience if any

- Organizational structure, governance and administrative framework: provide the number of paid staff members if it is a well constituted organization

- If relevant, state membership and affiliation to associations or umbrella groupings

- Provide an indication of the legal status. If none, provide an elaboration of its nature of existence.

- Target population group (indicate relevant community groups, women, indigenous peoples, youth, etc.)

- If the organization has been in existence before, the proponents should explicitly describe previous experience relevant to the proposed project including, as relevant: projects addressing problems of biodiversity loss; climate change mitigation and/or climate-proofing; land degradation/sustainable forest management; pollution of international waters; chemicals management; OR experience with projects that focus on environment and natural resources management and sustainable development at community level.

## 1.3 Project Objectives and Expected Results

This section can be laid out in a matrix form and should contain a clear and specific statement of what the proposed project will accomplish. Preferably this should follow a logical framework. Among the issues to address include:

- The problem statement or challenge the project intends to address

- The primary objective and specific objectives of the proposed project

- The full description of the rationale (justification) for the project. The rationale should indicate the importance of the proposed project to the GEF Small Grants Programme in terms of contributing to its overall and or specific focal area objective(s). It should also reflect the relationship of the project to other relevant programmes such as local, district or national government programmes, other GEF and UNDP projects, multilateral and bilateral aid agency projects, and other community-based, CSO, and/or private sector activities. This will ensure that the intervention is not a standalone activity.

- The specific results or outcomes that the project will produce. The expected results are the measurable changes which will have occurred by the end of the project as a result of the planned intervention (e.g. land area under forest cover increasing because of tree planting and promotion of natural regeneration of vegetation etc).

## 1.4 Description of Project Activities

This section, to be included in a logical framework, should describe what will actually be done to produce the expected results and accomplish the project's objectives. There should be a clear and direct linkage between the activities and the expected results or outcomes. (The proponent must ensure that the activities are a means to achieving the results). Note that weakness in this area may be a major reason for failure to receive funding. Activity descriptions should be as specific as possible, identifying what will be done, who will do it, when it will be done (beginning, duration, completion), and where it will be done. In describing the activities, an indication should be made regarding the organizations and individuals involved in or benefiting from the activity.

## 1.5 Implementation Plan and Time Frame

This section may be presented in graphical (table) form and can be attached as an annex. It should indicate the sequence of all major activities and implementation milestones, including targeted beginning and ending dates for each step. Provide as much detail as possible at this stage. The Implementation Plan should show a logical flow of steps, indicating that all the things that must happen have been carefully thought through from the current to the end of project situation. Please include in the Implementation Plan the required reports, project reviews and evaluation activities.

## Plan to Ensure Community Participation

## Please describe how the stakeholder communities were involved in Project planning and design and will be involved in: i) Project implementation and ii) Project monitoring and evaluation. This information will serve a basis for assessing and understanding community participation and ownership.

  - Knowledge Management

Please describe how you plan to capture, share and disseminate the knowledge, lessons learned and good practices gained through the implementation of the project.

  - Gender Mainstreaming

Please describe how the project takes into consideration the roles and needs of men and women (with a focus on the needs of women), and how this would be reflected in the results and benefits of the project.

  - Communication and Replication of Project Results

Please describe how you would communicate the goals, activities and results of the project with the community members, other community-based organizations and other key stakeholders. If the project requires awareness-raising at the local level, please describe the plan/activities you would use to achieve the target results and ensure replication of project results.

SECTION B:

PROJECT RISKS, MONITORING & EVALUATION

This section should detail the risks, issues, assumptions, sustainability strategies and also describe the project work plan and monitoring during the implementation. It should provide a full description of the issues outlined below:

## 2.0	Risks to Successful Implementation

Please identify and list the major risk factors that could result in the project not producing the expected results. These should include both internal factors (for example, the technology involved fails to work as projected) and external factors (for example, significant currency fluctuations resulting into changes in the resources of the project). Please also propose risk mitigation measures to address the potential risks.

Please include in this section the key assumptions on which the project plan is based (for example, government and environmental policy remaining stable) which are anticipated in project planning, and on which the feasibility of the project depends.

## 2.1	Monitoring, Evaluation Plan and Indicators

This section should be laid out as per table 1 below. It should contain an explanation of the plan for monitoring and evaluating the project, both during its implementation (field activities) and at completion (review and analysis).

| Brief description of General Objective of Project: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Brief Description of Specific Objective No 1: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| List the activities necessary to fulfil this objective. Indicate who is responsible for each activity and an indicator of activity accomplishment. |  |  | Duration of Activity in Months (or Quarters) |  |  |  |  |  |  |  |  |  |  |  |
| Activity | Responsible Party | Indicator | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| 1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Table 1: Activity Planning

Project monitoring schedule

The project should be monitored according to a planned schedule, in line with the milestones identified in the Implementation Plan and Time Frame (section 1.5 above).

Among the key issues to be addressed as part of M&E are:

- How will the performance of the project be tracked in terms of achievement of the steps and milestones set forth in the Implementation Plan;

- How will the impact of the project be assessed in terms of achieving the project's objective(s);

- How will the mid-course correction and adjustment of the project design and plans be facilitated on the basis of feedback received;

- How will the participation of community members in the project monitoring and evaluation processes be achieved.

Project indicators

Please propose specific and measurable indicators which help capture the achievement of project results. These indicators will form the basis for monitoring and evaluation. These indicators should be aligned with the SGP Country Programme Strategy (CPS) and may be refined in consultation with the NC and or NSC. The indicator set for the project should draw upon the set of SGP project level indicators (see Annex 1), but can also be enriched by other project-specific and or national indicators that are appropriate for the project to track. Please identify at least one biophysical indicator pertaining to the relevant GEF focal area (or focal areas, if the project has a secondary focal area) and one indicator from each of the categories of ‘capacity development, policy influence & innovation’; ‘livelihoods & sustainable development, community based adaptation and empowerment’ indicators provided (see Annex 1).

## 2.2	Sustainability of Results Achieved

Sustainability is a critical aspect in all the GEF SGP funded projects. The proposal should outline the steps to be taken before, during, and at project completion to ensure that once all the SGP funds have been disbursed, the project impact will continue for many years thereafter.

The funds provided by SGP are primarily seed funds, designed to give the project a significant start. However, project proponents should envision the project three or even five years after SGP funds have been utilized, and consider the factors that could contribute to the success and continued impact of their project, and address them accordingly.

# SECTION C: PROJECT BUDGET

The Project Budget is an important part of every GEF SGP project proposal and must be completed prior to consideration of a proposed project for funding. Once a project has been approved for funding, the budget information becomes part of the binding Memorandum of Agreement (MOA) between the GEF SGP and the proposing organization.

The development and management of a realistic budget is an important part of developing and implementing a successful GEF project. Careful attention to issues of financial management and integrity will enhance the effectiveness and impact of the project. In keeping with the role of the GEF SGP as a support mechanism for community-level initiatives, every effort has been made to keep financial management requirements as straightforward and non-burdensome as possible. The following important principles should be kept in mind in preparing a project budget:

- Include only costs which directly relate to efficiently carrying out the activities and producing the objectives which are set forth in the proposal. Other associated costs should be funded from other sources.

- The budget should be realistic. Find out what planned activities will actually cost, and do not assume that you will be able to make do for less.

- The budget should include all costs associated with managing and administering the project. In particular, include the cost of monitoring and evaluation.

- "Indirect costs" or administrative overhead costs such as staff salaries and office rent are not funded by the GEF SGP. These therefore should not be part of the funding request.

- GEF SGP funds should be spent according to the agreed budget.

- All relevant, financial records should be made available. These may be independently audited, and may become public information.

- The budget line items are general categories intended to assist in thinking through where money will be spent. If a planned expenditure does not appear to fit in any of the standard line item categories, list the item under other costs, and state what the money is to be used for.

- The figures contained in the Budget should concur with those on the Proposal Cover page.

- GEF SGP grant requests should not exceed fifty thousand United States Dollars (US$50,000) per project, and per Operational Phase.

3.1 Financial Details

- Project Funding Summary

The proponent should provide a summary on how the project will be funded. This should be laid out in a matrix form as in table 2 below.

Table 2: Project funding summary

| Funding Source | Funding Plan, [local currency] |  | Total [local currency] | Total US$ |
| --- | --- | --- | --- | --- |
|  | Year 1 | Year 2 |  |  |
| a. GEF SGP |  |  |  |  |
| b. Community |  |  |  |  |
| c. Proposing Organization |  |  |  |  |
| d. Other co-financiers |  |  |  |  |
| Total Project Cost |  |  |  |  |

- Community Contribution

All cost-sharing contributions (cash and in-kind) should be itemized. In particular, the in-kind contributions should be estimated using the SGP methodology/guidelines and summarized as in table 3 below. This should include sources and nature of the contribution (e.g. Youth Organization contributing labour, land, cash, etc). Please indicate whether the contribution is already committed or just a projection.

Table 3: Community Contributions

| Sources of Community Contribution | Type (cash/in kind) | Committed or Projected?* | Value, in local currency |
| --- | --- | --- | --- |
| 1. |  |  |  |
| 2. |  |  |  |
| Total |  |  |  |

- Proposing Organization Contribution

The GEF SGP applies the principle of co-financing the target activities between the relevant partners in the project. It is therefore important that proposing organizations make some contribution towards the operational and programmatic costs of the project. This can be laid out in a simple matrix as in table 4 below and should capture the different project partners and proponents.

Table 4: Proposing organizations contributions

| Sources of Contribution | Type | Committed or Projected? | Value, local currency |
| --- | --- | --- | --- |
| 1. |  |  |  |
| 2. |  |  |  |
| Total |  |  |  |

3.2 Projected Expenditures

This section will detail expenditure categories and how the funds will be dispensed over the project period. Typically, SGP projects generally do not exceed 2 years, however, the exact length of the period can be determined in consultation with National Coordinator and NSC based on project objectives. The anticipated expenditures in the project must be captured as below with clear line items.

Table 5: Projected expenditures

| Expenditure Category | Year 1, [local currency] | Year 2, [local currency | Total, [local currency | US$ | % Total |
| --- | --- | --- | --- | --- | --- |
| 1. Personnel / Labour |  |  |  |  |  |
| 2. Equipment / Materials |  |  |  |  |  |
| 3. Training / Seminars / Travel Workshops |  |  |  |  |  |
| 4. Contracts |  |  |  |  |  |
| 7. Other support requested |  |  |  |  |  |
| Total Project Cost |  |  |  |  |  |

3.3 Bank Details

Please provide the bank account information where project funds are proposed to be received.

When the proponent is a well established organization, which may have multiple bank accounts, it is necessary to indicate which bank account will be used to receive SGP funds, and how these funds can be tracked and accounted for.

When the proponent is a new community group, details should be provided on how the book keeping will be done and if necessary include a capacity building element within the project proposal that will enable the proponent to operate financially.  If the community group is successful in receiving an SGP grant, a separate bank account would have to be opened for handling of grant funds. This should be done in the shortest time frame possible.

ANNEX 1: INDICATORS

A.  GEF SGP Project Indicators

GEF SGP project indicators in the focal areas of biodiversity, climate change, land degradation and sustainable forest management, international waters, and chemicals are presented below. Proponents are advised to select relevant focal area indicators from the table below. In addition, proponents (if necessary in consultation with the NC), should identify and include indicators within the areas of impact pertaining to “Capacity Development, Policy Influence & Innovation”, “Livelihoods & Sustainable Development, Community Based Adaptation and Empowerment”.

| GEF SGP OP5 results indicators |  |
| --- | --- |
| Biodiversity (BD) |  |
| BD1 | - Hectares of indigenous and community conserved areas (ICCAs) influenced - Hectares of protected areas influenced - Hectares of significant ecosystems with improved conservation status |
| BD2 | - Hectares of production landscapes / seascapes applying sustainable use practices - Number of significant species with maintained or improved conservation status - Total value of biodiversity products/ecosystem services produced (US dollar equivalent) |
| Climate Change (CC) |  |
| CCM1 | - Tonnes of CO2 avoided by implementing low carbon technologies: - Renewable energy measures (please specify) - Energy efficiency measures (please specify) - Other (please specify) - Number of community members demonstrating or deploying low-GHG technologies - Total value of energy or technology services provided (US dollar equivalent) |
| CCM4 | - Tonnes of CO2 avoided by implementing low carbon technologies: - Low carbon transport practices (please specify) - Total value of transport services provided (US dollar equivalent) |
| CCM5 | - Hectares of land under improved land use and climate proofing practices - Tonnes of CO2 avoided through improved land use and climate proofing practices |
| Land degradation (LD) & Sustainable Forest Management (SFM) |  |
| LD1 | - Hectares of land applying sustainable forest, agricultural and water management practices - Hectares of degraded land restored and rehabilitated |
| LD3 | - Number of communities demonstrating sustainable land and forest management practices |
| International Waters (IW) |  |
| IW | - Hectares of river/lake basins applying sustainable management practices and contributing to implementation of SAPs - Hectares of marine/coastal areas or fishing grounds managed sustainably - Tonnes of land-based pollution avoided |
| Chemicals (POPs) |  |
| POPS | - Tons of solid waste prevented from burning by alternative disposal - Kilograms of obsolete pesticides disposed of appropriately - Kilograms of harmful chemicals avoided from utilization or release |
| Capacity Development, Policy and Innovation (all focal areas) |  |
| CD | - Number of consultative mechanisms established for Rio convention frameworks (please specify) - Number of community-based monitoring systems demonstrated (please specify) - Number of new technologies developed /applied (please specify) - Number of local or regional policies influenced (level of influence 0 – 1 – 2 – 3 – 4 – 5) - Number of national policies influenced (level of influence 0 – 1 – 2 – 3 – 4 – 5) - Number of people trained on: project development, monitoring, evaluation etc. (to be specified according to type of training) |
| Livelihoods, Sustainable Development, and Empowerment (all focal areas) |  |
| Cross-cutting | Livelihoods & Sustainable Development: - Number of participating community members (gender disaggregated) (Note: mandatory for all projects) - Number of days of food shortage reduced - Number of increased student days participating in schools - Number of households who get access to clean drinking water - Increase in purchasing power by reduced spending, increased income, and/or other means (US dollar equivalent) - Total value of investments (e.g. infrastructure, equipment, supplies) in US Dollars (Note: estimated economic impact of investments to be determined by multiplying infrastructure investments by 5, all others by 3). Empowerment: - Number of NGOs/CBOs formed or registered - Number of indigenous peoples directly supported - Number of women-led projects supported - Number of quality standards/labels achieved or innovative financial mechanisms put in place |

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

| REVIEW COMMENTS | RESPONSE |
| --- | --- |
| Comments from STAP (received 23 September 2011) |  |
| Attention to the GEF Focal Area 'learning objectives' is highly relevant to the selection of individual small grant projects. In particular, this allows for additional opportunities to further evaluate the effectiveness of common approaches such as product certification, payments for ecosystem services, and community forest management among others. | Alignment to the “learning objectives” of the GEF Focal Areas will be further fostered in GEF SGP OP5 through an enhanced focus on capacity development, which includes the enhancement of community methodologies and practices, as a key objective in GEF-5. Aside from grants targeted for capacity development, each GEF SGP project is inherently capacity development through a “learning by doing” approach. In this approach, community relevant and appropriate methodologies and practices are tested and modeled. GEF SGP has already piloted product certification of timber and honey as well as community carbon accounting as a basic step towards payments of ecosystem services particularly linked to REDD+ and plans to support more of these. Strengthen approaches in community forest management will also come about in the increased support targeting Indigenous and Community Conserved Areas (ICCAs). The portfolio of GEF SGP projects are then reviewed for “best practices” and proven methodologies to produce technical guidance notes and training materials to enhance the effectiveness of GEF SGP projects, and of other projects through its KM sharing networks. . For example GEF SGP has captured knowledge from different regions to produce sustainable biodiversity products catalogues that show how biodiversity resources become commercially valuable products and also help link small producers to markets. Similarly lessons are being exchanged between a number of projects focusing on reduced emissions in dairy farms. Past projects will be identified and planned future projects will be encouraged to form the basis of planned manuals on Community Carbon Accounting and Community-Based Adaptation that is focused on the ecosystem approach. |
| STAP understands that the GEF SGP tends to be treated very much as a stand-alone project in each UNDP Country Office, often weakly integrated with other national and local-level multi-focal area initiatives. As such, STAP recommends attention be given as to how the GEF SGP will be integrated institutionally in-country so that the GEF SGP's outputs support multiple objectives, influence other activities, and where possible are sustained over the long term. | GEF SGP has several mechanisms in place to ensure integration and coordination of its Country Programme portfolios with UNDP Country offices and other national and sectoral initiatives: 1) the country programme strategy (CPS) development involves multi-stakeholder consultation and discussions, and linkages, partnerships and synergies with country-level actors and programmes are explored during this process to ensure greater synergy and portfolio effectiveness; 2) Each GEF SGP cCountry Programme is governed by a multi-stakeholder National Steering Committee (NSC) that includes government officials, UNDP country office representative, NGOs, academics and other key stakeholders from different sectors. Members of the NSC bring their knowledge and experience to guide and advise on project development and implementation, ensuring linkages and helping to establish partnerships with other national and focal area initiatives; 3) Linkages with other ongoing national processes, such as NAPAs, NAPs, and NIPs (see section A.2) are systematically explored with NCs, NSC members or GEF SGP grantees often involved as members in national dialogues or committees; 4) In GEF SGP OP5, links with Convention Focal Points will be further strengthened with periodic meetings and briefings. In many countries, convention focal points often serve as members of GEF SGP NSCs. The GEF SGP Operational Guidelines now provides for the formation of Technical Advisory Groups to further provide participation for representatives of Convention Focal Points in the technical review of GEF SGP project proposals; 5) GEF SGP National Coordinators have joined as members of national committees in GEF National Portfolio Formulation Exercises. GEF SGP has also served as a delivery mechanism for key national and regional projects and programmes such as the Nile Transboundary Environmental Action Project, the South China Sea project and the EU Tropical Forest programmme in South East Asia. In OP5, opportunities will continue to be explored for GEF SGP to serve as an effective grassroots delivery mechanism for GEF and other donor programmes addressing environment and sustainable development objectives. Through such collaboration synergies and linkages will be strengthened between GEF SGP and other national and focal area initiatives. |
| Finally, STAP would recommend that the contribution of these projects to the development of human and institutional capital and improved knowledge management at national level be further elaborated wherever possible. The contribution to GEF learning objectives, noted above, is one such step. However, these projects are uniquely placed to improve learning and knowledge management at the national level, and contribute directly to our understanding of the delivery of global environmental benefits and sustainable development objectives. | GEF SGP works with poor and vulnerable people and communities to take action to address global environmental challenges. In the process of developing, implementing and monitoring and evaluating these projects, communities are empowered organize themselves to take action while the knowledge and capacity of these communities is strengthened to deal with global environmental issues, and to pilot and adopt sustainable approaches and techniques. Generating and sharing knowledge is an important goal of the GEF SGP as already stated above. All projects and country programmes will incorporate a significant knowledge generation and sharing component as part of project design and in the update of the OP5 country programme strategy. Each grantee will be expected to develop and submit knowledge products, including a final project report summarizing project activities and achievements that can be included in the GEF SGP global database. The GEF SGP database will be improved to reflect the growth and expansion of the programme, so that it will be able to accommodate more sophisticated monitoring and evaluation indicators and tools as well as knowledge sharing and exchange mechanisms. GEF SGP will help maximize global learning through the sharing of experiences and best practices, both in person through horizontal grantee exchanges and national workshops, as well as virtually through the online system. Based on these experiences, the programme will promote the adoption and replication of these best practices when designing new projects across similar thematic areas. It should be noted that in the sharing of these experiences, as is the practice in the development of GEF SGP knowledge products, successes of communities, special sectors such as indigenous peoples, women, and youth, and civil society organizations in developing enhanced organizational skills, awareness of, networking and advocacy for the environment, and participation in policy consultations and development planning have always been elaborated and highlighted. In GEF SGP OP5, the organization of “Knowledge and Best Practice Fairs” which would highlight these successes at the national level is a target activity for each GEF SGP Country Programme. |
| Comments from France (received 21 November 2011) |  |
| First we would like to stress that the names of these sixteen countries are unclear as the project detail only mention thirteen of them: Cuba, Egypt, Ethiopia, Indonesia, Iran, Kazakhstan, Madagascar, Malaysia, Peru, Papua New Guinea, Turkey, Tanzania, South Africa.” Which are the remaining three countries? | This CEO Endorsement document requests funding for 16 countries having access only to STAR funds, with no Core allocation. These include: Argentina, Cuba, Egypt, Ethiopia, Indonesia, Iran, Kazakhstan, Madagascar, Malaysia, Morocco, Peru, Papua New Guinea, Turkey, Thailand, Tanzania, and South Africa. |
| a) the expected outputs of the project Framework should be completely revised and instead of number of project funded, it should set output indicators in terms of biodiversity conservation, climate change attenuation or adaptation, desertification/land degradation reduction, transboundary waters management, POPs reduction and concrete indicators of CBOs/CSOs capacities improvements. | GEF SGP’s detailed results framework with quantitative output indicators and targets for measuring direct global environmental benefits is included as Annex A to the CEO endorsement document. Project template and specific indicators at the project level are included as Annex A.1 to the document. This framework, with output indicators in each focal area, was originally prepared and shared in the GEF SGP global project CEO endorsement document for Core funds in November 2010. It presents GEF SGP’s expected results within its 5th Operational Phase, with grant funding from both Core and STAR funds. |
| b) the purpose of the GEF SGP remain unclear between a long term assistance to all CBOs/CSOs project in each GEF SGP countries (without clear phasing out strategies or capacity improvement process with clear steps) or the purpose of creating sustainable and long lasting capacities amongst CBOs/CSOs beneficiaries (then with a clear purpose of steps by step improvement and capacity building goal). In one hand the PIF state that GEF SGP should continue to fund CBOs/CSOs beyond this past 18 years because “The programme is a critical resource for GEF SGP’s partner organizations and communities, without which their available support channels would be reduced and their ability to confront environmental issues limited (p16).” This seems to mean that without this new GEF SGP phase, investments made in the past 18 years in CBOs/CSOs would be lost. On another hand, the PIF state that “GEF SGP will continue developing capacity of civil society organizations (CSOs), with priority for community-based organisations (CBOs) and indigenous peoples organisations” and “To ensure sustainability of community capacity, GEF SGP will ensure beneficiaries of capacity development are rooted in and deeply connected within the communities, so when projects are completed, the knowledge and technical skills remain within the communities to continue carrying out environmental protection activities.” In this case, the PIF should clearly put output indicators in terms of CBOs/CSOs with sufficient sustainable capacities instead of number of CBOs/CSOs’ funded projects. Our recommendation is to clarify the role of GEF SGP in terms of capacity building output and methodology to help low capacity organizations to reach a point of sustainable capacities to manage global environment issues. We suggest GEF SGP to put in place new challenging output like CBOs/CSOs increased leveraging funding capacity indicators, or goals of helping CBOs/CSOs moving from GEF SGP small grant management to medium size or even full size project management. | GEF SGP had been tasked with the primary objective of helping generate “global environmental benefits” through community or local action. Very small amount of grants for the first time could possibly be utilized for direct and stand alone capacity development activities (still related to generating global environmental benefits), the rest of the grants are directed at generating GEF focal area outcomes on the ground aligned to the GEF-5 strategic objectives. In fact, in previous operational phases, GEF SGP was instructed to consider stand-alone capacity development activities under the category of management costs. It is in the process of producing the on-ground results in which capacity development of the CBO/CSO grantee-partners occur in a “learning-by-doing” approach. Through the CBO’s or CSO’s 2 – 3 years implementation of the project, a step-by-step capacity development occurs, specific to the focal area subject of the project and with the aim to sustain the initiatives and gains made by the project. The 2007 Joint Evaluation of the GEF SGP verified that GEF SGP projects indeed have high sustainability because of this. While GEF SGP has been operational for 18 years, the need for GEF SGP has continued to increase. New countries have joined the programme with basic foundational capacity building needs and fledgling CBOs and NGOs. In the more mature countries, the greater awareness and enhanced capacity of civil society have increased absorptive capacity and range of possible strategic actions to address global environmental problems. As they become better established GEF SGP country programmes experience rising demand from communities and civil society actors, often greatly in excess of available funding, especially as the overall global environment challenges continue to grow due to population growth, industrialization, and degradation of the natural resource base. There are also a lot of cases where new approaches and innovative models only become convincing for wider replication or scaling up when tested over many relevant situations. A critical mass of small community-based projects is also required either to properly cover an ecosystem (i.e. watersheds or coastal zones) or to pool sustainable products for fair trade (i.e. organic certified honey for export). Additionally, it should be also noted that not all country programmes have been operational for 18 years. GEF SGP started in 1992 with only a few countries in its pilot phase, and expanded country coverage gradually – with the largest increase in country programmes occurring in the last four years during GEF4. Only eight GEF SGP country programmes are 18 years’ old, while more than half of all country programmes are less than 8 years old Given that GEF SGP was primarily tasked to help generate “global environmental benefits” (GEB), the GEF SGP OP5 targets in Annex A which will serve as basis for its output indicators are in the language that reflects GEB. For example, by stating that “110 Indigenous and Community Conserved Areas will be positively influenced” it is also implied that the indigenous and local communities involved and their CSO partners will have their capacity developed in skills such as delineation of ancestral domains, inventory of resources, conservation planning and implementation and advocacy for policy support. Other examples include “60 ecosystems with conservation aware communities” and “adopting sustainable use”, “restoration and enhancement of 15,000 hectares of forest and non-forest lands initiated”, and 27,000 hectares under improved agricultural, land and water management practices.” None of these targets will be met and sustained without the capacities of the community members and their CSO partners also being developed. GEF SGP, however, in receiving funding from GEF which requires that its funded activities be linked to GEB, have to imbed capacity development within its targets, a consequence of the process undertaken rather than the primary component, except for the 10% capacity development grants that have just now been allowed. As these capacity development grants relate to providing needed support so that GEF SGP country programme work indeed links with and helps generate GEB (e.g. improving awareness on conventions, networking, enhanced participatory M&E, production of knowledge products, and case studies for sharing lessons learned), most likely the grantee CSOs would have to be those with enough capacity to provide these supportive activities to other less capable CBOs/CSOs and community partners. As the capacity development of CBOs/NGOs are imbedded in the accomplishments and targeted outcomes of GEF SGP globally and its country programmes, the way by which new challenging outputs are expressed as capacities of CBOs/CSOs increase over time is as laid out in the Council paper G36/4 “Small Grants Programme: Execution Arrangements and Upgrading Policy for GEF-5.” In this Council approved paper, more “mature” GEF SGP Country Programmes (in this submission, these are Argentina, Egypt, Indonesia, Iran, Kazakhstan, Malaysia, Morocco, Peru, South Africa, and Turkey) are expected to produce higher level outcomes such as increased replication, scaling up, and mainstreaming of successful projects, as well as generating useful knowledge management products. They should also eventually be able to support and organize strong local networks of grantees and local NGOs that are influencing local and national development planning and policy making; with NSCs that are active, not only in proposal reviews, but also in influencing policy and resource mobilization. Meeting these higher level outcomes actually require and thus imply that CBO/CSO grantees and partners of GEF SGP, particularly those that had accessed grants in earlier operational phases, are targeting and meeting more challenging tasks. In the 2nd Independent Evaluation of the GEF SGP, it was concluded that implementing projects at the $25,000 level which is the average for GEF SGP or even at the $50,000 level does not provide enough exposure and experience to go after even medium-sized projects. It was recommended that “strategic projects” at maximum of $150,000 be provided to allow a higher “ladder” of capacity to develop. “Strategic projects” grants have now been incorporated in the GEF SGP Operational Guidelines for this purpose (see Annex H, Part III para 54). |
| c) One shouldn’t avoid recognizing adverse effects of GEF SGP on the field after 18 years of operation in some countries. One known adverse effect in some GEF SGP countries is the development of CBOs/CSOs projects brokers who are “selling” to community to other community the drafting of the same type of project which is perfectly fitting with GEF SGP criteria and get usually selected for funding against a % fee of the amount awarded by GEF SGP to the community. It would be good that GEF SGP monitoring tools track for example if the exactly same template of projects are funded other different communities and time within one GEF SGP country program. Other kind of area of improvement could be assessed. Currently the PIF doesn’t provide information on its assessment of areas of improvement for the future. | GEF SGP has a proven and established governance structure as laid out in its Operational Guidelines (attached as an Annex to this document), and set of procedures that has helped limit “brokering” of NGOs in project development. These include the following 1) National Steering Committee (NSC): a voluntary body composed of high-level and respected government officials, academics, NGOs, private sector representatives and technical experts. The NSC members are generally well-informed about other projects and forums in their areas of expertise, and able to play a role in promoting coordination and synergy and development of partnerships with other national initiatives. NSC members as well as CBOs/CSOs linked to them cannot access GEF SGP grants. There is also a rotation of non-governmental members every three years. 2) Country-based team with a National Coordinator and Programme Assistant. This team is UN-contracted and reporting to the GEF SGP Global Manager to assure their “neutrality”. The team works with all past and future grantees, and is able to work closely with grantees in proposal development, as well as provide regular oversight to projects under implementation. With their in-country presence and local knowledge, the programme team can play a role in avoiding or limiting such “brokering”. 3) Grantees’ network as well as links with credible NGOs. GEF SGP has developed grantees’ networks in countries, which are able to provide capacity development assistance and mutual monitoring between grantees to avoid such “brokering” of NGOs. Links to credible local NGOs result in fast feedback whenever there are violations to GEF SGP procedural and ethical rules. 4) Site visits and community participation. NSC members and NCs/PAs undertake regular monitoring site visits, and maintain close contacts with communities. Some NSCs approve projects based on pre-approval visits to communities to make sure that the proposal have been developed with the community in a highly participatory manner and the project has a fit specific to the special situation and context of the community, something which will be missing in “factory” developed proposal. . Furthermore, as recommended by the 2007 Joint Evaluation of the GEF SGP, the programme undertook not only a financial but a management audit. Conducted by Deloitte, no issue regarding possible “brokering” or any serious critical management issue was found. In GEF SGP OP5, there will again be an audit exercise that is risk based. The risk of “brokering” by CBOs/CSOs will be factored in the risk ranking and will certainly be looked into. The areas for improvement of GEF SGP for GEF-4 as well as GEF-5 have been detailed in the 2007 Joint Evaluation report and subsequent GEF SGP papers submitted to the GEF Council, including the following: - GEF/C.33/5: Small Grants Program: Follow up to the 2007 Joint Evaluation (2008) - GEF/C.36/4 Small Grants Programme: Execution Arrangements and Upgrading Policy for GEF-5 (2009) - GEF/C.38/Inf.05: Update on SGP Upgraded Country Programs (2010) Nonetheless, GEF SGP has planned an “advisory assessment” to be done by the GEF Evaluation Office in late 2013 which will look into GEF SGP’s implementation of the 2007 Joint Evaluation recommendations and to identify further areas of improvement (which then could include how best to prevent “brokering”) to be done within GEF-5 and to be planned for GEF-6. |

ANNEX C:  CONSULTANTS TO BE HIRED FOR THE PROJECT USING GEF/LDCF/SCCF/NPIF RESOURCES

| Position Titles | $/ Person Week* | Estimated Person Weeks** | Tasks To Be Performed |
| --- | --- | --- | --- |
| For Project Management |  |  |  |
| Local |  |  |  |
| International |  |  |  |
| Justification for travel, if any: |  |  |  |
| For Technical Assistance |  |  |  |
| Local |  |  |  |
| International |  |  |  |
| Justification for travel, if any: |  |  |  |

*  Provide dollar rate per person week.    **  Total person weeks  needed to carry out the tasks.

Annex d:  status of implementation of project preparation activities and the use of funds

A.  explain if the ppg objective has been achieved through the ppg activities undertaken.

B.  describe findings that might affect the project design or any concerns on project  
         implementation, if any:

C.  provide detailed funding amount of the ppg activities and their implementation status in the 
        table below:

| Project Preparation Activities Approved | Implementation Status | GEF/LDCF/SCCF/NPIF Amount ($) |  |  |  | Cofinancing ($) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Amount Approved | Amount Spent Todate | Amount Committed | Uncommitted Amount* |  |
| Total |  | 0 | 0 | 0 | 0 | 0 |

*  Any uncommitted amounts should be returned to the GEF Trust Fund.  This is not a physical transfer of money, but achieved  through 
             reporting and netting out from disbursement request to Trustee.  Please indicate expected date of refund transaction to Trustee.

annex e:  calendar  of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/NPIF  Trust Fund or to your Agency (and/or revolving fund that will be set up)

ANNEX F: SGP OP5 M&E Plan

| Item | M&E Activity | M&E Level and Type | Responsible Parties | Budget Source | Timeframe |
| --- | --- | --- | --- | --- | --- |
| Project Level |  |  |  |  |  |
| 1 | Participatory Project Monitoring | Project; Implementation | Grantee | Covered under project grant amount | Duration of project |
| 2 | Baseline Data Collection | Project; Results | Grantee | Covered under project planning grant amount or project grant amount | At project concept planning and proposal stage |
| 3 | Two or Three Project Progress and Financial Reports (depending on agreed disbursement schedule) | Project; Implementation | Grantee | Covered under project grant amount | At each disbursement request |
| 4 | Project Workplans | Project; Implementation | Grantee and NC | Covered under project grant amount | Duration of project |
| 5 | NC Project Proposal Site Visit (as necessary / cost effective) | Project; Implementation | NC | Variable | Before project approval, as appropriate |
| 6 | NC Project Monitoring Site Visit (as necessary / cost effective) | Project; Implementation AND Results | NC | Variable | On average once per year, as appropriate |
| 7 | NC Project Evaluation Site Visit (as necessary / cost effective) | Project; Implementation AND Results | NC | Variable | At end of project, as appropriate |
| 8 | Project Final Report | Project; Implementation AND Results | Grantee | Covered under project grant amount | Following completion of project activities |
| 9 | Project Evaluation Report (as appropriate) | Project; Implementation AND Results | NC (with contracted independent external party) | Variable | Following completion of project activities |
| 10 | Prepare project description to be incorporated into global project database | Project; Implementation | PA and NC | Covered under country program operating costs | At start of project, and ongoing as appropriate |
| Country Level |  |  |  |  |  |
| 11 | Country Programme Strategy Review | Country; Implementation | NC, NSC, CPMT | Included in NC, NSC, and CPMT and other staff time | Once per operational phase |
| 12 | Strategic Country Portfolio Review | Country; Implementation AND Results | NSC | Covered under country program operating costs | Once per operational phase |
| 13 | NSC Meetings | Country; Implementation AND Results | NC, NSC, UNDP Country Office | Covered under country program operating costs | Minimum twice per year |
| 14 | Performance and Results Assessment (PRA) of NC Performance | Country; Implementation | NC, NSC, UNDP Country Office, CPMT, UNOPS | Covered under budgeted staff time | Once per year |
| 15 | Country Programme Review resulting Annual Country Report | Country; Implementation AND Results | NC presenting to NSC | Covered under budgeted staff time | Once per year |
| 16 | Financial Four-In-One Report | Country; Implementation | NC/PA | Covered under budgeted staff time | Quarterly |
| 17 | Audit | Country; Implementation | UNOPS / External Contractor | Budgeted under global operating budget | As required on risk-assessment basis |
| 18 | General Programme Monitoring | Country; Implementation | UNDP Country Office | Covered by country office | Ongoing |
| Global Level |  |  |  |  |  |
| 19 | SGP Database | Global; Implementation AND Results | CPMT | Global operating budget and M&E budget | Ongoing |
| 20 | SGP Production of GEF Council Papers | Global; Implementation AND Results | CPMT | Covered under budgeted staff time and global operating budget | As required |
| 21 | Annual SGP Report | Global; Implementation AND Results | CPMT | Global operating budget and M&E budget | Annually |
| 22 | Inputs to UNDP annual development assistance evaluations in selected countries | Global; Results | CPMT, UNDP Evaluation Office | Covered under budgeted staff time; global operating budget and M&E budget | Annually |
| 23 | Inputs to UNDP knowledge products | Global; Results | CPMT | Covered under budgeted staff time; global operating budget and M&E budget | Ongoing |
| 24 | SGP Reporting to Conventions | Global; Results | CPMT through GEF Secretariat | Covered under budgeted staff time and global operating budget | At least one month prior to deadline for GEF Secretariat reporting to conventions (varies by convention) |
| 25 | Annual Work Plans | Global; Implementation | CPMT | Covered under budgeted staff time and global operating budget | Annually |
| 26 | Global Portfolio Monitoring and Oversight | Global; Results AND Implementation | CPMT | Covered under budgeted staff time and global operating budget | Ongoing |
| 27 | Country Programme Review / Monitoring (through various mechanisms including monitoring visits as appropriate / cost effective) | Global; Implementation AND Results | CPMT | Covered under budgeted staff time and global operating budget | As necessary and appropriate |
| 26 | Programme Delivery Reports (GEF Financial Reporting) | Global; Implementation | UNOPS to UNDP-GEF | Covered under UNOPS operating costs | Quarterly |
| 29 | Co-finance Programme Delivery Reports (Co-financing Reports to Donors) | Global (can also be country); Implementation AND Results | UNDP and UNOPS | Covered under budgeted staff time | As required |
| 30 | Global Thematic Portfolio Reviews | Global; Results | CPMT | Global operating budget and M&E budget | Ongoing |
| 31 | Project Case Study Generation | Global; Results | CPMT | Global operating budget and M&E budget | Ongoing |

ANNEX H: GEF Small Grants Programme (SGP) Operational Guidelines

Purpose of this Document

These Operational Guidelines are intended to assist GEF SGP National Coordinators/Sub-Regional Coordinators (NCs/SRCs), National Steering Committees (NSCs), Sub-regional Steering Committees (SRSCs), National Focal Groups (NFGs), UNDP Country Offices and National Host Institution (NHI) staff in programme implementation at the country level. They are based on the experience and knowledge gained both at the country and global levels through years of GEF SGP programme implementation. They provide basic framework for operations about the structure, implementation, and administration of the programme. They also address the project cycle and grant disbursement. Programme and project monitoring, evaluation, and reporting are covered in the GEF SGP Monitoring and Evaluation Framework.

The guidelines and models set forth herein are meant to apply generally to all GEF SGP country programmes. It is recognized, however, that different contexts and situations will require different responses and adaptations. Any questions about the application of particular provisions of the guidelines or need for adaptation should be referred to the GEF SGP Global Manager and Central Programme Management Team (CPMT). On administrative and financial matters, questions may be answered by the UNOPS SGP Standard Operating Procedures and, if necessary, to the respective UNOPS SGP Portfolio Manager.

List of Acronyms

BAC			Budget Account Classification Code

CBO			Community-based Organization

CCF			Country Cooperation Framework

CO			Country Office

COA			Chart of Account (ATLAS)

COB			Country Operating Budget

CPMT			Central Programme Management Team

CPS			Country Programme Strategy

GEF			Global Environment Facility

IOV			Inter-office Voucher

M&E			Monitoring and Evaluation

MOA			Memorandum of Agreement

MOD			Miscellaneous Obligation Document

NC			National Coordinator

NFP			National Focal Person

NFG			National Focal Group

NGO			Non-governmental Organization

NHI			National Host Institution

NPFE 			GEF National Portfolio Formulation Exercise

NSC			National Steering Committee

OP			Operational Programme

PA			Programme Assistant

PO			Purchase Order (ATLAS)

REQ			Requisition (ATLAS)

SBAA			Standard Basic Assistance Agreement

SGP			GEF Small Grants Programme

SOPs			Standard Operating Procedures

SRC			Sub-Regional Coordinator

SRSC			Sub-Regional Steering Committee

SPS			Sub-Regional Programme Strategy

TOR			Terms of Reference

UNCBD		United Nations Convention on Biological Diversity

UNCCD 		United Nations Convention to Combat Desertification

UNDP			United Nations Development Programme

UNOPS		United Nations Office for Project Services

UNFCCC 		United Nations Framework Convention on Climate Change

Part I: 	GEF SGP Programme Structure

- The structure of the GEF Small Grants Programme (SGP), implemented by UNDP, is decentralized and country-driven. Within the parameters established by the GEF Council and reflected in the Project Document for an Operational Phase, the programme seeks to provide for maximum country, and community-level, ownership and initiative. This decentralization is balanced against the need for programme consistency and accountability across the participating countries for the achievement of the GEF global environmental objectives, and the SGP’s particular benchmarks as stated in the Project Document for an Operational Phase.

- The SGP is a global and multi-focal area GEF project, approved for funding by the GEF Council on a rolling replenishment, and implemented on behalf of the GEF partnership by UNDP, and executed by UNOPS. In the case of upgraded country programmes, UNOPS execution is the recommended option although a country-specific execution modality utilizing a national non-governmental organization or a consortium of non-governmental organizations, selected by UNDP through a competitive process, can be utilized. Within the UNDP framework, the SGP, as a global programme, is handled differently from UNDP core national or regional programmes.

- The GEF Council approves the SGP Project Information Form (PIF), GEF CEO clearance document, and SGP Project Document for an operational phase. The SGP Project Document provides the framework for SGP operations in accordance with the GEF mandate, including specific benchmarks for project achievements. It also sets forth many of the programme and financial reporting requirements for which UNDP has legal responsibility.

- As a global programme, the SGP brings together country programmes of participating countries across all world regions. The key eligibility criteria for countries to participate in SGP are:

- Existence of environmental needs and threats in GEF focal or thematic areas;

- Ratification of at least one of the global environmental conventions including the United Nations Convention on Biological Diversity (CBD); the United Nations Framework Convention on Climate Change (UNFCCC); the Stockholm Convention on Persistent Organic Pollutants; and United Nations Convention to Combat Desertification (UNCCD);

- Government commitment in the participating country and support for the programme’s implementation modality according to the operational guidelines;

- Potential for strong government-NGO relations and positive support for local Civil Society Organizations;

- Commitment for resources mobilization : the UNDP/CO and government share available funding for SGP delivery from both GEF and non-GEF sources, and support efforts to attract other co-funding sources;

- Positive enabling environment;

SGP Headquarters Structure

- A UNDP/GEF Unit at UNDP Headquarters in New York provides fiduciary oversight for all of its GEF activities, including the SGP. Key UNDP Headquarters staff include the UNDP GEF Executive Coordinator, and his/her Deputy, who are legally accountable to UNDP and to the GEF Council for the utilisation of GEF resources.

- Overall SGP programme management, operational guidance and support to the country programmes,  as well as the identification and establishment of the SGP in new countries, are conducted by the SGP Central Programme Management Team (CPMT). The CPMT is composed of a Global Manager and Deputy Global Manager; Programme Specialists responsible for matrixed country support and focal area guidance, knowledge management, and monitoring & evaluation; Programme Associates; as well as external consultants as needed.

- The United Nations Office for Project Services (UNOPS) provides programme execution services including administrative, financial, legal, operational, procurement and project management for the SGP as described in detail in the UNOPS SGP Standard Operating Procedures (SOPs). The UNOPS SGP Cluster Coordinator and his/her team work closely with the SGP Deputy Global Manager and CPMT staff.

- The SGP Global Manager and his/her alternate, the SGP Deputy Global Manager, are ultimately responsible for the overall management, strategic direction, policy development and resource mobilization efforts of the SGP. The Programme Specialists are primarily responsible for guidance on GEF focal areas and thematic directions, country programme support, assigned regional coordination responsibilities, knowledge sharing, partnership development and networking. As necessary, the Global Manager and Deputy Global Manager may delegate certain functions to the Programme Specialists.

- SGP regional teams, composed of at least one staff member from CPMT and from UNOPS, as well as the regional senior National Coordinator as needed, provide a range of technical advice, operational, management and administrative support to country programmes in each of the six SGP world regions, divided as follows:

- Africa

- Arab States

- Asia

- Europe & CIS

- Pacific

- Latin America & the Caribbean

- While the CPMT regional focal point focuses primarily on GEF technical and programmatic matters, and the UNOPS regional focal point is responsible for administrative and financial issues, the SGP regional team works collaboratively in advising country programmes with regard to all substantive and operational matters. The regional teams also review the annual SGP country staff performance and recommend ratings for review by the Deputy Global Manager, and his/her counterpart in UNOPS, prior to endorsement and finalisation by the Global Manager.

- SGP Programme Associates are responsible for daily administration, filing and archive management; financial record-keeping and reporting to donors; human resources support; external communications; organisation of meetings; and responses to routine requests for information. The Programme Associates monitor completion of SGP work-plans, and assists in CPMT activities, correspondence, and other assigned tasks.

SGP Country Programme Structure

The SGP operates in a decentralized and country-driven manner through a National Coordinator or Sub-regional Coordinator (both hereafter to be referred as NC) and National Steering Committee or National Focal Group for those in sub-regional programme modality (both hereafter abbreviated to NSC) in each participating country, with some modification in the case of countries in a sub-regional programme modality, with financial and administrative support provided by the UNDP Country Office (CO). In some countries, a National Host Institution (NHI) or host NGO is responsible for programme implementation in conjunction with the NC and NSC. While the SGP is a global programme, at the country level it operates under the overall UNDP SBAA agreement. As a global programme, the SGP is not considered a part of the CCF or UNDP core functions.

- The NSC is composed of voluntary members from NGOs, academic and scientific institutions, other civil society organizations, the UNDP CO, and government, with a majority of members coming from the non-governmental sector. The NSC provides overall guidance and direction to the country programme, and contributes to developing and implementing strategies for country programme sustainability.

- The technical capacity of the individual NSC members is an important criterion in determining its composition, and to the maximum extent possible the NSC membership should include experts in the relevant GEF focal areas of biodiversity; climate change mitigation; international waters; sustainable land management; sustainable forest management and REDD; persistent organic pollutants/ chemicals; as well as capacity development. The inclusion of the government GEF Operational Focal Point (OFP) or relevant Convention Focal Point in the NSC is also recommended.

- The NSC is responsible for the review, selection and approval of projects, and for ensuring their technical and substantive quality as regards the strategic objectives of the SGP. In collaboration with the NC, the NSC contributes to the development of the Country Programme Strategy (CPS) in accordance with the relevant Operational Phase project document and national environmental priorities, and oversees its implementation. NSC members are expected to support the country programme in resource mobilization and in mainstreaming SGP lessons learned and successes in national development planning and policy-making. NSC members are encouraged to participate in pre-selection project site visits and in project monitoring and evaluation.

- The NSC may also constitute Technical Advisory Groups (TAGs) with a pool of voluntary experts on call to serve as a technical sub-committee, for review of proposals and in relation to specific areas of programming and partnership development. The TAG can also be tasked by the NSC to provide specific technical guidance in specialised areas of work, such as carbon measurement, payments for ecosystem services, marketing and certification of products, transboundary diagnostic analysis, and other relevant fields. In addition, TAGs may also be formed in response to donor and co-financing requirements mobilised for the SGP country programme.

The SGP NC has lead responsibility for managing the country or sub-regional programme implementation, and ensuring that grants and projects meet GEF and SGP criteria. The NC major functions inter alia include: (i) assisting CSOs in the formulation of project proposals; (ii) serving as the ex officio secretariat for the NSC; (iii) ensuring sound programme monitoring and evaluation, including periodic project site visits; (iv) resource mobilization; (v) communication and dissemination of SGP information; and (v) global reporting to CPMT, UNOPS, responding to audits, and other tasks as stipulated in their ToR.

- The UNDP CO provides management support to the SGP country programme as outlined in this document. The UNDP Resident Representative/Resident Coordinator (hereafter abbreviated to UNDP RR) in each UNDP CO assigns a senior staff person (typically the Sustainable Development Advisor or environment focal point) to serve as the SGP focal point.  The UNDP RR participates in the NSC or may designate the focal point as his/her delegate in the NSC.  Each UNDP CO also contributes to monitoring programme activities – usually through broad oversight by the designated focal point as part of NSC responsibilities; facilitates interaction with the host government; and develops links with other in-country financial and technical resources.

- The UNDP CO is also responsible for providing operational support – the RR signature of grant project MOAs (on behalf of UNOPS); appointment letters to NSC members (on behalf of SGP); local grant disbursements; HR administration; as well as assisting in audit exercises for the programme.  The detailed steps for each operational aspect are described in the UNOPS SGP SOPs.  The UNDP CO also plays a fundamental role in launching a new SGP programme in terms of endorsement of the government application to be a participating SGP country and in helping CPMT organize the start up mission. The UNDP CO also plays a critical role in the proper closing of an SGP country programme.

Part II 	Implementation and Administration of SGP Country Programmes

In-country institutional arrangements

- While the SGP is a global programme, at the country level it operates under the overall UNDP SBAA agreement, but remains accountable to the CPMT/UNOPS SGP Cluster at Headquarters and, ultimately, to the GEF Council. There are two basic modalities for SGP hosting arrangements that CPMT, in consultation with country stakeholders, will decide for the country programme. In most countries, the programme is hosted by the UNDP CO, although this may also mean that the SGP office is physically located outside of the CO premises. Where there are issues of accessibility and based on consultations with stakeholders, the programme could be hosted  in a National Host Institution (NHI), which may be an NGO or an academic institution.

- In case of NHI hosting, UNOPS issues and administers a sub-contract with the NHI that outlines the technical support and administrative services to be provided, as well as the applicable operating budget. In all cases, the UNDP CO provides needed support for SGP in-country operations in coordination with the CPMT and UNOPS. Whatever the hosting arrangements, all country programmes respond equally to the relevant Operational Phase project document and global SGP Operational Guidelines.

- As noted above, NCs are guided by CPMT regional focal points for the majority of operational and technical matters, whilst reporting ultimately to the SGP Global Manager. NCs are also accountable to the UNDP RR for country-level programme expenditures and on matters regarding meeting the ethical and professional standards of the UNDP.  The UNDP RR with members of the NSC is responsible for preparing the annual evaluation of the NC performance and recommendation concerning contractual status for review by CPMT and UNOPS.

- In keeping with the spirit and mandate of the SGP to develop and foster the capacities of CSOs in participating countries, it is expected that as individual country programmes mature it will be possible to transfer the hosting arrangements from the UNDP CO to NHIs. Any decision for transfer should be based on a full consultative process and analysis of key factors, and must be approved by the CPMT in consultation with the UNDP RR. In certain cases, where the selected NHI does not fully meet performance expectations, and upon consultation with country stakeholders, the contract may be terminated by the CPMT and UNOPS, and hosting will be transferred either to the UNDP CO or to another NHI.

- The relationship with an NHI may range from the provision of physical office space, with the NC and NSC carrying full responsibility for programme management; one in which the NHI is responsible for providing specifically agreed services, such as technical advice and support; through to one where the NHI carries full responsibility for managing the SGP programme.  The extent of responsibility will be clearly identified in the contract for services signed by UNOPS and the NHI and may evolve over time.

- The identification of a pool of suitable NHIs may be carried out through a process of competitive bidding, or by gradually accumulating a list of available and interested organizations in consultation with key stakeholders. Local representation of international NGOs would not normally be eligible.  The legitimacy and neutrality of potential NHIs within the national NGO community are essential qualifications to carry out SGP grant-making activities. Once a pool of organizations has been established, the following factors will be considered by the CPMT and UNDP CO in order to select the best candidate:

- National stature and credibility;

- Good working relationships with other CSOs, including participation in environment/ development networks;

- Demonstrated compatibility with the procedures, objectives, and grant-making functions of the SGP, GEF, and UNDP;

- Significant experience in community-based, participatory environment and development;

- Substantial involvement and technical expertise in environmental issues related to the GEF focal areas and the Rio conventions;

- Proven programme management and administrative capacity with systems in place.

- The NC is normally an employee of UNOPS whereas the contract is administered locally by the UNDP CO on behalf of UNOPS.  In some cases, the NC contract administration can be covered under the terms of the contract with the NHI. The selection of the NC is done through a publicly advertised and competitive selection process. As a general rule, the recruitment process for the NC is managed on behalf of UNOPS by the UNDP CO under the overall supervision of the UNDP RR. This is ordinarily the case even if the NC will be placed in an NHI; however, the NHI, as appropriate and upon approval of CPMT, may manage the NC recruitment. The selection panel submits three of the top applicants to the Global Manager for final selection and decision. The recruitment process and related guidelines are highlighted in more detail in the UNOPS SGP SOPs.

- Typically, NHIs do not normally administer grant funds. As country programmes evolve, however, it may become desirable to include direct grants administration as part of NHI responsibilities under UNOPS-issued contracts or other mechanisms, thereby increasing the level of country ownership of, and civil society participation in, the programme. Administrative procedures will need to be devised to ensure that the administration of grant allocations and their transferral to grant recipients remain transparent, accountable and fluid. NHIs cannot be awarded nor use SGP grant funds.

SGP country staff roles and responsibilities

- The NC is responsible for the overall functioning of the SGP in each participating country, and for the achievement of the benchmarks established for country programme implementation in the CPS and SGP Project Document for the relevant Operational Phase. The NC is expected to have full-time dedication to the SGP.  The NC is responsible for ensuring sound programme and project monitoring and evaluation, and laying the foundation for programme sustainability. In project development, the NC may work directly to assist proponent CSOs access needed support  including the recommendation of support through planning grants. The NC, jointly with the UNDP CO, bear direct responsibility for all local programme expenditures. A critical aspect of the NC job performance is to carefully monitor and supervise these expenditures under the overall supervision of UNOPS and to ensure accountability and transparency

- The NC usually represents the SGP in local and national meetings, workshops, and other events, and may be accompanied by members of the NSC. However, for legal and financial purposes, only the UNDP RR or his/her Officer in Charge (OIC) may represent the SGP in-country (on behalf of UNOPS). Only the UNDP RR or his/her Officer in Charge (OIC) can sign SGP grant Memoranda of Agreement (MOAs) and for signing any co-financing arrangements on behalf of SGP. While the NC may initiate and undertake co-financing and other negotiations for the programme, s/he should never officially sign such agreements. The NC, however, may sign non-binding collaborative agreements between SGP and other projects and programs. The NC should consult the CPMT and the UNOPS SGP Cluster should there be doubt on signing rules and procedures.

- The performance of NCs is evaluated annually.  The evaluation is undertaken through an online Performance and Results Assessment (PRA) in two parts:  a self-assessment by the NC, and a performance evaluation with NSC inputs under the charge of the UNDP RR.  These two parts of the evaluation should be completed shortly after the completion of the reporting period.  The completed and signed evaluations are submitted to the CPMT. The PRA evaluations are reviewed by the CPMT and UNOPS regional teams, and final decisions are then taken by the SGP Global Manager and Deputy Global Manager on contract renewal, and other actions that might need to be taken.

- In most countries, the NC works with a Programme Assistant/Associate (PA). On behalf of UNOPS, the UNDP CO may hire a PA with technical and/or administrative skills and functions depending on local needs. The NC shall be involved in the selection process and the panel recommendation will be forwarded to CPMT and UNOPS for final approval. The NC will be in-charge of the supervision and PRA for the PA. In certain cases, consultants with a technical background, especially in the GEF focal areas, may be recruited to contribute to project design, implementation, and monitoring and evaluation, and can be delegated by the NC to provide these services to CSOs and SGP projects as necessary.  The recruitment process and related guidelines are highlighted in detail in the UNOPS SGP SOPs.

National Steering Committee procedures

- The NSC is a central element of the SGP and provides the major substantive contribution and oversight to the programme, in coordination with the NC. While staffing and operational management of the SGP is undertaken through UNDP/UNOPS structures, no SGP project may be undertaken at the country level without the approval of the NSC. As such, the NSC must do its best to ensure the technical and substantive content of SGP grants, and the administrative and financial capacity, either actual or potential, of the CSO grant recipients.  The UNDP RR, or his/her delegate, as well as other members of the NSC, are encouraged to provide any relevant information about these concerns, especially the financial and organizational integrity of CSOs. Operationally, the decisions of the NSC are considered final provided they are consistent with these operational guidelines, the SGP Project Document for the operational phase and the Country Programme Strategy.  However, neither the NSC nor its individual members as programme volunteers, hold any legal or fiduciary responsibility for the SGP or its activities.

- The selection of NSC members is normally done by the NC in consultation with the UNDP RR.  For new country programmes, the NSC is often established as a result of a preparatory mission or in the initial stages of launching the programme.  NSC members should have an abiding interest and commitment to working with communities and share a vision of what sustainable development and "thinking globally, acting locally" might mean in terms of linking the GEF focal areas with community needs and concerns. NSC non-governmental members must have high credibility and wide experience working with local communities and CSOs in the country and thus can represent their needs and interests in committee discussions. Strong, experienced, and technically competent civil society representation on the NSC is crucial as a means of keeping the SGP responsive to its mandate to work with CSOs, CBOs and indigenous peoples. These members must also have the requisite knowledge about GEF Focal Areas and/or specific themes such as gender, sustainable livelihoods, and knowledge management. Governmental and donor agency members should hold positions relevant to the work of the SGP and at a level where they could make decisions on behalf of their agencies. NSC members on the whole must be able and willing to discuss constructively and develop consensus decisions. The NSC, with the NC,  are responsible for ensuring that participatory, democratic, impartial, and transparent procedures for project review and approval, as well as all other aspects of programme implementation at the country level in accordance with the SGP Project Document for the relevant Operational Phase.

- The composition of  a newly established NSC is subject to ratification by the SGP Global Manager while subsequent appointments can be ratified by the responsible CPMT Regional Focal Point. In general, only one government representative on the NSC is required. However, depending on the circumstances, country programmes can have additional government representatives such as Convention focal points, although in any case majority of members must be non-governmental. The UNDP RR provides the appointment letters on behalf of the SGP.

- NSC members usually serve for a period of three years.  Each country or sub-regional programme must decide whether this term is renewable, and how eligibility for renewal is determined.  In general, periodically inviting new members is a sound and healthy policy that brings new ideas and expertise to programme implementation, and roughly one quarter of NSC members may rotate in any given year. Changing the entire membership at one time should be avoided.

- Participation in the NSC is without monetary compensation. Travel expenses for project site visits or to NSC meetings can be covered by the SGP country operational budget.

- NSCs adopt desicions under the principle of consensus, and rarely resort to voting to determine whether a project is approved or a particular course of action is taken. To facilitate meetings, the NSC may decide to select its Chairperson(s) in the following way: (i) one of the most committed expert member to Chair for a particular period of time; (ii) members to chair meetings on a rotating basis to enhance each member’s participation; and (iii) on a co-chair approach with government and non-government representation to promote civil society leadership and CSO-government collaboration which are institutional objectives of the programme.

- The NC serves ex officio on the NSC, participating in deliberations, but not in decisions in the project selection process. The NC usually convenes the NSC and functions as its secretariat, including preparing minutes of meetings and maintaining a historical record of programme decisions and implementation. A copy of NSC minutes, signed by the members, and other pertinent material should be filed at the UNDP CO.

- In as wide a consultation as possible with country stakeholders, the NC shall prepare a long list of possible volunteers to the NSC. From this, the NC in consultation with the UNDP RR prepares the list of NSC members to be nominated for approval by the SGP Global Manager by considering both the expertise and qualifications of the individual candidates, and the overall composition and balance of the committee. While certain institutions (the UNDP, and appropriate governmental ministry or agencies, the NHI) must be represented in the NSC, members should also be chosen who as individuals, including from the private sector and donor community, would contribute significantly to the committee and the programme’s various expertise needs (e.g. on GEF focal areas, sustainable livelihoods, gender considerations, communications, resource mobilization, capacity development).  The NC, after due consultation with other NSC members of good standing and the UNDP RR, may recommend  changes in the composition of the committee to CPMT if it becomes clear that a particular member's participation is not contributing to the programme.

- The objectivity, transparency and credibility of the NSC is of paramount importance to the success of the country programme, and to maintaining good relations among stakeholders. As a general rule, country programmes cannot consider proposals associated with organizations of sitting NSC members. A CSO may nonetheless submit proposals when its representative has finished the term of service and is no longer on the Committee. On an exceptional basis, and under specified conditions pre-approved by CPMT, CSOs with members in the NSC can submit  proposals.

Country Programme Strategy

- Before any grant-making or other programme activities may take place, each SGP participating country must have an approved Country Programme Strategy or Sub-regional Programme Strategy (abbreviated here to CPS). The development/revision of the CPS is designed to ensure congruence with the SGP Project Document for the relevant Operational Phase; the strategic planning frameworks associated with the relevant Rio Conventions; as well as with the GEF National Portfolio Formulation Exercise (NPFE) where relevant.

- For new SGP country programmes, the development of a CPS is one of the first tasks to be undertaken by the NC and newly-formed NSC. In both new and continuing SGP country programmes, it is important to involve key stakeholders in the CPS revision/elaboration process, and to fully engage and involve the NSC. In this regard, the CPS may be considered a living document, and shall be revised or updated in every operational phase of SGP, or as deemed necessary by the NSC, to align country programme priorities with GEF policies and priorities, and those included in the relevant SGP Project Document.

- As described in the CPS Guidance framework, the development or revision of the CPS serves several broad purposes to:

- Identify the national circumstances and priorities of the country vis-à-vis the Project Document for the relevant Operational Phase;

- Provide stakeholders with a framework document to understand the priorities for SGP  funding for strengthened country relevance and ownership;

- Provide a strategic framework for allocating resources, especially selection of SGP projects, through a bio-geographic and/or thematic focus;

- Serve as the framework for country programme operations and guiding programme implementation;

- Constitute the basis for the assessment of country programme achievements and impact.

- The development/revision of the CPS should be undertaken as a participatory process that engages the full range of non-governmental and government stakeholders in the country. The CPS preparation should be seen not only as a document to satisfy global programmatic requirements, but as a country-led process which has value in its own right. The key players in the process are the NC (who facilitates the process, and is responsible for the majority of the drafting), and the NSC (which provides input and guidance throughout the process, and endorses the end product).

- The CPS should contain: (a) background situation of the country which the SGP country programme has to consider; (b) key objectives vis-a-vis the country situation and the objectives of the global SGP Prodoc for the operational phase; (c) geographic (with maps) and/or thematic focal areas; (d) priority activities to be supported by grantmaking; and (e) expected outcomes, indicators, and M&E plan.

- Recommended steps to developing the CPS are as follows:

- NC prepares an initial CPS draft for consultation with the NSC based on the current SGP Project Document;

- Wide stakeholder consultations held with key CSO, government, academic and other concerned parties to discuss relevant issues (where possible, these consultations to be linked to the National Portfolio Formulation Exercise (NPFE) of the GEF in the country);

- Incorporation of stakeholder inputs into the draft CPS by the NC, and initial approval of the document by the NSC;

- Submission of the draft CPS to the CPMT Regional Focal Point for comment and review;

- Further CPS revision as necessary based on comments and recommendations by the CPMT;

- Submission of the revised CPS by the NC for formal endorsement by the NSC;

- Final approval of the endorsed CPS by the SGP Global Manager, or delegated CPMT Regional Focal Point;

- Posting and circulation of the final version of the CPS as a public document.

Country Operating Budget

- The Country Operating Budget or Sub-regional Operating Budget (abbreviated here to COB) is the financial provision for country, or sub-regional, programme implementation. The COB is prepared by the NC, and reviewed and approved by the CPMT and UNOPS. The COB should allow the effective operation of the country or sub-regional programme in implementing activities in support of  the objectives of the Project Document, as well as to be responsive to specific country circumstances and needs, as reflected in the CPS. In countries where a NHI hosts the SGP, the COB is generally covered by the terms of the contract for services between the organization and UNOPS. The COB process and related guidelines are highlighted in detail in the UNOPS SGP SOPs.

Part III	Implementation and Administration of SGP Grants

SGP grants and project cycle

- Each SGP country programme should, after adopting or revising its CPS, prepare and issue an SGP programme announcement. Information in the call for proposals should clearly state that the SGP makes grants to eligible CSOs, with priority for supporting poor and vulnerable communities in the GEF focal areas, with a maximum grant amount for a project of US$50,000. The subsequent process of developing an SGP project should then take place in a transparent manner covering the: (i) project preparation guidelines setting forth the eligibility criteria; (ii) application/proposal review process and calendar; (iii) formats for project concept and proposal development, and; (iv) co-financing requirements in cash and/or in-kind.

- Project concepts from eligible CSOs and CBOs may be screened by the NC or jointly with the NSC. Each country programme should determine which screening modality it will follow, and periodically review this decision to make sure that the modality chosen is working well. In both cases, project concept selection should be done on the basis of established eligibility and selection criteria in accordance with the CPS. At the very least, project concepts should be relevant to one or several of the GEF focal areas and that they reflect the needs of the community or communities and/or stakeholders that would be involved. Once the concepts have been selected, the proponent organizations will be notified of this decision and asked to develop complete project proposals.

- It is critical for all project proposals to meet the GEF and SGP criteria. While it is an important part of the NC responsibilities to work with CSOs in proposal development, sometimes additional assistance is nonetheless required.  In such cases, two options may be considered: (i) a local consultant may be hired to help the CSO/CBO/communities according to terms of reference that the NC elaborates in coordination with the organization; and (ii) the SGP planning grant modality may be used.

Planning Grants

- The NC or NSC may authorize planning grants once project concepts have been selected. CSOs such as CBOs, indigenous peoples’ organisations and communities with little experience in project design and management receive priority to benefit from this assistance. Hence, the planning grant has an important capacity-building function which in itself is an important SGP objective. The NC makes recommendations to the NSC about which proponent organizations would require a planning grant.

- A planning grant can be used by an eligible CSO to organize stakeholder workshops or meetings to design the project in a participatory manner. The planning grant can be used to contract an experienced NGO or local consultant to work with the project proponents to elaborate the project, to undertake baseline assessments, develop a business plan (for projects with strong sustainable livelihood elements), and through learning-by-doing, build capacity in proposal design including the development of indicators and a monitoring and evaluation plan.

- Administratively, a planning grant is a grant like any other SGP grant, and therefore can only be made to eligible CSOs. The project document for the planning grant specifies the activities to be undertaken, and the responsibilities of the parties concerned.  The NSC generally approves the planning grant, although the NSC can in certain instances also delegate approval to the NC for certain exceptional cases (e.g. time-sensitive activities, smaller amounts).  The  process follows the modus operandi of an SGP facilitative grant-making and is explained in detail in the UNOPS SGP SOPs.

Project proposals

- SGP provides grants to support activities that help achieve the programme objectives outlined in the CPS and the SGP project document for the Operational Phase. In terms of helping achieve global environmental benefits, the SGP’s starting point is to ensure that each project proposal fits the GEF criteria, and that each proposal clearly articulates how project objectives and activities would have a positive effect in the relevant GEF focal areas. To create sustainability and impact beyond the project, SGP projects can combine demonstration, capacity-building, network building, awareness raising, and dissemination of lessons learned as integral components.  Given this comprehensive approach, while a logical framework is not formally required, it would be advisable to include a Monitoring and Evaluation work-plan in each proposal (see SGP M&E Framework).

- As a demand-driven programme, SGP projects endeavour to address both the GEF criteria, as well as community needs and initiatives. The SGP usually works with communities and localities that confront a multitude of social and economic development problems that impact on concerns related to global environmental conventions. For SGP interventions to have relevance and utility at the community level, these non-GEF circumstances are taken into account in project design. A key guiding philosophy of the programme has been to reach the marginalized poor and vulnerable communities, especially when there are no other donors present, and where development baseline conditions have not been met. Typically, the SGP will therefore need to mobilize additional resources to help provide the co-financing, technical assistance, capacity-building, gender training, income-generation component, or whatever non-GEF element may be necessary for a project’s success. These project components are vital to achieving local acceptance, ownership, and sustainability of SGP interventions.

Funds disbursement

- The maximum amount for an SGP grant is $50,000 per project. In special cases, grants for “strategic projects” that consolidate efforts of several communities and CSOs could be provided at a maximum of $150,000. SGP grants generally only cover a portion of project costs, with other components provided for by the CSO partner, the community itself, or by other donors.  Since SGP grants fund activities that are directly relevant to the GEF criteria, co-financing must be sought for community baseline or sustainable development needs.  However, since it would be unrealistic to require a baseline/incremental cost exercise for each individual project, each country should instead endeavour to mobilize enough funding in cash or in kind to “match” the GEF country grant allocation.

- Once the NSC has approved a project for SGP funding support, a Memorandum of Agreement (MOA) is signed on behalf of UNOPS between the grantee and the UNDP CO. SGP projects normally have a duration of between one and three years.The amounts and schedules may differ, contingent upon the nature and length of project activities, but in no case should the first disbursement be more than 50% of the total project grant amount (except when justified and prior approval from UNOPS has been received). The MOA and grant disbursement process, the applicable templates, and all related guidelines are found in detail in the UNOPS SGP SOPs.

- A grantee may submit another proposal upon successful completion of an initial project but no grantee can receive funds exceeding US$50,000 in a given operational phase. Any grantee which has received the maximum $50,000 in one Operational Phase, may however submit another funding request in the following Operational Phase if the evaluation of project outcomes are positive. .

Part IV  	Reporting and Communications

- The NC has lead responsibility for communications between the country programme and the CPMT. In general, the NC reports on substantive and technical matters to the CPMT, and on administrative and financial issues to the UNOPS portfolio manager. The NC should keep the UNDP CO informed of progress in programme implementation, usually through the RR and SGP focal point in the UNDP CO. In particular, the NC and PA are expected to maintain a close working relationship with the UNDP CO regarding the COB and grants disbursements which serves to keep the UNDP abreast of SGP developments.  The NC should also endeavour to share relevant SGP reports with the GEF Operational and Political Focal Points as well as global environmental convention focal points.

- Communications among country programmes are facilitated through the global, regional, and sub-regional list servers, the SGP global database and workspace, and the SGP website. Recurring global reporting requirements, such as annual reports, are complemented by periodic requests by the CPMT and UNOPS for information on specific subjects, such as reports under preparation for the GEF Council, or for the relevant global environmental conventions. Full guidance on all project and programme reporting is provided in the SGP Monitoring & Evaluation Framework

- SGP country teams are responsible for entering detailed information for all prior and current Operational Phases into the SGP database, including the upload of grant project MOAs. Since the database is the foundation for all reporting and communications at the global level, it is imperative that NCs and PAs input the database as soon as projects are approved by the NSC, and keep it regularly updated on the progress of projects. The SGP database and website also includes visual documentation of SGP projects and country programmes, accounts of lessons learned, and case studies. Project briefs should be stored in the files of every project for easy use and sharing.

- The NC is required to report on technical and substantive project and programme progress through the annual country programme report. The annual report complements the information that is entered in the SGP database and should cover progress in meeting the year’s deliverables as well as other important information including: (i) assessment of the overall progress for the country programme portfolio; (ii) results of project monitoring and evaluation; (iii) key outcomes of SGP-sponsored events; (iv)  progress in strengthening working relationships with CSOs, as well as with government agencies and donors; (v) results of resource mobilization efforts; (vi) development of SGP visibility as a GEF programme and activities to share lessons learned and influence policy; and (vii) any special challenges and difficulties faced.

- The NC shall take all necessary measures to ensure the visibility of the GEF financing. Such measures shall be in accordance with the need to give adequate publicity to the action being implemented as well as to the support from the GEF. A communication and visibility plan shall be outlined in each project document. This should include, inter alia, the compulsory use of the GEF logo on all material, publications, leaflets, brochures and newsletters, websites, business cards, signage, vehicles, supplies and equipment, display panels, commemorative plaques, banners, promotional items, photographs, audiovisual productions, public events and visits and information campaigns. The plan should also include press releases, press conferences and press visits to project sites.

- The Programme Review is an overall assessment of the country programme performance to be undertaken by the NC and the NSC, in consultation with SGP grantees and other stakeholders, at the completion of an SGP Operational Phase. The purpose of the Programme Review is to assess the cumulative progress of the country programme in a particular Operational Phase and provide strategic recommendations on the direction for the programme in the next Operational Phase. Once finalized, the Programme Review should be shared by the SGP country team with the country GEF Operational and Political Focal Points and also the relevant Rio Convention focal points.

- Audits of SGP country programmes will be conducted in accordance with the internationally accepted auditing standards, and applicable financial rules and regulations. The SGP audit exercises are designed to improve the transparency, accountability and quality of SGP country and global operations. The audits will cover management, financial, and administrative issues as they relate to the country programme as a whole, and will not normally include provisions for project-level inspection.  The principles and processes governing SGP audit operations can be found in the UNOPS SGP SOPs.

Annex I  Countries’ STAR Contribution to GEF Small Grants Programme ($US)

| Country | FOCAL AREAS |  |  |  |  |  |  |  |  | Total Project Budget ($US) | Total Fee ($US) | TOTAL ($US) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Climate Change |  |  | Biodiversity |  |  | Land Degradation |  |  |  |  |  |
|  | Project Budget | Fee | Subtotal | Project Budget | Fee | Subtotal | Project Budget | Fee | Subtotal |  |  |  |
| Argentina | 865,385 | 34,615 | 900,000 | 865,385 | 34,615 | 900,000 | 865,385 | 34,615 | 900,000 | 2,596,154 | 103,846 | 2,700,000 |
| Cuba | 1,153,846 | 46,154 | 1,200,000 | 1,153,846 | 46,154 | 1,200,000 | 1,153,846 | 46,154 | 1,200,000 | 3,461,538 | 138,462 | 3,600,000 |
| Egypt | 1,810,000 | 72,400 | 1,882,400 | 572,500 | 22,900 | 595,400 | 186,250 | 7,450 | 193,700 | 2,568,750 | 102,750 | 2,671,500 |
| Ethiopia | 961,538 | 38,462 | 1,000,000 | 961,538 | 38,462 | 1,000,000 | 1,240,385 | 49,615 | 1,290,000 | 3,163,462 | 126,538 | 3,290,000 |
| Indonesia | 1,346,154 | 53,846 | 1,400,000 | 1,346,154 | 53,846 | 1,400,000 | 769,231 | 30,769 | 800,000 | 3,461,538 | 138,462 | 3,600,000 |
| Iran | 1,153,846 | 46,154 | 1,200,000 | 480,769 | 19,231 | 500,000 | 288,462 | 11,538 | 300,000 | 1,923,077 | 76,923 | 2,000,000 |
| Kazakhstan | 769,231 | 30,769 | 800,000 | 769,231 | 30,769 | 800,000 | 769,231 | 30,769 | 800,000 | 2,307,692 | 92,308 | 2,400,000 |
| Madagascar | 576,923 | 23,077 | 600,000 | 1,889,423 | 75,577 | 1,965,000 | 995,192 | 39,808 | 1,035,000 | 3,461,538 | 138,462 | 3,600,000 |
| Malaysia | 1,480,769 | 59,231 | 1,540,000 | 1,451,923 | 58,077 | 1,510,000 | 144,231 | 5,769 | 150,000 | 3,076,923 | 123,077 | 3,200,000 |
| Morocco | 192,308 | 7,692 | 200,000 | 384,615 | 15,385 | 400,000 | 384,615 | 15,385 | 400,000 | 961,538 | 38,462 | 1,000,000 |
| Papua New Guinea | 240,385 | 9,615 | 250,000 | 1,923,077 | 76,923 | 2,000,000 | 240,385 | 9,615 | 250,000 | 2,403,846 | 96,154 | 2,500,000 |
| Peru | 576,923 | 23,077 | 600,000 | 2,692,308 | 107,692 | 2,800,000 | 192,308 | 7,692 | 200,000 | 3,461,538 | 138,462 | 3,600,000 |
| South Africa | 480,769 | 19,231 | 500,000 | 961,538 | 38,462 | 1,000,000 | 480,769 | 19,231 | 500,000 | 1,923,077 | 76,923 | 2,000,000 |
| Tanzania | 961,538 | 38,462 | 1,000,000 | 1,538,462 | 61,538 | 1,600,000 | 961,538 | 38,462 | 1,000,000 | 3,461,538 | 138,462 | 3,600,000 |
| Thailand | 961,538 | 38,462 | 1,000,000 | 384,615 | 15,385 | 400,000 | - | - | - | 1,346,153 | 53,846 | 1,400,000 |
| Turkey | 528,846 | 21,154 | 550,000 | 528,846 | 21,154 | 550,000 | 192,308 | 7,692 | 200,000 | 1,250,000 | 50,000 | 1,300,000 |
|  | 14,060,000 | 562,400 | 14,622,400 | 17,904,231 | 716,169 | 18,620,400 | 8,864,135 | 354,565 | 9,218,700 | 40,828,365 | 1,633,135 | 42,461,500 |

It is important to consult the GEF Preparation Guidelines when completing this template

Project ID number will be assigned by GEFSEC.

Refer to the Focal Area/LDCF/SCCF Results Framework when filling up the table in item A.

GEF will finance management cost that is solely linked to GEF financing of the project. PMC should be charged proportionately   
   to focal areas based on focal area project grant amount.

Same as footnote #4.

GEF SGP participating countries have been broadly classified according to the number of years they have participated in the program and the amount of cumulative resources disbursed through the program.  There is an expectation that SGP programs in those countries with the most SGP experience (Category II countries) should be able to deliver “higher level” results within each focal area.  Suggested higher level outcome add-ons are included in the results framework as the “Category II Step-up.”

“Avoided GHG emissions” is among the GEF-5 indicators for the climate change focal area, and is a relevant outcome for SGP.  The SGP approach, and level of available resources, inherently implies that SGP cannot, by itself, generate a transformative influence on the global climate problem directly through the amount of GHG emissions avoided.  At the same time, many, if not all, SGP climate change mitigation projects directly contribute to a reduction or avoidance of GHG emissions, and these positive results should be documented.  Recognizing that addressing global climate change will require action by the entire global community, SGP’s theory of intervention (in all focal areas) is heavily predicated on its catalytic effects, and thus the SGP results framework focuses on results of this nature.

Agro-ecosystems including grasslands and rangelands

This generic project template can be customized if needed in accordance with the country needs and country programme strategy.

Details are provided in the guidelines which include what should go into the contents page

Each project should have one primary Focal Area which should be indicated. In addition projects may have secondary focal areas which should be specified in the project rationale and approach. Appropriate indicators should be selected in line with the primary and secondary focal areas of the project.

Four months after submission

Note that community participation means much more than how the community will benefit from the project. It refers to active involvement and ownership by the relevant stakeholders. Describe the specific steps that have been taken/planned to maximize this involvement.

Please indicate as many objectives as in the project and include rows as required for the project under preparations.

Refers to contributions made directly towards projects realization such as labour, materials, time and other quantifiable resources that count towards the achievement of the project results. An approximate amount should be indicated in the table.

Outline other forms of support requested from SGP which are not included in the budget. This support may be for both technical and administrative matters (and not for additional funding). This may cover areas which you need to specify such as: Consultants; Procurement; and Other (specify).

To ensure cost-effectiveness, project level monitoring and evaluation activities, including project site visits, are conducted on a discretionary basis, based on internally assessed criteria including (but not limited to) project size and complexity, potential and realized risks, and security parameters.

As per policy approved  by the GEF Council Meeting (November 10-12, 2009, Washington DC) based on GEF/C.36/4 Small Grants Programme: Execution Arrangements and Upgrading Policy for GEF-5 (see para 19 and paras 52 - 53)

For more information about global programming, please see the UNDP Programming Manual, especially Section 8.3.  The Programming Manual is available in UNDP Country Offices and at the following website:  http://www.undp.org/osg/pm/index.htm

For the purpose of the SGP and its grantmaking, CSOs refer to national and local non-governmental organizations (NGOs) with priority for community-based organizations (CBOs), indigenous peoples, farmer’s, scientific community, women’s groups, and the youth and children organizations.

https://intrafed.unops.org/ORGANIGRAMME/NAO/SGP/SGP_MANUAL/Pages/default.aspx

For a full list of participating SGP countries see: http://www.sgp.undp.org//index.cfm?module=ActiveWeb&page=WebPage&s=contry_profile

In the case of SGP Sub-regional Programmes, the Sub-Regional Coordinator (SRC) may manage the programme,     while projects are reviewed and approved by a voluntary National Focal Group (NFG) with part-time facilitation by a National Focal Person (NFP). Some countries, with substantial grantmaking,  may decide to shift to a country programme modality still linked to the subregional group with a full-time NC or a Community Program Officer and the SRC providing subregional coordination and technical support.

National Host Institution or NHI and host NGO are used interchangeably in this document because SGP country programmes commonly employ both terms.

See full-length version of SGP NC ToRs.

The NC should not accept any other functions unless a cost-sharing arrangement can be negotiated with the UNDP CO or host NGO and validated by CPMT/UNOPS.

These include the GEF National Capacity Self-Assessment (NCSA) process; the CBD National Biodiversity Strategies and Action Plans (NBSAPs); the UNFCCC National Communications; the UNCCD National Actions Programmes (NAPs); and the Stockholm Convention National Implementation Plans (NIPs).

Whilst a category of CSO for the GEF, international NGOs and private sector companies are not directly eligible for SGP support, but may co-finance the relevant national NGO, CBO, indigenous peoples’ or community projects.

Planning grants are usually in the range of $2,000 to $5,000 depending on the capacity of the proponent and additional work that have to be done. The NSC should decide on how to make the provision of planning grants in the most facilitative way such as allowing the NC to make planning grant decisions and reporting on these in NSC meetings.

In many cases, it may however be advisable to provide smaller initial amounts when the grantee-partners have lower implementation capacity.

The matching of GEF funds with co-financing is finally reckoned at the global programme level so as not to disadvantage new country programmes or those in difficult situations.

SGP Country Programmes are required to monitor the funds (grants and COB amounts) and expenditures allocated to them. Reporting tools and relevant guidelines are provided by the UNOPS SGP SOPs.