request for

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

part i: project information

| Project Title: GEF SGP Fifth Operational Phase--implementing the program using STAR resources III |  |  |  |
| --- | --- | --- | --- |
| Country(ies): | 11 | GEF Project ID: | 5736 |
| GEF Agency(ies): |  | GEF Agency Project ID: | 4561 |
| Other Executing Partner(s): | UNOPS | Submission Date: | November 14, 2014 |
| GEF Focal Area (s): |  | Project Duration(Months) | 24 months |
| Name of Parent Program (if applicable): - For SFM/REDD+ - For SGP - For PPP | GEF Small Grants Programme | Project Agency Fee ($): | 278,606 |

- Focal Area Strategy framework

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | Trust Fund | Grant Amount ($) | ### Cofinancing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 274,569 | 290,000 |
|  |  |  |  | 274,568 | 290,000 |
|  |  |  |  | 892,995 | 991,000 |
|  |  |  |  | 892,995 | 991,000 |
|  |  |  |  | 892,994 | 991,000 |
|  |  |  |  | 587,276 | 610,000 |
|  |  |  |  | 587,275 | 610,000 |
|  |  |  |  | 246,241 | 240,000 |
|  |  |  |  | 246,241 | 240,000 |
|  |  |  |  | 765,424 | 720,000 |
|  |  |  |  | 314,477 | 300,000 |
|  |  |  |  | 314,476 | 300,000 |
| Subtotal |  |  |  | 6,289,531 | 6,573,000 |
| Project Management Cost |  |  |  | 675,620 | 677,000 |
| Total project costs |  |  |  | 6,965,151 | 7,250,000 |

- Project Framework

| ### Project Objective: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Grant Amount ($) | ### Confirmed Cofinancing ### ($) |
| Conservation of Globally Significant Biodiversity Through Community-based Initiatives and Actions |  | 1. Improved sustainability of protected areas and indigenous and community conservation areas through community-based actions 2. Mainstreamed biodiversity conservation and sustainable use in production landscapes, seascapes and sectors through community initiatives and actions | At least 6 community and civil-society based projects funded supporting biodiversity conservation in indigenous and community conservation areas At least 5 community and civil-society based projects funded supporting biodiversity conservation through mainstreaming |  | 549,137 | 580,000 |
| Reduction or Avoidance of GHG Emissions While Building Climate Resilience at the Community-level |  | 3. Demonstration, development and transfer of low-GHG technologies at the community level 4. Increased energy efficient, low-GHG transport at the community level 5. Conservation and enhancement of carbon stocks through sustainable management and climate proofing of land use, land use change and forestry | At least 18 community and civil-society based projects funded supporting the transfer of low-carbon technologies At least 18 community and civil-society based projects funded supporting low-GHG transport At least 18 community and civil-society based projects funded supporting conservation and enhancement of carbon stocks |  | 2,678,984 | 2,973,000 |
| Reverse and Prevent Desertification/Land Degradation and Mitigate the Effects of Drought in Affected Areas Through Community-based Initiatives and Actions |  | 6. Maintenance or improvement in flow of agro-ecosystem and forest ecosystem services to sustain livelihoods of local communities 7. Reduction of pressures at community level from competing land uses (in the wider landscapes) | At least 12 community and civil-society based projects funded supporting maintenance or improvement of flow of ecosystem services At least 12 community and civil-society based projects funded supporting reduction of pressures from competing land uses |  | 1,174,551 | 1,220,000 |
| Sustainable Management of Transboundary Water Bodies at the Community-level |  | 8. Communities support the implementation of Strategic Action Programmes (SAPs) in trans-boundary surface and groundwater basins; 9.Communities support the implementation of Strategic Action Programmes (SAPs) in large marine ecosystems management | At least 5 community and civil-society based projects funded supporting community initiatives for sustainable management of transboundary surface and groundwater basins; At least 5 community and civil-society based projects funded supporting community initiatives for sustainable management of large marine ecosystems management |  | 492,482 | 480,000 |
| Reduce and Eliminate the Release of Harmful Chemicals into the Environment Through Community-based Initiatives and Actions |  | 10. Phase out of POPs and chemicals of global concern at community level | At least 15 community and civil-society based projects funded supporting the phase out of POPs and chemicals of global concern |  | 765,424 | 720,000 |
| Enhance communities and CSOs’ capacity to diagnose, understand and transform complex dynamic nature of global environmental problems and develop local solutions focusing on biodiversity, climate change and land degradation, while also covering international waters and chemicals |  | 11. Communities and CSOs are better informed via global, national and local knowledge sharing/learning, workshops and trainings about global challenges and local actions required 12. Ability of communities and CSOs to diagnose, understand and transform information and knowledge into local actions increased and retained | At least 126 communities and CSOs involved in knowledge sharing/learning, workhops and training with increased understanding of global environmental challenges; At least 126 communities and CSOs will have increased capacity to develop local solutions to global environmental challenges |  | 628,953 | 600,000 |
| Subtotal |  |  |  |  | 6,289,531 | 6,573,000 |
| Project management Cost (PMC) |  |  |  |  | 675,620 | 677,000 |
| Total project costs |  |  |  |  | 6,965,151 | 7,250,000 |

- sources of confirmed Cofinancing for the project by source and by name ($)

Please include letters confirming cofinancing for the projeSct with this form

| Sources of Co-financing | Name of Co-financier (source) | Type of Cofinancing | Cofinancing Amount ($) |
| --- | --- | --- | --- |
|  | Multiple |  | 800,000 |
|  | Multiple |  | 732,000 |
|  | UNDP |  | 1,874,000 |
|  | Multiple |  | 800,000 |
|  | Multiple |  | 800,000 |
|  | Multiple |  | 2,244,000 |
| Total Co-financing |  |  | 7,250,000 |

- trust fund Resources Requested by agency, Focal Area  and country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
|  |  |  | Global (STAR 3rd Tranche) | 6,965,151 | 278,606 | 7,243,757 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 6,965,151 | 278,606 | 7,243,757 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide information for this
    table.  PMC amount from Table B should be included proportionately to the focal area amount in this table.

2   Indicate fees related to this project.

- Consultants working for technical assistance components:

| ### Component | ### Grant Amount ($) | ### Cofinancing ($) | ### Project Total ($) |
| --- | --- | --- | --- |
| ### International Consultants |  |  | 0 |
| ### National/Local Consultants |  |  | 0 |

- Does the project include a “non-grant” instrument?

(If non-grant instruments are used, provide in Annex D an indicative calendar of expected reflows to your Agency 
       and to the GEF/LDCF/SCCF/NPIF Trust Fund).

part ii:  project justification

A. describe any changes in alignment with the project design of the original pif

A.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSA, NIPs, PRSPs, NPFE, Biennial Update Reports, etc.: No Table 1. Countries; Project’s consistency with relevant plans and strategies in the recipient countries.. Armenia; The project is in line with the national environmental and development agenda that call for improved land use planning and improvement of economic mechanisms for natural resource management. In particular, it is consistent with the Government Program of the Republic of Armenia for 2014-2017 (Par 2.4.4; 2.2.2.1), Second National Environmental Action Plan (Par 6.1), National Action Plan to Combat Desertification, 2010-2020 Sustainable Agricultural Development Strategy (Sec 7; 8), Armenia Development Strategy for 2014‐2025 (Par 9.4.2; Sec IX), National Forest Policy and Strategy (Chapter IV), National Forest Program and other national policies and strategies.. Burundi; The Project is in line with the national environmental strategies and plans in Burundi, including the National Strategy and National Action Plan for combating Land Degradation, the National Strategy for Environment, the National Strategy and National Action Plan for Biodiversity, the National Strategy and National Action Plan for Climate Change and the National Framework on Bio Security. These strategies are implemented among others by two national institutions which are the National Institution of Environment and Nature Conservation and the Burundi Geographical Institution.. Cameroon; The community projects to be implemented in Cameroon are in line with the national environmental and development agenda that call for support to initiatives that can improve community resilience to climate variability that increases local community vulnerability and lessens ecosystem resilience. In accordance with the national development agenda that targets the Far North region of the country which is one with the poorest local communities (including women, youth and children), these projects will improve the health of the environment while also contribute to inclusive and sustainable development of the targeted local communities. As mentioned in the Strategic Document for Growth and Employment, in the Far North of Cameroon the rate of extreme poverty is very high (about 41%) with 2 people out of 3 being very poor (Para 56, section 1.2.2.2). In the rural sector, one of the axes in favor of sustainable and inclusive growth is through the promotion of CSO actions in favor of the valorization of natural resources for poverty reduction through an inclusive, resilient and sustainable development (Para 206, section 3.1.2.3). The community initiatives to be supported will also be in line with the National Plan for Environment Management which in turn contributes to the country’s strategic document for development.. Democratic Republic of Congo (DRC); The project is consistent with DRC National Environment Action Plan which emphasizes the protection of endangered species and threatened ecosystems, reduction of pressure on tropical forests by reorganizing farming systems and promoting renewable energy technologies, improvement of agriculture and crops productivity and, involvement of local communities in sustainable natural resources and forest management. It is also in line with different national communications and environment policies concerning resilient measures regarding mitigation of effects due to climate change.. Ghana; The proposed project is in line with the following key policies the alignment with which is already articulated in SGP’s Country Programme Strategy (CPS) for its 5th Operational Phase (OP5): - The National Renewable Energy Strategy: aims at increasing the rate of adoption of efficient charcoal stove from 47% currently to 80% and efficient fuel wood stoves in urban areas from 4% currently to 30% by 2020. SGP-Ghana’s Immediate Objective 4 promotes and supports the upscaling of 1,000 innovative low carbon technologies, including cleaner and more efficient briquettes and charcoal stoves for domestic, institutional and commercial cooking and drying in both urban and rural communities - The National Forest and Biodiversity Strategy: aims at expanding the protected area system by including inland and coastal wetlands, fringe and riverine forests and sensitive areas such as slopes and sacred groves under sustainable management. SGP-Ghana’s Immediate Objective 1 is improving the sustainability of protected areas and indigenous and community conservation areas through community-based actions that support establishment of Community Resource Management Areas (CREMAs), upscaling the conservation of hippos, and supports the national preparation for REDD+ and agriculture carbon. - The Revision of the National Biodiversity Strategies and Action Plans (NBSAPs) in line with the CBD‘s new strategic plan, focus on national reporting, and implementation of guidance related to the Clearing House Mechanism (CHM). SGP-Ghana’s Immediate Objective 2 is mainstreaming biodiversity conservation and sustainable use into production landscapes, through community initiatives and actions in bio-enterprise development and integrating traditional ecological knowledge to explore new forms of co-management systems. - National land use and soil management, management of vegetative cover, wildlife and biodiversity management program. SGP-Ghana’s Immediate Objective 5 supports the conservation and enhancement of carbon stocks through conservation of natural regeneration areas, wildfire prevention, and communal afforestation (woodlots and plantations).. Kyrgyzstan; The protection of rare and endangered species, such as the snow leopard and the Aigul flower is fully in line with the national priorities as reflected in the National Strategy for Conservation of Biological Diversity in the Kyrgyz Republic adopted in March 2014. The proposed work is also consistent with the National Strategy for Sustainable Development of the Kyrgyz Republic, and with the National Strategy for Transition to Sustainable Development, both adopted via the President’s decree in early 2013. Further, the Global Snow Leopard Conservation Forum held in Bishkek (October 22-23, 2013) led to the endorsement of the Bishkek Declaration on Conservation of Snow Leopards and Kyrgyzstan is keen to further promote its leadership position in this important initiative though a high level policy dialogue, transboudnary cooperation, and concrete local level interventions aimed at improving peoples’ livelihoods through the prism of improving biological diversity and protecting the larger environment. The global program on snow leopard conservation has been initiated under the leadership of the President of the Kyrgyz Republic, Mr. Almazbek Atambaev and as such, enjoys high political support of the country’s government. The government of the Kyrgyz Republic also has identified development and further application of small and micro hydro power as a priority to tackle environmental issues, poverty and other development challenges. This is especially important for the development of remote communities and constitutes a big step towards the achievement of the Millennium Development Goals. In addition, the proposed project is fully consistent with the law of the Kyrgyz Republic on energy and the government’s plans to diversify peoples’ access to alternative/renewable energy sources. Finalization and adoption of the “Bio-safety Law” is highly needed, as at present there is an uncontrolled import of products containing living modified organisms (LMOs) in the Kyrgyz Republic due to absence of a regulatory law on bio-safety. The risks of LMOs penetration into the market of Kyrgyzstan is high and therefore, needs to be addressed.. Maldives; The objectives and priorities identified in this project are very much in line with the country’s priorities as identified in the Maldives Strategic Action Plan 2009-2013. In particular, these relate to the environmental conservation and economic development goals of the Strategic Action Plan, together with efforts towards addressing climate change, disaster risk management, fisheries, tourism, energy, water and sewerage, and gender parity. In addition Maldives is a signatory to the global Rio Conventions, and the SGP country programme can help the country fulfill its obligations and achieve the Conventions’ objectives, which are closely related to those of GEF-5 and national priorities.. Mongolia; The project is line with three important policy documents, namely “National Programme to Combat Desertification” (14 April, 2010), “National Programme on Climate Change” (6 January 2011) and the “Green Development Policy (May 2014), all approved by the Parliament of Mongolia among many other policy documents issued since 1990s, when Mongolia started shifting to a market economy. Activities to be carried out by the project are also in line with objectives and actions related to community groups and local governments in First Phase Action Plan to implement the National Programme to Combat Desertification, particularly in sections 5.2.1 through 5.2.5, where NGOs, CBOs, and specifically herder groups in the steppe and Gobi areas are obliged/requested to take action towards combating land degradation and desertification. Also the First Phase Action Plan to implement National Programme on Climate Change approved by the Government in 2011 includes a range of activities to reduce GHG emissions, build climate resilience, develop and transfer low-GHG technologies and increase energy efficiency at the community level. The recent Green Development Policy document refers to green development as a pattern of development that reduces poverty through an inclusive economy in which resources are used efficiently and without waste, supports ecosystems services, lowers GHG emissions and waste, and contains a whole range of activities to be addressed and contributed to by civil society and community groups.. Thailand; The project is in line with and supports the National Strategy for Climate Change under the supervision of the Ministry of Energy and the Ministry of Natural Resources and the Environment. There are two areas in particular where SGP can contribute: I. To increase proportion of renewable energy to be 20 % of the final national energy consumption with in the year 2022 so as to (1) reduce expense of energy import (2) reduce risk in electricity generation from over-burning natural gas , and (3) reduce/avoid emission of green house gas II. To increase carbon sinks by reforestation, afforestation, and urban green areas. The SGP programme in Thailand has been working closely with the two relevant ministries, and includes their staff as members of the SGP National Steering Committee and Technical Advisory Group.. Ukraine; The project is in line with the priorities identified in several national strategies and policies. Ukraine is a party to the UNCCD and the Parliament of Ukraine has ratified the Law №61-IV “On joining of Ukraine to the UNCCD”. Ukraine is an Annex 5 country to the Convention. The Law of Ukraine on National Environmental Strategy till 2020, approved by the Parliament in 2011 (№ 2818-VI), and the National Action Plan, approved by the Cabinet of Ministers of Ukraine in 2011 (№ 577-р), identify among the country’s priorities the development of the National Programme on combating desertification and land degradation, and its implementation. Currently, the Government is formulating the Draft National Programme. The Law of Ukraine on soil protection regulates legislative, economic and social basis for land protection and combating land degradation in Ukraine. The Law of Ukraine, from 1991 (№ 796-ХП) on "The legislative regime of the territories, suffering from nuclear pollution as a result of Chernobyl catastrophe” is also relevant. The Government has developed a Programme of Development of Forests and Forest Industry Complexes till the year 2015 to improve forest resources management and protection. A Forestry Code was established in 1994. The Government has developed and started to implement the Programme (Conception) of Development of Land Use, the State and Regional Programmes of Land Protection from Water and Wind Erosion, and the State Programme of Natural Environment Protection and Rational Use of Natural Resources. A Land Code was established in 1992. Ukraine became Party to the UN Framework Convention on Climate Change (UNFCCC) in 1997 and ratified the Kyoto Protocol in 2004, committing itself to stabilizing its greenhouse gas (GHG) emissions for the period of 2008-2012 at 1990 level. The Government of Ukraine has taken some important steps to address climate change since 2005. In August 2005, the Government of Ukraine approved the National Plan on Approaches for the Implementation of the Provisions of the Kyoto Protocol to the UNFCCC. In February 2006 the Cabinet of Ministers approved regulation on evaluation, approval and implementation of projects intended to decrease the amount of anthropogenic greenhouse emissions according to the Kyoto Protocol. In April 2006 the Cabinet of Ministers approved regulation on functioning of a national system of evaluation of anthropogenic emissions and absorption of greenhouse gases that are not regulated under Montreal Protocol on ozone-depleting substances. Currently, upon the request of the Government of Ukraine, the GEF FSP “Capacity Building for Low Carbon Growth in Ukraine” is working on the concept of Ukraine's low carbon growth strategy by 2020 and 2050. The GEF SGP will collaborate with this project and contribute to the strategy development at the local level through the participation of CSOs.. Vietnam; This project is in line with the national environmental strategies and plans, including the Biodiversity Action Plan, National Target Program to Respond to Climate Change, National Energy Efficiency Programme, National Action Plan to Combat Land Degradation and Desertification, National Green Growth Strategy, National Forest Development Strategy and National REDD+ Action Programme. The projects supported through SGP will help to mainstream biodiversity conservation and sustainable use into production landscapes, seascapes and sectors through community initiatives and actions, support the conservation and enhancement of carbon stocks through sustainable management and climate proofing of land use, land use change and forestry, promote the demonstration, development and transfer of low carbon technologies at the community level and improve flow of agro-ecosystem and forest ecosystem services to sustain livelihoods of local communities..

A.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities.  No change

A.3 The GEF Agency’s comparative advantage: No change

A.4. The baseline project and the problem that it seeks to address:  No Change

A. 5. Incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:   No change

A.6  Risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and measures that address these risks: No change

A.7. Coordination with other relevant GEF financed initiatives  No change

B. additional information not addressed at Pif stage:

B.1 Describe how the stakeholders will be engaged in project implementation. SGP operates through a multi-stakeholder approach engaging a range of stakeholders including NGOs, CBOs, indigenous people, the private sector, government, academia, and donor partners. SGP country programs’ decision making body is the National Steering Committee, which is composed of government agencies, civil society leaders, research institutes, donors and private sectors. Such a multi-stakeholder committee plays a critical role in the entire program cycle of SGP, including strategy development, grant review and approval, as well as promoting policy influence, networking, and partnership development. During project implementation, a broad range of stakeholders are engaged as active partners during grant implementation, including inter alia research institutes, local and municipal governments, international NGOs, as well as national and international volunteers. Such multi-stakeholder cooperation is sometimes formalized through legal agreements, and often is undertaken informally through provision of technical assistance, parallel co-financing, information sharing, knowledge dissemination, networking as well as replication and upscaling. With regard to indigenous peoples and marginalized populations, SGP follows a set of principles that advocate for a flexible, time sensitive, and simple project cycle in order to allow these "difficult to reach" groups to access SGP support. The programme has pioneered numerous user-friendly modalities to work with poor and marginalized groups including alternative proposal formats such as participatory video, photo stories, and community theatre, and allowances are made for concept and project submission in local and vernacular languages. SGP also allows for flexible disbursement terms to cope with indigenous peoples’ culture, customs and seasonal movements. Through stakeholders’ workshops organized by SGP, CSOs are able to learn of SGP projects and activities and provide inputs on how to improve on them.

B.2 Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF):  The communities targeted by SGP are often poor and vulnerable, and typically have low levels of technical and institutional capacity to adequately address global environmental problems.  According to the Joint Evaluation (2008), more than 60% of SGP grants target poor communities in participating countries, which have the greatest need for assistance. Indigenous peoples, who have the knowledge and experience to create sustainable solutions to environmental challenges, are also targeted by at least 15% of SGP grants.  Approximately a quarter of SGP grants specifically support women, who constitute another priority target group.  SGP helps utilize the full potential of women and men and transform marginal and vulnerable sectors into active actors for sustainable development.  The second  independent evaluation report of SGP noted:

"Access to and acceptance by communities - the GEF/SGP’s principal clients - almost invariably requires an emphasis on activities which communities perceive are closely linked to their own immediate concerns, a characteristic by no means limited to poorer countries. Ask a low-income rural community in the developing world what their priority problems are, and the answer is unlikely to feature biodiversity or climate change. Few, if any, communities begin with an understanding or awareness of these terms."  (SGP Second Independent Evaluation Report, p.p. 23)

SGP works to develop sustainable livelihoods, including through the creation and support for small and medium enterprises at the community level that contribute to sustainable resource use, generate local benefits from environmental conservation measures, and promote innovative and entrepreneurial approaches to critical problems such as energy conservation and generation.  Thus, where poverty once forced communities to take a short-term view and an exploitatively opportunistic approach to natural resource utilization, the realization of livelihoods and enterprises linked to natural resources creates a desire for a long term view and careful resource management. In SGP communities, sustainable livelihoods and enterprises create the capacity and also provide additional resources for environmental protection. Thus, a key factor in the success of SGP projects is the linkage of the generation of socioeconomic benefits with the generation of global environmental benefits, which can be achieved in many different and creative ways depending on the specific issue targeted.

SGP will continue to apply its gender mainstreaming approach, ensuring that priority is given to women led projects and those with high participation of women, and gender specific components.  SGP makes efforts to seek gender disaggregated information to the extent possible about project beneficiaries and participants.  The National Steering Committees of SGP in each country are curently being strengthened to ensure designation of a gender focal point on each NSC to track grant making towards women focused projects.

B.3. Explain how cost-effectiveness is reflected in the project design: As noted by the Joint Evaluation of the SGP in 2007, "GEF SGP is a cost-effective instrument for the GEF to generate global environmental benefits through NGOs and community-based organizations" (Joint Evaluation 2007, pp. 46), and "The efficiency of outcome ratings for the GEF SGP grants appear to be better than those for the FSPs and MSPs” (Joint Evaluation 2007, pp. 50). Furthermore, the GEF Council paper (GEF/C.33/5, p. 1) "Small Grants Program: Follow up to the 2007 Joint Evaluation" recommended a "level of management costs on the basis of services rendered and cost efficiency rather than a set percentage". The principle of determining SGP management costs on the basis of services rendered was recently reconfirmed by the GEF Secretariat and UNDP in GEF5. Among the services provided by SGP which go beyond simply grant administration, are notably its focus on capacity building of grantees (working with some of the poorest and low capacity groups who are at the same time more vulnerable to environmental challenges), strengthening networking of civil society organizations, learning and knowledge management, partnership building and resource mobilization with a view to scaling up and strengthening sustainability of projects. In addition, SGP will further enhance the programme’s and grant projects’ cost efficiency by actively exploring opportunities to: 1) be utilized as delivery mechanism for community/NGO components of FSPs – whereby it would have a share of additional management budgets while providing an on-the-ground mechanism to deliver a greater volume of grants; 2) raise additional co-financing from non-GEF sources in ways that management costs are defrayed. At the project level, GEF SGP will engage voluntary NSC members to provide technical and management assistance to communities, obtain local governments and other partners’ co-financing and support, ensure linkages and synergies with other ongoing activities and other proper activities to further improve projects’ cost effectiveness.

C.  describe the budgeted m &e plan:  SGP’s M&E plan is designed to address how SGP will meet reporting requirements, as well as providing information at the project, country and global level for adaptive management, and contributing to the capture of knowledge.  M&E reports and information generated by SGP country programmes are shared with national GEF focal points and convention focal points and NSCs.  At the global level, SGP issues an Annual Monitoring Report which draws upon national reports from each SGP country programme and tracks SGP's OP5 indicators.  SGP also contributes to reporting to the conventions and to GEF and UNDP as required.  M&E activities outlined in the plan are undertaken as necessary and appropriate to ensure cost-effectiveness.  M&E activities and tasks are commensurate with the size of projects and take into consideration other associated factors such as complexity and risks involved.  SGP's monitoring and evaluation system is in-line with GEF and UNDP monitoring and evaluation policies, including consistency with UN Evaluation Group standards and norms, and complies with all GEF M&E minimum standards, including: SMART indicators for implementation and results, baseline information, identification of required programme reviews and evaluations, specified roles and responsibilities, and a budget allocated to support M&E activities.

In OP5 SGP's strategic objectives include specific outcomes on M&E within the framework of capacity development, including enhancing SGP stakeholders and partners capacity to apply M&E methodologies and tools.  At the global level, SGP is continuing to improve the SGP database, and facilitate the tracking of outcomes across the portfolio. The SGP OP5 Results Framework is attached as Annex A to this document which inlcudes the results aniticpated in the ongoing operational phase to which this curent project will be expected to contribute.  The indicators identified in this results framework are the global level indicators designed to meet reporting on GEF-5 strategic objectives.  At the country and project levels appropriate additional focal area specific results-oriented indicators are applied to ensure projects achieve expected results, and to track successful approaches, including socio-economic outcomes where possible.  To support results reporting linked to the GEF-5 results framework, SGP will continue to improve indicators and mechanisms for reporting on results.

Table 2 below provides a list of SGP monitoring and reporting requirements at the project, country and global level.

Table 2

| Item | M&E Activity | M&E Level and Type | Responsible Parties | Budget Source | Timeframe |
| --- | --- | --- | --- | --- | --- |
| Project Level |  |  |  |  |  |
| 1 | Participatory Project Monitoring | Project; Implementation | Grantee | Covered under project grant amount | Duration of project |
| 2 | Baseline Data Collection | Project; Results | Grantee | Covered under project planning grant amount or project grant amount | At project concept planning and proposal stage |
| 3 | Project Progress and Financial Reports (2-3 depending on agreed disbursement schedule) | Project; Implementation | Grantee | Covered under project grant amount | At each disbursement request |
| 4 | Project Workplans | Project; Implementation | Grantee and NC | Covered under project grant amount | Duration of project |
| 5 | NC Project Proposal Site Visit (as necessary / cost effective) | Project; Implementation | NC | Variable | Before project approval, as appropriate |
| 6 | NC Project Monitoring Site Visit (as necessary / cost effective) | Project; Implementation AND Results | NC | Variable | On average once per year, as appropriate |
| 7 | NC Project Evaluation Site Visit (as necessary / cost effective) | Project; Implementation AND Results | NC | Variable | At end of project, as appropriate |
| 8 | Project Final Report | Project; Implementation AND Results | Grantee | Covered under project grant amount | Following completion of project activities |
| 9 | Project Evaluation Report (as appropriate) | Project; Implementation AND Results | NC (with contracted independent external party) | Variable | Following completion of project activities |
| 10 | Prepare project description to be incorporated into global project database | Project; Implementation | PA and NC | Covered under country program operating costs | At start of project, and ongoing as appropriate |
| Country Level |  |  |  |  |  |
| 11 | Country Programme Strategy Review | Country; Implementation | NC, NSC, CPMT | Included in NC, NSC, and CPMT and other staff time | Once per operational phase |
| 12 | Strategic Country Portfolio Review | Country; Implementation AND Results | NSC | Covered under country program operating costs | Once per operational phase |
| 13 | NSC Meetings | Country; Implementation AND Results | NC, NSC, UNDP Country Office | Covered under country program operating costs | Minimum twice per year |
| 14 | Annual Country Report Surveys | Country; Implementation AND Results | NC presenting to NSC, and submission to CPMT | Covered under budgeted staff time | Once per year |
| 15 | Financial Four-In-One Report | Country; Implementation | NC/PA | Covered under budgeted staff time | Quarterly |
| 16 | Audit | Country; Implementation | UNOPS / External Contractor | Budgeted under global operating budget | As required on risk-assessment basis |
| Global Level |  |  |  |  |  |
| 17 | SGP Database | Global; Implementation AND Results | CPMT | Global operating budget and M&E budget | Ongoing |
| 18 | SGP Annual Monitoring Report | Global; Implementation AND Results | CPMT with inputs from NCs | Global operating budget and M&E budget | Annually |
| 19 | Inputs to UNDP annual development assistance evaluations in selected countries | Global; Results | CPMT, UNDP Evaluation Office | Covered under budgeted staff time; global operating budget and M&E budget | Ad Hoc |
| 20 | SGP Reporting to Conventions | Global; Results | CPMT through GEF Secretariat | Covered under budgeted staff time and global operating budget | At least one month prior to deadline for GEF Secretariat reporting to conventions (varies by convention) |
| 21 | Annual Work Plans | Global; Implementation | CPMT | Covered under budgeted staff time and global operating budget | Annually |
| 22 | Global Portfolio Monitoring and Oversight | Global; Results AND Implementation | CPMT | Covered under budgeted staff time and global operating budget | Ongoing |
| 23 | Programme Delivery Reports (GEF Financial Reporting) | Global; Implementation | UNOPS to UNDP-GEF | Covered under UNOPS operating costs | Quarterly |
| 24 | Global Thematic Portfolio Reviews | Global; Results | CPMT | Global operating budget and M&E budget | Ad Hoc |

PART iII: Approval/endorsement by gef operational focal point(s) and gef agency(ies)

- Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): ): (Please attach the Operational Focal Point endorsement letter(s) with this form. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| H.E. Aram HARUTYUNYAN | Minister | Ministry of Nature Protection of Armenia | 03/07/2014 |
| Mr. Remy NDAGIJIMANA | Permanent Secretary | Ministry of Water, Environment, Land Management and Urbanism of Burundi | 03/17/2014 |
| Mr. Justin NANTCHOU NGOKO | Director | Ministry of Environment and Nature Protection of Cameroon | 03/10/2014 |
| Mr. Vincent KASULU SEYA MAKONGA | Director | Ministere de L'Environnement, Conservation de la Nature, Eaux et Forets of Congo, DRC | 03/19/2014 |
| Mr. Fredua AGYEMAN | Director | Ministry of Environment, Science, Technology and Innovation of Ghana | 03/17/2014 |
| Mr. Sabir ATADJANOV | Director | State Agency on Environment Protection and Forestry of Kyrgyzstan | 02/28/2014 |
| Ms. Miruza MOHAMED | Director | Ministry of Environment and Energy of Maldives | 03/19/2014 |
| Mr. Altangerel ENKHBAT | Director | Ministry of Nature, Environment and Tourism of Mongolia | 03/17/2014 |
| Mr. Chote TRACHU | Permanent Secretary | Ministry of Natural Resources and Environment of Thailand | 03/19/2014 |
| Mr. Vadym POZHARSKYI | Deputy Head | State Environmental Investment Agency of Ukraine | 01/17/2014 |
| Dr. Mr. Nam Thang DO | Vice Minister | Ministry of Natural Resources and Environment of Vietnam | 03/18/2014 |

B.  GEF agency(ies) certification

This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for CEO endorsement/approval of project.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu, UNDP-GEF Executive Coordinator |  | 11/13/2014 | Delfin Ganapin | 646-781-4383 | delfin.ganapin@undp.org |

GEF_CEOENDR_52

ANNEX A:  PROJECT RESULTS FRAMEWORK (either copy and paste here the framework from the Agency document, or provide reference to the page in the project document where the framework could be found).

| SGP OP5 Objectives | SGP OP5 Outcomes | SGP OP5 Results Indicators | OP5 Target | Sources of Verification | Assumptions |
| --- | --- | --- | --- | --- | --- |
| SGP OP5 Immediate Objective 1: Improve sustainability of protected areas and indigenous and community conservation areas through community-based actions | SGP BD Outcome 1.1: Improved community-level actions and practices, and reduced negative impacts on biodiversity resources in and around protected areas, and indigenous and community conservation areas Category II Step-up: Good practices replicated and scaled up outside SGP supported areas, as appropriate SGP BD Outcome 1.2: Benefits generated at the community level from conservation of biodiversity in and around protected areas and indigenous and community conservation areas Category II Step-up: Sustainable financial mechanisms for benefit generation identified and piloted, as appropriate SGP BD Outcome 1.3: Increased recognition and integration of indigenous and community conservation areas in national protected area systems Category II Step-up: Information about recognition of indigenous and community conservation areas within national level protected area systems shared through an established network, as appropriate SGP BD Outcome 1.4: Increased understanding and awareness at the community-level of the importance and value of biodiversity Category II Step-up: Environmental education programs formally integrated in school curricula, as appropriate | Number and hectares of ICCAs and other PAs positively influenced through SGP support Number of community members with improved livelihoods related to benefits from protected areas Number of significant species with maintained or improved conservation status Number and hectares of significant ecosystems with maintained or improved conservation status Number of communities with increased understanding and awareness | At least four ICCAs and PAs positively influenced through SGP. At least 80 community members with improved livelihoods related to benefits from ICCAs and PAs 4 significant species benefited 4 significant ecosystems with conservation aware communities resulting in their maintained or improved conservation status 40 hectares of significant ecosystems with maintained or improved conservation status More than 8 communities with increased understanding and awareness | GEF SGP database, project reports and monitoring visits SGP case studies SGP grantee data from innovative monitoring approaches | Governments and international agencies commit to CBD obligations regarding local and indigenous populations |
| SGP OP5 Immediate Objective 3: Promote the demonstration, development and transfer of low carbon technologies at the community level | SGP CC Outcome 3.1: Innovative low-GHG technologies deployed and successfully demonstrated at the community level Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate SGP CC Outcome 3.2: GHG emissions avoided | Number of countries with demonstrations addressing community-level barriers to deployment of low-GHG technologies Number of national or international partners or agencies are aware of SGP practices and lessons | 5 countries with demonstrations addressing community-level barriers to deployment of low-GHG technologies At least 10 national or international partners or agencies are aware of SGP practices and lessons | GEF SGP database, project reports and monitoring visits SGP case studies | Progress will continue for complimentary initiatives by GEF and other development agencies to removing market barriers and improving energy access policies particularly at the local level. |
| SGP OP5 Immediate Objective 5: Support the conservation and enhancement of carbon stocks through sustainable management and climate proofing of land use, land use change and forestry | SGP CC Outcome 5.1: Sustainable land use, land use change, and forestry management and climate proofing practices adopted at the community level for forest and non-forest land-use types Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate SGP CC Outcome 5.2: Restoration and enhancement of carbon stocks in forests and non-forest lands, including peatland Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate SGP CC Outcome 5.3: GHG emissions avoided | Hectares under improved sustainable land management and climate proofing practices Hectares of forests and non-forest lands with restoration and enhancement initiated | 500 hectares under improved sustainable land management and climate proofing practices Restoration and enhancement of 250 hectares of forests and non-forest lands initiated | GEF SGP database, project reports and monitoring visits SGP case studies | Change is possible on the ground at the community level whether or not national and international policy measures are in place |
| SGP OP5 Immediate Objective 7: Reduce pressures at community level from competing land uses (in the wider landscapes) | SGP LD Outcome 7.1: Improved community-level actions and practices, and reduced negative impacts in land use frontiers of agro-ecosystems and forest ecosystems (rural/urban, agriculture/forest) Category II Step-up: Partnerships with private sector, as appropriate | Number of community members with improved actions and practices that reduce negative impacts on land uses | At least 1,000 community members having improved actions and practices that have reduced pressure on land uses | GEF SGP database, project reports and monitoring visits | Government policy is in place and supportive of community-level sustainable land management practices |
| SGP OP5 Immediate Objective 8: Support transboundary water body management with community-based initiatives | SGP IW Outcome 8.1: Effective and climate resilient community-based actions and practices supporting implementation of SAP regional priority actions demonstrated Category II Step-up: Scaling-up and replication of good practices and lessons learned, as appropriate SGP IW Outcome 8.2: Synergistic partnerships developed between SGP stakeholders and transboundary water management institutions and structures supporting implementation of SAP regional priority actions Category II Step-up: Scaling-up and replication of good practices and lessons learned, as appropriate | Number of SAPs to which SGP is providing implementation support Number of regional transboundary water management processes to which SGP is contributing good practices and lessons | 2 SAPs for which SGP is supporting on the ground implementation of regional priority actions 2 regional transboundary water management processes to which SGP is contributing good practices and lessons | GEF SGP database, project reports and monitoring visits | Regional water body management organizations are institutionally willing and able to engage with community-level stakeholders |
| SGP OP5 Immediate Objective 9: Promote and support phase out of POPs and chemicals of global concern at community level | SGP CH Outcome 9.1: Improved community-level initiatives and actions to prevent, reduce and phase out POPs, harmful chemicals and other pollutants, manage contaminated sites in an environmentally sound manner, and mitigate environmental contamination Category II Step-up: Scaling-up and replication of good practices and lessons learned, as appropriate | Tons of solid waste avoided from burning Tons of obsolete pesticides disposed of appropriately Number of countries where SGP is contributing to the implementation of national plans and policies to address POPs, harmful chemicals and other pollutants | 5 tons of solid waste avoided from burning 2 tons of obsolete pesticides disposed of appropriately 3 countries where SGP is contributing to the implementation of national plans and policies to address POPs, harmful chemicals and other pollutants | GEF SGP database, project reports and monitoring visits | There are adequate opportunities for community-level stakeholders to address POPs, harmful chemicals, and other pollutants Community-level stakeholders develop the awareness and capacity to proactively address POPs, harmful chemicals and other pollutants |
| SGP OP5 Immediate Objective 10: Enhance and strengthen capacities of CSOs (particularly community-based organizations and those of indigenous peoples) to engage in consultative processes, apply knowledge management to ensure adequate information flows, implement convention guidelines, and monitor and evaluate environmental impacts and trends | SGP CD Outcome 10.3: Increased public awareness and education at the community-level regarding global environmental issues SGP CD Outcome 10.4: Capacity of CBOs and CSOs strengthened to support implementation of global conventions SGP CD Outcome 10.5: Increased application of community-based environmental monitoring SGP CD Outcome 10.6: Evaluation of SGP projects and programs against expected results strengthened, including increased capacity of CBOs and CSOs to apply relevant evaluation methodologies | Number of demonstrations and piloted examples of community-based environmental monitoring systems used in SGP projects Quantity and quality of evaluation documentation of expected project results, and unexpected effects Number of CBOs and CSOs demonstrating understanding of the role of evaluation through application of relevant evaluation methodologies | Capacities of more than 200 CSOs and CBOs strengthened At least 85% of projects incorporate M&E activities in their design At least 70% of projects specify sufficient indicators which are covered in completion reports |  |  |
| Cross-Cutting Results: Livelihoods and Gender | SGP’s Results Framework for OP5, as approved by the SGP Steering Committee, does not include specific objectives on livelihoods and gender. Nonetheless, SGP does produce positive results in these areas, which contribute to the overall achievement of Global Environmental Benefits through sustainable development. Generally, SGP seeks to improve livelihoods through increasing local benefits generated from environmental resources, and mainstream gender considerations in community-based environmental initiatives. | Percentage of projects that include gender analysis or incorporate gender relevant elements in a positive manner Percentage of projects with appropriate gender balance of participants and target beneficiaries Percentage of projects that include socioeconomic analysis Number of community members with sustained livelihood improvement resulting from SGP support | 100% of projects that include gender analysis or incorporate gender relevant elements in a positive manner (baseline TBD in OP5) 100% of projects with appropriate gender balance of participants and target beneficiaries (baseline TBD in OP5) 100% of projects that include socioeconomic analysis (baseline TBD in OP5) 1,000 community members with sustained livelihood improvement resulting from SGP support | GEF SGP database, project reports and monitoring visits SGP case studies | All SGP projects have sufficient scope to include gender mainstreaming |

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

1.  Comment from France: Most of capacity building outcomes are anticipated through workshops and trainings. We suggest to support the development of capacity building output within CBOs and CSOs’ small grant projects and to experience direct “learning by doing” capacity building results.

Response:

Indeed capacity development is incorporated as a project element in all SGP demonstration projects.  Capacity development and learning underpin all SGP activities.  An integral understanding of how local communities manage change combined with innovative approaches to capacity development—at all levels and among a broad spectrum of grantees and partner organizations—have proven critical to achieve environment and sustainability goals.  Almost all SGP-supported projects include capacity development, communications and experience consolidation and learning elements.  The fact that SGP supports small projects, with a trial and error approach, demonstrates its strategic niche as a capacity development mechanism in the GEF system.  Many partners consider SGP’s capacity development approach one of its most valuable features, because SGP projects (small scale) can afford to fail.  SGP’s “learning-by-doing” approach builds capacity across the board, and prepares communities to test, fail, succeed and upscale.  The capacity development results in the entire focal area portfolios are reported through focal area results.

In addition to the built-in capacity development activities in individual projects, a dedicated 10% of the funding is devoted to focused capacity development grants that can build capacity through stakeholder workshops, and efforts for improved communications, networking, monitoring, and partnership development.  The results in this dedicated capacity development are reported under the focal area of capacity development in SGP’s Annual monitoring reports.

2.  Comment from Germany: Germany suggests a more detailed description of the catalytic character of the SGP contribution for all eleven country cases.

| Countries | Responses |
| --- | --- |
| Armenia | With its limited grant resources, SGP-Armenia has been pioneering in solving complex environmental and socio-economic issues through the introduction of innovative and non-traditional approaches to problem solving at the community level. These small-scale successful practices and proved community-based approaches, can be viable alternatives to traditional ones, and are being adopted and scaled-up by governments, donors and agencies as well as businesses. In Armenia, solar energy use and energy efficient housing initiatives demonstrated by SGP projects have been spread out through replication and scaling up in different regions of the country by other donors, businesses and individuals. An innovative and low-cost wastewater treatment technology successfully piloted and tested for the first time in Armenia and the South Caucasus Region is another example of SGP’s interventiona, which is expected to have a catalytic effect by producing further uptake. The decentralized problem-solving approach demonstrated with SGP support through the use of non-traditional wastewater treatment eco-technology is now being scaled-up by the Global Water Partnership through DFID funding and is currently the object of intense discussion among the country-level stakeholders: government, other communities and donors. Finally, the catalytic effect of the SGP will be enforced through the Grantmaker+ support services to be provided by SGP-Armenia in the 6th Operational phase. The SGP country programme, as an incubator of innovative ideas and cost-effective approaches, will serve as a platform for knowledge transfer and experience exchange processes, which will be facilitated by the SGP team. |
| Burundi | Small grants can make big impacts as SGP projects are easy to implement and results of these projects can be easily documented and replicated. As SGP projects are catalytic projects, results and best practices can be replicated at national level by local communities through support of other donors. SGP projects can also serve to test models and approaches and generate good practices which can be adopted and used by environmental stakeholders and contribute to the national environmental policy. Through some national ceremonies made around SGP projects, SGP can be very well known at national level and also then serve as a model in best practices. All these aspects mentioned above can help the small grants to make big impacts. SGP Burundi will aim to develop best practices and enhance partnerships with other environmental conservation stakeholders. It will also enhance local community capacities and develop solutions focusing on biodiversity, climate change, land degradation, international waters and chemicals. SGP Burundi will also try to mobilize resources, increase the visibility of its activities and try to respond to the national environmental policy. |
| Cameroon | SGP Cameroon will use the additional funds to reinforce the catalytic character of the work being undertaken in the two focal areas, for which funding is provided. In the Climate Change mitigation area SGP projects focus on “Innovative low‐GHG technologies deployed and successfully demonstrated at the community level”. Projects supported by SGP demonstrate win-win opportunities for reduction of GHG emissions while contributing to local livelihoods. SGP projects support design, production and popularization of improved low emission technologies (such as use of cook stoves, domestic biogas units) as well as supporting carbon sequestration efforts undertaken on community lands. In the Land degradation focal area, the additional funds will support ongoing efforts towards “improved community‐level actions and practices, and reduced negative impacts on agro‐, and forest ecosystems and ecosystem services demonstrated to sustain ecosystem functionality”. SGP has played a catalytic role by targeting severe land degradation in areas highly dependent on agro-silvo-pastoral farming system with noticeable reduced agricultural yields due to soil erosion due to rains water, loss of fertility from soil mining, declining soil organic matter content, and overgrazing. SGP efforts will promote sensitization and training on soil fertility improvement using organic manuring or compost and agroforestry species, as well as demonstration of anti-erosive structures that retain soil and water such as contour stone bunds and small permeable rock dams. SGP projects in the LD focal area will seek to establish synergies with projects for the enhancement of carbon stocks in the CC area and contribute to the improvement of livelihoods and promote improved skills for sustainable agriculture and natural resource management. |
| DR Congo | SGP-DR Congo will consolidate all the results of projects in the OP4-OP5 period and expand its scope of work to a new area in the eastern part of DRC. The consolidation of results will look into the effects and impacts of projects on the ecosystems. This stock taking will also address scaling up and mainstreaming of funded activities. Lessons learned from the geographic focus areas covered in OP4-OP5 will be replicated to the new areas which should be alongside the National Road One (RN1). This road cuts across numerous cities, and the region is affected by drivers of deforestation, which can be addressed through support from SGP mitigative actions in collaboration with local communities. Some of the ecosystems known as cities’ supplier basins in ecosystem services will be targeted for SGP intervention. SGP-DR Congo will focus its activities in the main deforestation areas of the region. |
| Ghana | Following the revision of the National Biodiversity Strategies and Action Plans (NBSAPs) in line with the CBD‘s new strategic plan adopted at COP-10, national reporting, and implementation of guidance related to the Clearing House Mechanism (CHM), the remaining STAR funds are being allocated to SGP Ghana to undertake the following activities in biodiversity conservation and climate change. SGP-Ghana will work on biodiversity conservation and rural livelihoods reinforcement within the White and Black Volta basin ecosystem. The project aims at addressing current challenges in biodiversity conservation, and rural livelihoods faced by populations living on the fringes of the Black and white Volta basin which covers an of 4,840 sq. kilometres, and is home to over 150 resident elephants, 100 hippotamuses, 30 buffaloes, as well as other endangered wildlife, fauna and flora species identified within the basin. The project will focus on women, as change agents, by building their skills in biodiversity conservation, assisting them in planting depleted areas with native medicinal and ethno-veterinary tree species, and in honey production. The project will establish inter-community and inter-district networks to support and sustain project results, which will be upscaled into 60 more fringe communities. SGP-Ghana will develop local capacities to integrate the Convention on Biological Diversity (CBD) obligations into local level planning processes and support low carbon growth by helping communities within the transitional zone to improve on their climate change adaptive capacity, reduce their vulnerability and contribute to improving the resilience of their ecosystems under the sustainable land management projects. The programme seeks to conserve the wetlands and its biodiversity through facilitating the creation of local institutions for conservation, improving wetland management practices, improving livelihoods in fringe communities and deepening stakeholder participation in land use planning at the district level which will be upscaled to 14 other districts within the landscape. |
| Kyrgyzstan | SGP-Kyrgyzstan will focus on protecting mountain ecosystems, aiming to demonstrate good practices of biodiversity conservation and development of eco-tourism across several small projects. Buffer zones of the nature protection areas will be chosen as target areas. Special attention will be paid to promotion of the renewable sources of energy and energy-efficient technologies with the aim to contribute to saving mountain forests from cutting and reduce CO2 emissions. Through multi-stakeholder dialogues, GEF SGP Kyrgyzstan plans to support the Global Snow Leopard Initiative at the level of local communities. Land degradation remains one of the biggest environmental problems in Kyrgyzstan, therefore the program will continue to enhance communities and CSOs’ capacity to develop sustainable agriculture and marketing of organic products. The Issyk-Kul province of Kyrgyzstan will become a target area for these initiatives, which is in line with the Landscape Strategy for years 2014-2016 being implemented by SGP under the Government of Japan supported COMDEKS project. Knowledge management will be a critical component of SGP’s efforts and will become a significant part of the each project, in order to promote greater catalytic effects from the results of SGP projects. SGP Kyrgyzstan will also support establishment of demonstration zones and undertake exhibitions in each region of the country. |
| Maldives | To generate greater impacts beyond individual grants, SGP-Maldives will collect and consolidate positive results of projects in GEF 5 in order to support revival of sustainable traditional practices and promotion of energy efficient technologies. These would then be replicated and scaled up to achieve even bigger impacts through partnerships, networking and market instruments. In addition, lessons learnt will be shared extensively among grantees and to the wider public. More knowledge management and outreach activities will be carried to expand the pool of capable grantees and other partners. |
| Mongolia | To scale up the existing good practices and produce catalytic effects, SGP Mongolia will focus on organizational (or institutional) scaling up by expanding and strengthening its community development centers in the GEF SGP geographical focus area and by appointing regional coordinators. As of today, there are 4 community development centers established with assistance of SGP projects which are functioning with SGP guidance. SGP-Mongolia’s past experiences prove that communities themselves are the ones to promote, advertize and spread good practices and to ensure their adoption. SGP-Mongolia recognizes the importance of resource mobilization in creating greater results. Local loan funds have been created at the soum/village/county level, which are supported by the state budget. Information materials will be prepared purely for this purpose and a series of talks are planned with soum authorities to mobilize funds from local sources to use and transfer the SGP know-how and knowledge through local community exchanges in the countryside. Private sector will be targeted to participate in the series of talks and private sector cooperation will be sought for further scaling up. |
| Thailand | Well-planned small grant projects are not too technically and institutionally complicated to implement, compared with bigger projects. Results, successes or failures, can be easily monitored and documented for the purpose of learning and sharing among several other small grant project proponents and stakeholders. Through networking and clustering of several small grant projects wider impacts can be produced from their collective results- depending upon specific contexts. However, small grants projects cannot also be expected to produce “overnight changes” or be a “panacea” for environmental challenges. Rather the collective results and knowledge generated from small grant projects can help to lay the foundation for more systematic resource management and improved environmental governance at the local level. SGP-Thailand is a country-driven programme and relevant authorities are involved in its implementation. In addition to grants, several other activities are undertaken such as stakeholders workshops, mid-course evaluation workshop, and periodic communication practice among stakeholders. These efforts are supported and replicated by two departments of the concerned ministries: the Office of National Environmental Fund of the Ministry Of Natural Resources and the Environment, and the Department of Alternative Energy Development and Efficiency of the Ministry of Energy. Both departments have been working closely with SGP and grantee communities. While the former works to up-scale selected completed SGP projects under its grant scheme, the latter opted to choose SGP projects to replicate/up-scale/mainstream to contribute to its current Community Energy Master Plan. SGP-Thailand will increase its focus on landscape and seascape approaches, aiming to demonstrate aggregated impact across several small projects. Currently under dialogue with major stakeholders mentioned above, 10 out of 25 river basins of the country are potential targets. Realizing the nature of environment problems, the programme will continue to enhance communities and CSOs’ capacity to diagnose, understand and transform complex dynamic nature of global environmental problems and develop local solutions focusing on biodiversity, climate change and land degradation, while also covering international waters and chemicals. Knowledge management will be a key part of this strategy. |
| Ukraine | SGP-Ukraine will support scaling up of SGP results into GEF or other donors FSPs, as well as contributing its results to the work of involved Ministries and other stakeholders in line with the major strategic documents at the national level. The results of SGP projects will provide pilot testing that can contribute to better land management in Ukraine. SGP will use UNDP’s experience in Chernobyl in applying a holistic “area-based development” approach aimed at restoring a sense of community self-reliance by showing local people that they themselves hold the key to their lands recovery. These efforts will serve as a template for community-based efforts across the Zhytomyr region. Expanding upon the early results of UNDP, this effort will emphasize community empowerment, building a spirit of activism, and helping overcome “victims’ syndrome,” as residents re-build basic infrastructure and meet other urgent needs. Gender equality and women’s empowerment through proactive promotion of women-led projects, and the mainstreaming of gender in all relevant projects is of significant importance in SGP work. It forms solid background for further national and global networking of women grantee-leaders for knowledge-sharing and policy advocacy. SGP-Ukraine will also plan to continue its successful work with youth in achieving wider SGP and sustainable development objectives. Country driven approaches and linkages to the national development strategies remains a priority. Civil society in Ukraine is at the forefront of environmental protection and discussions on environmental and social issues. Awareness-raising and sensitization campaigns, well-targeted information programmes by CSOs will be supported and encouraged. SGP-Ukraine will work very closely with numerous civil society organizations to support their voice in bringing important issues to the table for discussion and further action. This can be achieved through implementing strategic projects, conducting stakeholder workshops and Knowledge Fairs. |
| Vietnam | SGP Viet Nam will promote national and local impact of SGP projects through: - Strategically focusing in certain focal areas and thematic issues in a geographic focus area - Testing innovative ideas and replicating/upscaling successful community strategies and approaches through policy influence and capacity development - Knowledge management (documentation and dissemination of lessons learnt) and policy advocacy at local and national levels - SGP projects must be community driven, and meet SGP criteria in terms of addressing BD, CC and LD issues in the context of CC through integrated management of natural resources. SGP projects will also support project sustainability by contributing to mainstreaming in strategies and action plans on sustainable development at the national and local levels (provincial/district) and by working in partnership with these programmes to support policy advocacy. - Capacity development for CSOs and its networks and communities to play a key role in the development process - Consultations with CSOs and communities - bringing the voice of concerns to the law/policy making. - Integration of results and experience into larger programmes and projects. |

Annex C:  status of implementation of project preparation activities and the use of funds

A.  provide detailed funding amount of the ppg activities financing status in the table below:

| PPG Grant Approved at PIF: |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF/LDCF/SCCF/NPIF Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent Todate | Amount Committed |
| Total | 0 | 0 | 0 |

annex D:  calendar  of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/NPIF  Trust Fund or to your Agency (and/or revolving fund that will be set up)

Project ID number will be assigned by GEFSEC.

Refer to the Focal Area Results Framework and LDCF/SCCF Framework when completing Table A.

PMC should be charged proportionately to focal areas based on focal area project grant amount in Table D below.

For questions A.1 –A.7 in Part II, if there are no changes since PIF and if not specifically requested in the review sheet at PIF  stage, then no need to respond, please enter “NA” after the respective question.

There has been no change since the PIF approval in the alignment of the project with national strategies and plans, however a more detailed description of how the SGP activities in each country will align with the national strategies and plans is provided in Table 1 above.

To ensure cost-effectiveness, project level monitoring and evaluation activities, including project site visits, are conducted on a discretionary basis, based on internally assessed criteria including (but not limited to) project size and complexity, potential and realized risks, and security parameters.

GEF SGP participating countries have been broadly classified according to the number of years they have participated in the program and the amount of cumulative resources disbursed through the program.  There is an expectation that SGP programs in those countries with the most SGP experience (Category II countries) should be able to deliver “higher level” results within each focal area.  Suggested higher level outcome add-ons are included in the results framework as the “Category II Step-up.”

“Avoided GHG emissions” is among the GEF-5 indicators for the climate change focal area, and is a relevant outcome for SGP.  The SGP approach, and level of available resources, inherently implies that SGP cannot, by itself, generate a transformative influence on the global climate problem directly through the amount of GHG emissions avoided.  At the same time, many, if not all, SGP climate change mitigation projects directly contribute to a reduction or avoidance of GHG emissions, and these positive results should be documented.  Recognizing that addressing global climate change will require action by the entire global community, SGP’s theory of intervention (in all focal areas) is heavily predicated on its catalytic effects, and thus the SGP results framework focuses on results of this nature.

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.