GEF-6 Project Identification Form (PIF)

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

PART I: Project Information

| Project Title: | GEF SGP Sixth Operational Phase- Strategic Implementation using STAR Resources Tranche 2 (Part IV) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country(ies): | 24 Countries (refer to annex 1 for the list of countries) | GEF Project ID: |  |  | 9857 |
| GEF Agency(ies): |  | GEF Agency Project ID: |  |  | 5475 |
| Other Executing Partner(s): | UNOPS | Submission Date: |  |  | 10/09/2017 |
| GEF Focal Area(s): | MFA | Project Duration(Months) |  |  | 48 months |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  |  | Corporate Program: SGP |  |
| Name of parent program: | N/A |  | Agency Fee ($) |  | 766,687 |

- indicative Focal Area  Strategy Framework and Other Program Strategies

| ### Objectives/Programs (Focal Areas, Integrated Approach Pilot, Corporate Programs) | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- |
|  |  | ### GEF Project Financing | ### Co-financing |
|  |  | 4,679,994 | 4,867,000 |
|  |  | 4,679,994 | 4,867,000 |
|  |  | 2,231,892 | 2,321,000 |
|  |  | 2,231,892 | 2,321,000 |
|  |  | 2,231,892 | 2,321,000 |
|  |  | 1,037,171 | 1,079,000 |
|  |  | 1,037,171 | 1,079,000 |
|  |  | 1,037,171 | 1,079,000 |
| Total Project Cost |  | 19,167,177 | 19,934,000 |

- indicative Project description summary

| ### Project Objective: To support the creation of global environmental benefits and the safeguarding of the global environment through community and local solutions that complement and add value to national and global level action |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Co-financing |
| 1.Community Landscape and Seascape Conservation |  | 1.1 SGP country programmes improve conservation and sustainable use, and management of important terrestrial and coastal/marine ecosystems through implementation of community based landscape/seascape approaches | 50 landscapes/seascapes in support of protected areas, ICCAs, and SAPs 5 million hectares of landscapes/seascapes with improved, community-oriented conservation and sustainable use practices |  | 8,509,080 | 8,886,000 |
| 2. Climate Smart Innovative Agro-ecology |  | 2.1 Agro-ecology practices incorporating measures to reduce CO2 emissions and enhancing resilience to climate change tried and tested in protected area buffer zones and forest corridors and disseminated widely | At least 2 farmer leaders develop their capacity to demonstrate selected typologies per landscape At least 1 farmer association/network functioning in each landscape |  | 2,828,649 | 2,950,000 |
| 3. Low Carbon Energy Access Co-benefits |  | 3.1 Low carbon community energy access solutions successfully deployed in alignment with larger frameworks such as SE4ALL in at least 12 countries | At least 10 typologies of innovative solutions dmonstrated and documentd At least 5000 households achieving energy access Co-benefits such as resilience. ecosystem management, income, health and others measured in 12 leading countries (Note: The above are total output targets for the GEF SGP OP6, including part 1, 2, and 3 finance. Part IV finance will intensify investment in the land/seascapes) |  | 6,086,977 | 6,356,000 |
| Subtotal |  |  |  |  | 17,424,706 | 18,192,000 |
| Project Management Cost (PMC) |  |  |  |  | 1,742,471 | 1,742,000 |
| Total Project Cost |  |  |  |  | 19,167,177 | 19,934,000 |

For multi-trust fund projects, provide the total amount of PMC in Table B, and indicate the split of PMC among the different trust funds here: (     )

- Indicative sources of  Co-financing for the project by name and by type, if available

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
|  | UNDP |  | 2,800,000 |
|  | TBD |  | 1,800,000 |
|  | TBD |  | 1,800,000 |
|  | TBD |  | 4,000,000 |
|  | TBD |  | 500,000 |
|  | TBD |  | 8,234,000 |
|  | TBD |  | 800,000 |
| Total Co-financing |  |  | 19,934,000 |

- Indicative Trust Fund  Resources Requested by Agency(ies),  Country(ies), Focal Area and the Programming of Funds a)

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b)b) | Total (c)=a+b |
|  |  | Please refer to Annex 1: list of 24 countries that have provided OFP Endorsement Letters, along with a FA breakdown | BD, LD, and CCM |  | 19,167,177 | 766,687 | 19,933,864 |
| Total GEF Resources |  |  |  |  | 19,167,177 | 766,687 | 19,933,864 |

- Refer to the Fee Policy for GEF Partner Agencies.

- Project preparation grant (ppg)

Is Project Preparation Grant requested? YesNo If no, skip item E.

PPG  Amount requested by agency(ies), Trust Fund,  country(ies) and the Programming  of funds

| Project Preparation Grant amount requested: $ PPG Agency Fee: |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GEF Agency | Trust Fund | Country/ Regional/Global | 1Focal Area | Programming of Funds | (in $) |  |  |
|  |  |  |  |  | PPG (a) | Agency Fee(b) | Total c = a + b |
|  |  |  |  |  |  |  | 0 |
|  |  |  |  |  |  |  | 0 |
|  |  |  |  |  |  |  | 0 |
| Total PPG Amount |  |  |  |  | 0 | 0 | 0 |

- Project’s Target Contributions to Global Environmental Benefits

Provide the expected project targets as appropriate.

Based on discussion with the GEFSEC at the start of the GEF SGP 6th Operational Phase in 2014, it was agreed that the SGP will report on the relevant Corporate Results Indicators during the Annual Monitoring and Evaluation Reports (i.e. AMR, MTE, and TEs),   Considering the nature of the program which provides small grants to local communities and civil society oraganizations, it was agreed that indicative targets would not be set at the PIF stage.

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| - Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | 5 million Hectares (total of OP6 SGP) |
| - Sustainable land management in production systems (agriculture, rangelands, and forest landscapes) | 120 million hectares under sustainable land management | Hectares |
| - Promotion of collective management of transboundary water systems and implementation of the full range of policy, legal, and institutional reforms and investments contributing to sustainable use and maintenance of ecosystem services | Water-food-ecosystems security and conjunctive management of surface and groundwater in at least 10 freshwater basins; | Number of freshwater basins |
|  | 20% of globally over-exploited fisheries (by volume) moved to more sustainable levels | Percent of fisheries, by volume |
| - 4. Support to transformational shifts towards a low-emission and resilient development path | 750 million tons of CO2e mitigated (include both direct and indirect) | metric tons |
| - Increase in phase-out, disposal and reduction of releases of POPs, ODS, mercury and other chemicals of global concern | Disposal of 80,000 tons of POPs (PCB, obsolete pesticides) | metric tons |
|  | Reduction of 1000 tons of Mercury | metric tons |
|  | Phase-out of 303.44 tons of ODP (HCFC) | ODP tons |
| - Enhance capacity of countries to implement MEAs (multilateral environmental agreements) and mainstream into national and sub-national policy, planning financial and legal frameworks | Development and sectoral planning frameworks integrate measurable targets drawn from the MEAs in at least 10 countries | Number of Countries: |
|  | Functional environmental information systems are established to support decision-making in at least 10 countries | Number of Countries: |

part ii:  project JustiFication

1. Project Description. Briefly describe: 1) the global environmental and/or adaptation problems, root causes and barriers that need to be addressed; 2) the baseline scenario or any associated baseline projects, 3) the proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project, 4) incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF, CBIT and co-financing; 5) global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF); and 6) innovation, sustainability and potential for scaling up.

- Global Environmental Problems, Root Causes and Barriers The GEF 2020 Strategy highlights global environmental problems and their continuing and critical nature: 60 percent degradation of ecosystem services; biodiversity decline by 30 percent (with 60 percent occurring in tropical regions) between 1970 and 2007; 30 percent forest loss and 20 percent forest degradation; 80 percent depletion or overexploitation of fish stocks; 24 percent of land area degraded; and climate change no longer a future threat but a reality. The GEF 2020 Strategy further identifies population growth as one of the major factors in the causal chain of environmental degradation particularly as a rising middle class population creates increased demands that put further pressure on already fragile ecosystems. The same could be said of the rising population of poor and vulnerable communities. Taking both poverty and social exclusion into consideration, some 2.8 billion people, spread across all developing regions are at risk of falling deeper into the vicious poverty-environmental degradation cycle. Of these, about 1.5 billion rely on small farms with 500 million practicing shifting cultivation. Of the 200 million people relying on fisheries, most depend on artisanal fisheries as the sole source of livelihood. Traditional biomass is still the source for household cooking of 40% of the world’s population resulting in further forest degradation, CO2 emission, as well as being one of the top three causes of mortality for women using wood for cooking. This linkage between poverty and the environment has created greater challenges to environmental protection and ultimately making it difficult to meet the goals of sustainable development. Many communities are in dire need to sustainably utilize their natural resources and ecosystems for livelihoods and development, yet are often located in the most degraded or sensitive areas of their countries’ forest, grassland, or dryland landscapes and coastal areas. The increasing population pressure and prevailing poverty force many communities to take environmentally destructive paths such as in the case of slash-and-burn farmers, dynamite or cyanide fishermen, and mercury-using small scale gold miners. In a vicious cycle of poverty leading to environmental degradation and then to more poverty, poor communities become the victims themselves. At the community level environmental and developmental issues are very closely inter-connected and intertwined. Loss of forests means not just the loss of biodiversity but also increased vulnerability to climate change resulting in combined negative impacts on agricultural productivity and livelihoods. Increased soil erosion eventually reaches waterbodies and destroys coral reef biodiversity, the resource which many artisanal fisherfolk are dependent on. Similarly with heavy chemicals use, toxic elements are absorbed by phytoplankton, ingested by zooplankton and fish thereby contaminating the food chain. It is at the community level, particularly in environmentally degraded and poverty-stricken areas, where the impacts of climate change will be felt first and foremost especially by poor and vulnerable sectors. Yet it is also at the community level where solutions and effective action can emerge. Communities have shown themselves to be effective stewards of their environmental resources when provided a strong stake and empowered to undertake their management, rehabilitation and protection. In certain countries, community managed conservancies roughly equal or even exceed government managed protected areas. At least 22% of developing country forests and over half of the world’s 102,000 protected areas are managed by communities. A recent CBD study reported that there may actually be more indigenous and community conserved areas, covering as much area if not more, than officially designated protected areas. Citizen advocacy groups have also been vital to create more stringent environmental policies and to strictly implement them. Consumer campaigns have traditionally been the source of pressure that shifts industry to move into more environmentally friendly practices and products. When the term “sustainable development” was first defined by the Brundtland Commission in preparation for the Rio Summit in 1992, it was recommended that: a larger portion of total development assistance should go to investments needed to enhance the environment and the productivity of the resource sectors, reforestation and fuelwood development, watershed protection, soil conservation, agroforestry, rehabilitation of irrigation projects, small scale agriculture, low cost sanitation measures, conversion of crops into fuel, and the most effective efforts of this type are achieved through small projects with maximum grassroots participation. Thus the global environmental conventions, for which the GEF serves as financial mechanism, all contain provisions and decisions regarding engagement with civil society as well as with indigenous peoples, farmers, fisherfolk, women, youth and NGO sectors. The CBD, for example, in its COP6 Decision (vi/10, 29, 30) has invited the GEF to provide special consideration in funding to projects that clearly contain elements of participation of indigenous and local communities. Further, under the COP10 and 12 Decisions, the CBD has requested GEF to continue expansion of the SGP in developing countries for this reason, particularly in LDCs and SIDS. Twenty years later in Rio+20, the list of major civil society groups was actually expanded with a strengthened call in its outcome document for the direct involvement, not just of governments, but of major stakeholder groups and civil society in its implementation. With new global initiatives such as REDD+, a growing body of evidence gathered by the World Resources Institute has linked community forest rights with healthier forests and lower CO2 emissions from deforestation and forest degradation. This further validates GEF’s own evaluation of the role of local benefits in global environmental programmes, a 2006 study that concluded that for many areas of GEF-supported activities, local and environmental benefits are interlinked. The transformation of these communities and their local CSO partners into capable actors for environmental protection rather than continuing to be part of the root problem is thus one of the most effective ways to generate global environmental benefits. However, several important barriers to direct and meaningful involvement of major grassroots stakeholders and civil society continue to exist and constrain environmental action at all levels. One is the organizational weakness of many communities and local CSOs that prevents them from implementing strategic and collective action for sustainable development and global environmental benefits. Communities and local CSOs need a facilitative funding mechanism that provides direct access and technical support for capacity development, community organization and networking, local enterprise development and innovation, and building resilience to socio-economic and ecological changes. Particularly affected are the communities and local civil society organizations which by the nature of their remote locations and prevailing poverty or social exclusion have not had the opportunity to interact with funders and implement projects. A second barrier is the lack of relevant approaches and technologies that can respond to the often unique and difficult challenges faced by poor and vulnerable communities. These stakeholders need concrete, on-the-ground efforts, that are able to explore what the GEF Vision 20/20 calls “new frontiers of global environmental action” that will provide innovative models for eventual mainstreaming, replication and scaling up. Lessons learned from these innovative efforts will also contribute towards improving policy and decision-making. A third barrier to grassroots action on the global environment is the lack of supportive and relevant policies. A proactive effort on this is important as OPS5 reported, despite the solid record and systematic inclusion of CSOs in GEF affairs, civil society engagement needs further support due to numerous dynamics including relationships between CSOs and governments and the interpretation as well as documentation of meaningful and relevant engagement. Given this, the GEF itself has recently strengthened its policies supporting indigenous peoples as well as on women’s empowerment. Yet in many countries there is still need to facilitate positive working relationships between government and local CSOs, as well as to support grassroots networking, so that can multi-stakeholder alliancescan be developed and lead the way towards transforming policy and regulatory environments as called for in the GEF 20/20 Strategy, to create global environmental benefits at scale. Communities and civil society, if they are to contribute effectively to achievement of global environmental objectives, must be supported to develop greater technical and organizational capacities, tested through the actual implementation of increasingly more complex on-the-ground environmental and sustainable development solutions. The enabling environment needs to be created to expand community-based action at scale through positive national policy dialogue and development planning that brings in the experience and knowledge of capable and empowered community and CSO stakeholders. - Baseline Scenario Since the Rio Summit (1992), countries have implemented projects and programs in line with their commitments to various environmental conventions to which the GEF is a financing mechanism. This has been in the form of government as well as CSO implemented or executed projects and programs, with government implementation and execution forming the bulk. While many governments have started to place funding resources in the hands of CSOs, particularly donor governments with international NGOs, there are still major barriers in the case of local NGOs, and much more so CBOs (Community-based Organizations). This is reflected in the way GEF funds have been utilized for CSOs. The OPS5 report noted that despite the solid record of the GEF in civil society engagement, such engagement very often stops short of being meaningful, one reason being the relationship between CSOs and governments and interpretation of meaningful engagement.Relationship between government and CSOs can be determined by lack of confidence in the capacity of CSOs, particularly of local NGOs and CBOs, difference in development philosophy, policy and approaches, and lack of capacity of both parties to work with each other. An assessment by SGP National Coordinators of funding sources that can be used by CSOs other than SGP showed that: - Majority of the participating countries in the programme have some form of government funding mechanism to support CSO action. However, such mechanisms depend on availability of funds from donors, tend to be ad-hoc and non-predictable, government-led and with political agenda oftentimes coming up as an issue. Furthermore, the focus is more on socio-economic concerns at the local level, rather than addressing global environmental concerns, including education, nutrition, local development, media and communications, water supply and sanitation, women & youth empowerment, sexual & reproductive health, HIV/AIDS, agribusiness, rural infrastructure, and the like. - Aside from the GEF, there are other donors such as bilateral agencies, international development agencies, regional banks, embassies, International NGOs, philanthropic foundations, as well as some CSR-related resources from the private sector that can provide funds for CSO action. Most are also more focused on socio-economic concerns although some INGOs such as WWF, CI, and IUCN continue to be in the environment field while others such as OxFam, CARE, and Red Cross are increasingly getting into the climate adaptation work. The World Bank’s CIF especially its Dedicated Grants Mechanism for Indigenous Peoples which supports REDD plus projects is a new major source of funding for CBOs. There are also countries that have set up Environmental Funds, including endowment and sinking funds. However, when the criteria of direct access to grants by communities and local CSOs for integrated global environmental issues, particularly representing poor and vulnerable sectors in more remote areas and with limited capacity, track record or registration, and governance by a multisectoral national steering committee of both government and non-government members with the non-government in majority are factored in, then there are almost no other grantmaking mechanism of this type other than GEF SGP in these countries. The closest in approach are the Global Greengrants with a much lower grant levels (at $1,000 - $3,500), the Small Scale Initiative Programme (SSIP) of Le Fonde Francais Pour L’Environnment Mondial (FFEM) focused on biodiversity conservation in West and Central Africa and Madagascar (at 50,000 Euro maximum) and the Critical Ecosystems Partnership Fund (CEPF) focusing on biodiversity hotspots. With the presence of other interested donors, the SGP has increasingly served as a platform and delivery mechanism for partnership and co-financing of small grants. In many cases, these other funds are combined with SGP’s in a joint, parallel or sequential co-financing approaches, providing additional resources or to cover needed aspects that cannot be funded with GEF funds. CSO involvement in environment and sustainable development action will continue without GEF SGP. But there would be more limited contributions from CSOs particularly by poor and vulnerable communities and local CSOs on global environmental issues. Furthermore, while there have now been more than 20,750 community and CSO projects supported in 25 years of SGP operation, a critical mass still has to be reached in many countries particularly those that started up later. There is also need to consolidate assets of completed projects for scaling up, mainstreaming and replication. The many community-based and CSO-led projects that SGP has supported, as well as its development as a funding modality highly regarded by both CSOs and government in participating countries, can be considered as built-up assets that can serve as foundations for expanded work in GEF-6. Completed projects of SGP, particularly with the strong ownership and sustained support of involved communities and CSOs will proceed with minimal or little support from GEF and thus also forms a “baseline”. In the biodiversity focal area, there are presently more than 8,500 community-based projects with grantees and other related stakeholders connected together. For example, in regard to the GEF’s efforts to promote protected areas co-management between government and indigenous and local communities, there is now a global coalition of civil society actors in support of Indigenous and Community Conserved Areas and Territories (ICCAs) across all regions. Resulting in part from SGP’s advocacy for ICCAs, the GEF has formally adopted ICCAs as part of its strategy and funding priorities for the GEF-5 cycle, and Aichi Target 11 now includes a reference to other “effective area-based forms of conservation”, including ICCAs and private protected areas, as necessary for expanding the global coverage of protected areas (PAs) from 12% to 17%. This work together with the more focused SGP landscape approach projects (e.g. Community Management of Protected Areas Conservation – COMPACT, and Community Development and Knowledge Management in the Satoyama Initiative - COMDEKS) forms a strong foundation for landscape conservation initiative of SGP OP6 and its aim to generate increased global environmental benefits. In the international waters focal area, more than 760 projects provide working examples of community action aligned with the priorities identified in regional frameworks, particularly GEF full-sized projects’ regional Strategic Action Programmes (SAPs). Collaboration with the GEF FSPs in the Nile River, Niger River, the South China Sea/East Asia Seas and other waterbodies resulted in SAP implementation at the community level and community experiences and knowledge incorporated into regional management processes of transboundary waterbodies. With SGP’s work in the climate change focal area, more than 3,000 projects (33% on renewable energy and 27% on energy efficiency) are available to show innovative community low-carbon technologies that are adapted to local conditions and significantly contributing to provision of sustainable energy services and reduction of harmful GHG emissions while generating other co-benefits such as improved resilience and livelihoods. While small in scale, these successful pilot initiatives can be integrated and scaled up within larger national and international frameworks such as NAMAs (Nationally Appropriate Mitigation Actions), LEDS (Low Emission Development Strategies), Sustainable Energy for All (SE4ALL), as well as in the new initiatives taking shape with potential support from the Green Climate Fund and other funders. In the land degradation focal area there are more than 2,000 agricultural, pastoral and forest communities with improved agricultural management and implementing integrated approaches that bring in food security and poverty reduction considerations together. There are Community-Based Adaptation (CBA) pilot communities representing a variety of ecosystems in 9 countries that was supported by the GEF Special Priority for Adaptation (SPA) funds as well as in all thirty (37) SIDS with AusAID co-financing. There are 370 projects developed through SGP POPs and chemicals portfolio providing successful examples of community-based pesticide management in agriculture, promotion of organic farming as an alternative, reduction of chemicals usage and contamination, avoidance of open burning of solid waste and capacity development, awareness raising and knowledge sharing. A POPs Training Module is presently widely used by NGO and community leaders, with about 1,000 online users and more than 10,000 offline users. Partnerships and networking with CSOs dedicated to the chemicals focal area, such as with the International Pesticide Elimination Network (IPEN), have been established with plans for expanded efforts in project implementation as well as formation of coalitions for policy advocacy. Existing investments and assets have also resulted from SGP’s work with GEF Full-Sized Projects (FSPs), in synergy as well as in a supportive role, in implementing community components of these projects. Globally, several UNDP and donor co-financed programmes have also been implemented by SGP, such as: the Community-Based Adaptation programme funded by AusAid, the Community-Based REDD+ programme in partnership with UNREDD and with financing from Norway, the Community Development and Knowledge Management in the Satoyama Initiative (COMDEKS) funded by the Japan Biodiversity Fund and in collaboration with UNEP and UNU, the EU funded Environmental Governance and NGO Strengthening project, among others. All these built up assets and existing investments from government, bilaterals, donor agencies and international NGOs will be treated as “baseline” from which SGP Country Programme Strategies will develop its priorities and approaches which then feed into supporting the development (i.e. partnership and co-financing components) and selection of individual small grants projects to ensure the strategic and catalytic nature of SGP OP6 grantmaking. - Alternative Scenario and Expected Outcomes As a GEF corporate programme, SGP has always aligned its operational phase strategies to that of the GEF with the expectation that its role is to translate such strategies to community and local CSO action. SGP contributes to achieving GEF’s strategy outcomes by supporting innovative initiatives by these important stakeholders and building on the baseline assets so far achieved. Action at the local level by civil society, indigenous peoples and local communities is deemed vital also by the GEF 2020 Strategy (i.e. convening multi-stakeholder alliances as well as for broader participation in strengthening capacity and decision-making processes). The individual SGP project will be small but their aggregated impacts over time in more than a hundred countries, particularly as SGP moves into more programmatic grantmaking modalities such as the landscape/seascape management approach in GEF-6, will contribute significantly to global environmental benefits. This approach has been integral part of the GEF-6 Replenishment Programming and Policy Directions. The presentation of this present proposal covers the strategy for the entire GEF-6 implementation of the SGP, in line with the “GEF Small Grants Programme: Implementation Arrangements for GEF-6” (GEF/C.46/13), which was reviewed and approved at the GEF Council in its May 2014 meeting. This project follows the submission of the GEF SGP 6th Operational Phase –Part I, II, and III projects (total of GEF core set-aside funding of $140 million and STAR of $18 million in GEF-6). This Part IV project aims to provide supplementary STAR funding resources to countries aiming to sustain and increase involvement of local communities and civil society in advancing the impact of the SGP and ensuring efforts to safeguard the global environment from the bottom up. In total 48 countries have provided commitment to allocate GEF-6 STAR resources to the SGP. Based on discussion with the GEF Secretariat, it was agreed that a tranched approach (2-3 PIFs) will be taken to access STAR resources for all these countries, rather than all at once. Each tranche will consider several factors including: the balance of LDC/SIDS countries; regional balance, level of commitment/delivery of GEF-6 SGP core funding; and amount/percentage of STAR allocation to SGP. Further, based on feedback from the GEF Secretariat, some countries were not included in this global PIF, including due to GEF-6 STAR utilization. This PIF draws upon STAR resources endorsed by 24 SGP participating countries to enhance and increase impact of their SGP programmes. Among them, majority of 16 countries are Small Island Developing States (SIDS) and Least Developing Countries (LDCs) where SGP plays an important role in building necessary capacity for conserving the global environment. This project will be implemented in full alignment with the SGP OP6 Part I, II, and III projects, which support 110 countries in total. Many countries included in this PIF have allocated funding from two or more focal areas in order to enhance integrated SGP programming in their countries. Some countries have allocated resources in specific focal areas. For example, Jordan and Papua New Guinea have allocated funding primarily from the Biodiversity focal area to enable SGP to extend and enhance its Community Landscape and Seascape Conservation focus. Countries such as Marshall Island and Niger have allocated resources mainly from the Climate Change focal area to further support activities of CSOs and communities in sustainable energy access and climate change mitigation. Land degradation focal area STAR finances have been allocated in particular by Tanzania and Uganda, among others to further enhance SGP's strategic focus on sustainable agro-ecology and cover multiple focal areas. The grantmaking at the country level will be implemented based on the SGP Country Programme Strategies (CPS) for GEF-6 that have been prepared by each country to enable more strategic and integrated investments at the country and landscape/seascape levels. In all countries, CPS development process has been undertaken in a consultative manner to identify SGP's value added within the priority global environmental issues in line with the concerned Multilateral Environmental Agreements/Conventions and national policies and plans to guide SGP grantmaking and ensure its complementarity with other donor and country supported initiatives. The STAR funds through this PIF will be programmed in line with the CPS with close involvement of SGP's multistakeholder National Steering Committees in each country. In addition, this Multi-focal area project is consistent with the results framework and strategic objectives of the GEF's Biodiversity, Climate Change and Land Degradation. For Biodiversity, the project will support the CBD's Aichi targets, in particular those related to protected areas (11), ecosystem services (14) and traditional knowledge, innovations and practices (18). Key SMART indicator that the SGP will be using to measure contribution towards the Aichi Target would include be the coverage of both terrestrial and marine protected areas. This will include increased management effectiveness of both new and existing protected areas, including the Indigenous and Community Conserved Areas and Territories (ICCAs). Another SMART indicator would be the coverage of areas that promote sustainable use and mainstreaming of biodiversity in the production land/seascapes with sound policies and practices. The SGP will also track and report on number of threatened species that the project contributed for conservation. The programme goal of SGP for GEF-6 is to “effectively support the creation of global environmental benefits and the safeguarding of the global environment through community and local solutions that complement and add value to national and global level action.” To reach this goal SGP will use a three-pronged approach: (a) focusing its work on globally recognized critical ecosystems; (b) setting-up innovative institutional and financial support mechanisms to expand the value and impact of projects nationally and globally and; (c) systematically developing the capacity of local and national civil society stakeholders, including their ability to manage larger projects and more complex national challenges, as a key factor for environmental sustainability. SGP proposes to focus grant making around clear components that are based on country and global priorities and where strategic impact can be achieved. The grant making will be focused on priority themes that are multi-focal in character and leverage SGP’s ability to foster synergies among focal areas. Initial consultations with SGP country programmes have informed the development of this PIF, particularly where certain strategic components and outcomes will be prioritized. However, it is expected that the SGP country programme teams, in consultation with National Steering Committees and a broad base of country level stakeholders will be involved in consultations to elaborate and further prioritize the components and outcomes which are the most relevant to implement in their countries. These consultations will be reflected in the development of SGP OP6 Country Programme Strategies in each SGP county programme which will guide the implementation of grant making in each country. In order to effectively implement OP6, SGP will also serve as a “Grantmaker+” providing additional services and added value. The programme will set-up support mechanisms based on SGP experience and assets built up over the years, which allow SGP to build value beyond grant-making. These support mechanisms are based on the understanding that individual projects are not just ends in themselves but also the means to achieving more sustainable impact when greater cumulative and synergistic effects can be leveraged through the non-grant services provided by SGP such as institution building, knowledge networking, and policy advocacy. These efforts will also sustain the efficiency of SGP despite lower grant funds while at the same time facilitating scaling up, mainstreaming and replication. In OP6 SGP will contribute to the achievement of the following 7 Components. However, as Part IV financing of the GEF SGP 6th Operational Phase that is specifically financed by participating countries’ Focal Area STAR allocations of Biodiversity, Climate Change, and Land Degradation, this PIF will focus only on the first 3 components that are specifically linked to relevant thematic grantmaking at the country level. The SGP Part I and II finances supported by Core, which have been approved earlier by the GEF Council, will cover components 4 to 7. - Community Landscape and Seascape Conservation During OP6, SGP will identify important ecosystems and use a community-based landscape and seascape conservation (CLSC) approach for their protection and sustainable use. Under this component, SGP will implement a truly multi-focal approach involving communities in buffer zones and corridors thus providing connectivity for complex landscape mosaics. In the landscape approach, aside from continuing to provide direct access to GEF grants for small producer organizations, indigenous peoples’ networks, peasant associations, and farmers’ collectives worldwide SGP will help federate their efforts as part of the rapidly expanding global movement in support of the conservation of agro-biodiversity, food sovereignty, and in situ plant and animal genetic resources. Priority landscapes and seascapes for the CLSC will include sites inscribed on international conventions (i.e. World Heritage, Biosphere Reserves and Ramsar sites), as well as to the increasing diversity and quality in the governance arrangements of PAs contributing to the achievement of the CBD Aichi 2020 targets (such as ICCAs and private PAs). SGP will complement existing and planned GEF investments, particularly in support of transboundary conservation efforts in the international waters focal area, in partnership with other programmes such as the Critical Ecosystem Partnership Fund (CEPF), French GEF (FFEM), as well as grass-roots networks including the expanding global network of Locally Managed Marine Areas (LMMAs). As such, the identification process will make use of the “GEF criteria for Defining Globally Significant Sites for Biodiversity Conservation” in Annex 3 of the GEF-6 Programming Directions. In addition, SGP will reinforce and strengthen GEF support towards the planned 10-year work programme for protected areas to be established at the next World Parks Congress in November 2014 (‘The Promise of Sydney’). During OP6, with additional funding from the German Ministry of the Environment (BMUB), SGP will deepen and extend a global south-south coalition of CSOs in support for the achievement of ICCAs in relation to Aichi targets 11 (protected areas), 14 (ecosystem services) and 18 (traditional knowledge, innovations and practices). SGP has previously helped shape global policy for the implementation of the CBD Programme of Work on Protected Areas (PoWPA) through the development of a global registry for ICCAs ). During OP6, SGP will continue to work with the GEF, bilateral donors, UNEP WCMC, IUCN and other partners to quantify and track the global results of sustained support to ICCAs across all world regions. Building on the experience of COMPACT, the Satoyama COMDEKS Initiative, and the Global ICCA Support Initiative (ICCA GSI), SGP will build up its capacity to develop multi-focal area integrated landscape/seascape strategies and conceptual models. Seascape approaches will involve the identification and prioritization of waterbodies for intervention, coordination among key stakeholders in the identification of the root causes of environmental degradation, and the development and implementation of inter-linked activities to systematically address waterbody environmental degradation. SGP will promote a polycentric governance approach in international waters management based on the innovative model piloted in South China Sea, which involves coordinated actions and interventions from different actors, including the government, the communities, and the private sectors. The role of SGP is to join the coordinated efforts, and support community-based actions towards a shared goal as jointly identified by key stakeholders, in the area of coastal habitat management (such as mangroves, coral reefs, seagrass and other types of wetlands), fisheries management and land-based pollution, river and lake basin management, as well as integrated water resource management. The aim is for community demonstrations of integrated coastal and water resources management in select seascapes will be supported in at least 20 countries. The identification of priority seascape areas will thus strongly consider partnerships with GEF FSPs, in the Caribbean, the South China Sea/East Asian Seas, the Pacific as well as others in consultation with existing FSP interventions. In this, SGP will work with relevant GEF FSPs to enhance local capacity, link up with key stakeholders and form regional networks of communities to deepen cooperation among stakeholders of shared waterbodies. Such approaches will address a major community barrier in international waters management, i.e. the lack of a regional coordination mechanism to ensure linkages and coherence of highly local community projects to meet regional objectives in holistic transboundary watershed management. With the landscape and seascape conservation approach the potential for SGP to increase cross-country learning between projects is tremendous, reflecting a modest additional cost to upscale and build upon the foundations of “tried-and-tested” national delivery mechanisms established during previous SGP operational phases. There are at least 45 SGP country programmes that stand ready and are targeted to implement a landscape/seascape approach with the aim to improve the conservation and sustainable use management of important terrestrial and coastal/marine ecosystems. - Climate Smart Innovative Agro-ecology SGP’s niche under this component will focus on the production buffer zones of identified critical ecosystems, also in forest corridors in danger of fragmentation due to population pressure, often remote and unaddressed by other traditional donors. Small grants in this initiative will be applied in synergy with the GEF6 Sustainable Land Management (SLM) for Climate-Smart Agriculture programme to target geographical areas that show declining productivity as a result of human induced land degrading practices and the impact of climate change. In OP6, newer innovative and pragmatic approaches will be accommodated building on both current agriculture science as well as the knowledge base of communities. The use of the term “agro-ecology” is to highlight the strong added element of ecological considerations to the usual short-term production oriented agriculture. This is necessitated not only by the need to rehabilitate degraded land but also to adapt to the changing climate which requires strong consideration for sustaining ecosystem services within and adjacent to farms, the growing concerns for more healthy food systems, and thus a holistic approach for sustainable farming with multiple benefits from climate resilience to farm productivity. An example of this will be the promotion of the development and uses of organic materials from natural mineralization processes, increased use of scalable good land management systems and working with communities to test and implement good land management policies. SGP will apply principles of climate-smart agriculture and a landscape approach promoting use of organic based fertilizers for improving soil productivity, increasing food security and reducing emissions from land degradation. This will require close collaboration with public and private sector to help poor farmers access environmentally friendly fertilizers and to improve food security and to rehabilitate soils. SGP will focus on building the capacities of smallholder organizations and identifying specific problems and proposed solutions by these community level organizations so that their objectives can be further refined in dialogues with the NSCs for the grants and with government, the private sector and other development agencies for possible scaling up, mainstreaming, and replication. SGP will also promote time tested and proven land management systems such as agro-forestry while also focusing on building the capacities of smallholder organizations to innovate with new and more appropriate practices and systems that adaptively utilize traditional knowledge and modern technologies. SGP’s efforts in OP6 will further focus on increase of ecological connectivity, reducing forest fragmentation and improving forest biodiversity values at landscape levels; promoting good management practices in community and smallholder forestry and farmlands, and a local level land management policy required to protect and enhance genetic pools in the wild that could form a repository of germplasm for domestication and re-introduction into degraded landscapes – all with increasing resilience to climate change in mind. In addition, as seeds are a primary resource for farmers and represent their best weapon in dealing with climate change impacts, smallholder farmers will be supported to improve food security using a conservation approach to plant and genetic resources for food and agriculture that includes improving seed quality and adopting more resilient strains in various types of landscapes. At the end of SGP OP6, agro-ecology practices which enhances not only yields from agricultural farms but also other social, economic and environmental benefits that incorporate measures to reduce CO2 emissions and enhance resilience to climate change would have been tried out along the protected area buffer zones and forest corridors and disseminated widely in at least 30 priority countries. - Low-Carbon Energy Access Co-benefits SGP will contribute to satisfying global demand for energy services for people without access to electricity and those that still rely on traditional biomass for cooking. SGP will focus on providing bottom-up energy solutions that are low-cost and provide high potential for carbon emissions reductions. Such efforts will contribute to GEF climate change objectives, which include “support for energy access initiatives at the local level, including demonstrations and piloting of renewable options”. SGP will align its efforts with the larger framework of Sustainable Energy for All (SE4ALL) to facilitate mainstreaming and scaling up. SGP is well positioned to meet the goals of “Sustainable Energy for All” to facilitate national and global replication as SGP’s work with CSOs is consistent with SE4ALL’s strategy emphasizing the ability of CSOs to directly assist the poor. SGP will focus on providing bottom-up energy solutions that are low-cost and provide high potential for carbon emissions reductions including small hydro, bioenergy systems from waste and efficient stoves. Such solutions aligned with national country strategies (e.g., NAMAs, LEDS, energy access policies etc.) are a crucial part of the “decarbonization”, addressing energy service needs of rural, urban and remote communities and entrepreneurs, who cannot be served by the central grid in case of electricity or centralized distribution systems in case of cooking and heating fuels. Such bottom-up energy solutions will also use integrated approach going beyond energy sector aiming at increasing climate resilience, reducing poverty, enhancing gender equality and achieving the sustainable development goals. SGP is multifocal in nature and is uniquely positioned to promote synergy across the various GEF focal areas and corresponding conventions, according to GEF-6 programming directions, which emphasize that “coordination of clean energy policies with relevant policies in other areas, such as agriculture, rural development, health, poverty eradication, gender equality and women’s empowerment, and energy security, have the potential to generate synergistic co-benefits at the local, national, and global levels.” These solutions would be easily replicable in similar countries and SGP will facilitate knowledge exchanges between communities potentially including programmatic regional initiatives to achieve greater impact. Activities will include 1) capacity building efforts enabling the community to develop and use innovative technologies; and 2) working with SE4All inspired project preparation facilities, promoting new business models, and providing catalytic financing through grants directly to CSOs and communities. This approach will address a major barrier to investments and financing for energy access over and above a lack of available capital or high initial purchase costs - an absence of adequate information sharing and understanding among energy sector players at various levels regarding the alternative and sustainable opportunity solutions available to them to invest in bottom-up energy enterprises. In addition to capacity building and catalytic financing, SGP will make an emphasis on knowledge management and systematization. Based on the work accomplished in the past operational phases, several countries are already well positioned to take a lead in this initiative. It is expected that low carbon community energy access solutions will be successfully deployed in 50 countries with alignment and integration of these approaches within larger frameworks such as SE4ALL initiated in at least 12 countries, as well as in relevant initiatives of the Green Climate Fund and other funds. - Local to Global Chemicals Management Coalitions SGP will focus its support in this component towards communities at the forefront of chemical threats either as users or consumers. Activities will include support for innovative, affordable and practical solutions to chemicals management in joint efforts with SGP’s established partners such as the International POPs Elimination Network (IPEN), as well as new partnerships including with government agencies, research institutions, the private sector, and international agencies such as UNIDO and WHO. Efforts would include women and indigenous peoples who still do not participate in all aspects of decision-making related to the sound management of chemicals. Artisanal gold miners, responsible for 30% of global mercury emissions of 1,000 tons per year will also be a priority sector for SGP. Similarly efforts focusing on e-waste recycling would necessitate SGP expanding its work to cover urban areas to reach the informal sector involved in such recycling. Another priority area is to raise awareness on the health and environmental impact of open burning practices of some waste streams (e.g. acid lead batteries, copper) for recycling purposes. In overall chemicals management, building on the successes in some SGP country programs in establishing the certification system of organic biodiversity products (such as the organic honey-producing business certification supported by SGP Mexico), a priority area would be to establish systems of local certification of producers and/or their products through promotion of organic production processes, the development and implementation local certification manual/guidelines, networking of producers, as well as strategic linkages and agreements between producers and consumers. s. Work will also involve advocacy for national government policies that will influence markets including chemicals import and export. In mercury management, at least one artisanal gold-mining community in each of the hotspot countries will shift their practice to the use of alternative gold mining techniques and serve as good practice example for similar communities as well as for policy advocacy in these countries. Another important partner for SGP in OP6 will be the private business sector, which would be most likely to have strong influence on the control of mercury in artisanal gold mining and on e-waste management. Within SGP OP6, innovative community-based tools and approaches will demonstrated, deployed and transferred, with support from newly organized or existing coalitions in at least 20 countries for managing harmful chemicals and waste in a sound manner. - CSO-Government Policy and Planning Dialogue Platforms In order to effectively implement SGP objectives in OP6, support mechanisms will be set-up based on SGP experience and assets built up over the years. Many SGP country programmes have reported on past contributions and efforts to influence national local and national policy formulation. Building on the experience of trust and constructive working relationship of its multi-sectoral National Steering Committees, SGP will support the establishment of “CSO-Government Policy and Planning Dialogue Platforms” (potentially in partnership with the GEF CSO Network) in at least 50 countries. These platforms will serve to build trust and foster joint working relationships between civil society and government on key areas for environment and sustainable development policies. More specifically, they will assist governments in establishing and institutionalizing the link of SGP communities to development plans and policy reforms that may affect them. Dialogue can allow CSOs to highlight important and relevant issues, offer information to supplement official government data, and provide fresh insights. A broader understanding of what CSOs may reveal provides valuable entry points for government support and engagement in FSPs, MSPs and also leverage additional financial resources for CSO/SGP activities. In the national context positive dialogue strengthens the country ownership of present and future policies. Potential participants of such dialogues will include GEF Operational Focal Points and Convention Focal Points, national policy makers and technical specialists, FSPs, MSP partners, potential donors, lead CSO partners. Global grantee community will be tapped for knowledge and lessons learned. The platforms will also relay on existing mechanisms of CSO involvement in the countries as well as GEF and SGP activities such as national portfolio formulation exercises and knowledge fairs. At the country level SGP has already started supporting the establishment of CSO-Government policy dialogues facilitating participation of grantee partners in government advisory bodies, connecting policy makers with the grassroots level sustainable development issues. Different types of CSO-led policy dialogue platform initiatives will be supported by SGP with the aim to influence central, regional and local government policy-making processes. - Promoting social inclusion In OP6 SGP will undertake targeted efforts to support greater social inclusion of vulnerable and affected groups, including women, indigenous peoples, youth and the disabled who have a stake in and an important role to play in global environmental management and sustainable development. In OP5 SGP efforts towards gender mainstreaming included adding gender relevant sections in all programme documents and templates. On SGP National Steering Committees were required to designate a member as a gender focal point and as a youth focal point. Relevant countries where indigenous people form a significant segment of the population were also required to ensure the representation on the NSC of an indigenous peoples focal point. In OP6 SGP in line with the GEF Gender Mainstreaming Policy and Gender Action Plan will direct further support towards mainstreaming gender in all relevant projects, as well as through promotion of women-led projects. Opportunities for national and global networking of women grantee-leaders for knowledge-sharing and policy advocacy will be explored where relevant. SGP will review and update the gender mainstreaming requirements in its templates and strategies and ensure gender is considered as a core element of the planning and implementation tools of SGP at all levels. SGP will further promote the use of gender-sensitive indicators and collect gender-disaggregated data. Additionally, SGP will provide training tools and activities for its country programme staff, NSC members, grantees and partners that can ensure the application of gender mainstreaming considerations in all SGP country programmes. SGP will aim for an increase in the number of women led projects and projects with gender components in OP6 over the levels achieved in OP5. SGP recognizes that numerous challenges continue to be faced by indigenous peoples who manage natural resources in ICCAs, territories, PA buffer zones, and production landscapes to ensure that their occupation of landscapes and seascapes, as well as their governance of natural resources, are appropriately recognized by local and national authorities. During OP6, SGP will work to enhance assistance to indigenous peoples to participate more fully in the relevant national, regional and international policy-making processes, such as the creation of national ICCA networks, participating in the CBD Programme of Work on Protected Areas (PoWPA), implementation of National Biodiversity Strategies and Action Plans (NBSAPs), exploring new livelihood strategies for indigenous peoples and local communities created by the Nagoya Protocol on Access and Benefit Sharing (ABS). SGP will develop and pilot an Indigenous fellowship to promote proactive mentoring and capacity-building of indigenous peoples at national, regional and global levels. At least 12 IP fellowships are envisioned, some designed to strengthen the capacity for leadership on global environment and sustainable development issues while some fellows will work alongside SGP national coordinators to expand and improve SGP’s support for indigenous peoples. Indigenous peoples have submitted to the GEF and the UN system regular inputs and recommendations with regards to options for enhanced programming. In response to their calls to expand and improve this support, SGP will support the use of its regular and strategic projects for addressing priority areas for action. Efforts will be made to mobilize additional resources to initiate a dedicated grant-making window to support indigenous peoples on priority themes. SGP will also aim to enhance engagement of youth and disabled. On youth engagement SGP has identified many best practices in the climate change area in particular where youth organizations have been instrumental in raising awareness and promoting advocacy, while the involvement of the disabled has been given specific attention in the AusAid/DFAT co-financed SIDS Community Based Adaptation (CBA) programme in the context of building adaptive capacity and communities’ resilience to effects of climate change. In OP6 SGP will take stock of existing experiences and efforts and work to further enhance its support to youth and persons with disabilities to further engage these socially important and often vulnerable groups. - Global Reach for Citizen Practice-Based Knowledge In line with its mandate to support community action to address global environmental issues, SGP will support enhanced knowledge exchange at the global level through a Global Reach for Citizen Practice-Based Knowledge programme. Specifically this will be comprised of the following two knowledge platforms. A “Digital library of Community Innovations for the Global Environment” will feature tested methods and technologies, many of them original innovations, developed by SGP and other partners and CSOs. The platform will prioritize the documentation and dissemination of practices that have the potential for replication in other countries of the south and that will also facilitate technology uptake and help transfer technical expertise from a community in one country to other communities, CSOs, policymakers and development practitioners. For this purpose, the National coordinators is each country will select 1-2 tested innovative technologies or practices that have significant potential for replicating and up–scaling to document and develop how-to toolkits. The technical step by step how-to toolkits will be developed in a way to facilitate easy replication and will then be grouped by common technical areas in SGP (e.g. cook stoves, biogas digester, etc) in an online platform. For further dissemination, SGP will aim to partner with other organizations that also promote, fund and produce knowledge on innovative community practices. An active digital library of community-based innovations for use by the larger public should be operational in at least 50 countries by end of SGP OP6. A “South-South Community Innovation Exchange Platform” will aim to promote knowledge exchange between SGP countries to encourage cross country/region replication of good practices. The rationale for this is to be able to produce high impact and scaling up of the innovations and practices developed by SGP grantees, as well as other CSOs at the regional level, as currently all grantmaking and associated knowledge exchange happens at the national level. As such, this platform will link mentors to emerging practitioners and set aside some funds to select a few strategic projects that can have high potential impact to facilitate knowledge exchanges in specific technologies, regions and landscapes. Currently, the existing South-South exchange platforms in UNDP, World Bank and other organizations do not target CSOs or communities. SGP will aim to partner with and complement other South–South initiatives wherever possible. By end of SGP OP6, there will be at least 20 SGP participating countries where active South-South community innovation exchange platforms exist. - Incremental Cost Reasoning The SGP provides support to communities and CSOs in their work to contribute to both global and local environmental benefits. As discussed in the baseline section above, without GEF support through SGP grantmaking, environmental protection, rehabilitation, and overall sustainable development will be much harder to achieve. The current baseline scenario shows that much more have to be done as increasing populations of poor and vulnerable communities try to increase their agricultural productivity, access energy, and use fisheries, oftentimes through unsustainable means, further jeopardizing their livelihoods and the ecosystems these depend on. Short-term decision-making is often unavoidable when people are on a day-to-day survival basis. Additional and substantial resources, both cash and non-cash, are needed to shift them to the long-term and holistic thinking required for environmental action. Yet, community stakeholders in remote frontline areas where critical environmental action is needed are unfortunately the ones with the least access to technical and financial resources to address even the local concerns that ultimately link to and impact on global environmental issues. While many developing country governments have started to put more resources to local development and to CSOs as partners, the demand for socio-economic development coupled with the lack of awareness as well as mechanisms to integrate this demand to similarly compelling environmental concerns, have led to an imbalance in the allocation that is inimical to environmental needs. Sustained GEF support to SGP has led to the development of a funding modality that could help fill the gap and is appropriately designed to be the critical partner of poor and vulnerable frontline communities and related local CSOs to build awareness of the local-global links of environment and sustainable development issues, develop capacity for meaningful engagement, show effective and innovative approaches, and strengthen local and civil society institutions that can add to national, and eventually, global action. Over time, portfolio of community-based projects, strategically linked, create a critical mass for transformational shifts through increased area coverage, national to global sharing of lessons learned, and the broad networking of capable and committed local stakeholders for effective advocacy and holding all to commitments made in global environmental agreements. Independent evaluations of the SGP have also shown that the programme can add value to larger projects of the GEF and other donors either through complementation of projects and activities or helping them more effectively reach communities and CSOs for access to available resources. - Global Environmental Benefits The GEF SGP provides support to achieve global environmental benefits at the community level. The SGP strengthens the capacity of communities and civil society organizations, increases their knowledge and awareness about environmental threats, and provides them financial support to overcome short-term decision-making that negatively affects environmental resources. Many SGP projects have direct links to achievement of global environmental benefits thematically when these projects focus on globally important and critical endangered species and geographically when these projects are located in critically important landscapes and seascapes. Successful innovative projects of high relevance to oftentimes neglected sectors such as indigenous peoples, women, youth and children, and the disabled provide models or examples for designing larger national efforts as well as filling in important national policy gaps. Within the GEF, UNDP, and other agencies, tested SGP approaches, lessons learned, country staff, and stakeholder networks have become resources in the design and/or implementation of larger projects. The 2015 Joint Evaluation of the SGP conducted by the Independent Evaluation Offices of the GEF and of UNDP states as Conclusion 1 of the evaluation:“SGP continues to support communities with projects that are effective, efficient and relevant in achieving global environmental benefits while addressing livelihoods and poverty, as well as promoting gender equality and empowering women. Replication, scaling up and mainstreaming are happening.” The discussion above of SGP priority projects and activities for GEF-6 shows a much more enhanced set of strategies to endure that SGP contributes to global environmental benefits. Firstly is the full alignment of SGP priorities to that of the GEF-6 Programming Directions and of its outcomes to meeting the GEF-6 replenishment targets. Secondly, is the greater attention to creating synergy among individual projects through the use of landscape or seascape approaches as well as taking all opportunities for complementation with larger projects of the GEF and other donor agencies. Thirdly, is the linking of SGP local initiatives to global initiatives such as SE4ALL as well as fostering joint efforts with global networks such as the GEF NGO Network and IPEN. Finally, there will be the formalization and more organized implementation of previously more ad-hoc support activities into a “Grantmaker+” set of roles designed to support scaling up, mainstreaming and replication that will provide higher level capacity development (i.e. IP Fellowships), networking and institutional support, knowledge sharing (i.e. South-South Technology Exchange Platform), and advocacy mechanisms at national levels (i.e. CSO-Government Dialogue Platforms), and where relevant, all these to extend to regional and global levels. - Innovativeness, Sustainability and Scaling up Potential Following the principle of “local action, global impact” and a demand-driven and “venture capital” approach to grantmaking, SGP has supported communities in developing innovations that customize local solutions to global environmental challenges. The SGP approach encourages local innovation and creativity through its bottom-up and participatory practice in the design of projects, in the recognition of the relevance and value of local or traditional knowledge, and in allowing greater flexibility and adaptive management of projects. The wide diversity of countries, local situations, and stakeholders the SGP works with creates in itself a situation requiring an openness to many new ideas and their testing. Community innovations in SGP are manifested in the testing and ground-truthing of low-cost technologies and sustainable production methods, in new methodologies for the involvement of stakeholders, and in integrating traditional decision-making processes within the wider frameworks and action relevant meeting country commitments to international environmental agreements. Because SGP funding is modest and its interventions designed to be initially small scale, the program can readily support community-based experimentation. Once a novel idea has been tested on the ground and proven to be effective in meeting community needs, it can often take off more widely through grantee networks as well as networking with other CSOs, further resulting in more innovations and eventually attracting additional donor and or government support for wider application. In GEF-6, the innovation process will be further supported through the establishment of a digital library of community innovations, building on the tens of thousands of SGP-supported projects, as well as a South-South Community Innovation Exchange Platform to share these innovations across countries. Achieving sustainability of project outcomes is central to SGP. According to its 4th Independent Evaluation (GEF Evaluation Office 2007), and the 5th Independent Evaluation in 2015, the SGP has secured a high success rate in sustaining project results. Project proponents are required to build measures into their project design that increase the likelihood of outcome sustainability. The screening of project proposals by the National Steering Committee includes a systematic assessment of whether such measures are sound and based on realistic assumptions. Project logical frameworks include outcome indicators that are monitored periodically. Project monitoring activities are designed to verify that initial assumptions hold, and that the required elements for outcome sustainability are in place. Most grants include a capacity development component and a sustainable livelihoods component to ensure that achievements will be sustained at the smallholder and resource-user level. Proactive adaptive management is applied throughout the life of the projects by the National Coordinator who works with SGP grantees to take corrective action whenever there are indications that project outcomes may be compromised or may not be sustained after the project ends. SGP does not generally support the creation of new organizations but rather strengthens existing CBOs and NGOs. Although most communities continue applying acquired skills in their day-to-day work SGP ensures retention of new skills through various means: inviting leaders or members of former grantee organizations to new training; using former SGP grantees as trainers for other communities and projects; continuing as much as possible monitoring former grantees and trouble-shooting when required; and establishing mentoring and peer-to-peer support among communities. Ultimately, the sustainability of SGP projects results from the strong ownership of the community or CSO grantee-partners to the actions taken and resulting outcomes, the empowerment built in the process of implementation, and the fact that these projects are meeting their most important needs particularly for sustainable livelihoods. In GEF-6, the sustainability of SGP projects will be further enhanced as these projects gain more support from each other in the synergy created in landscape/seascape approaches, in the complementation with larger projects of the GEF, other agencies and government, and in the further support that will be derived from “Grantmaker+” activities (e.g. capacity, development, networking, knowledge sharing, policy advocacy, resource mobilization) for scaling up, mainstreaming and replication. Most SGP innovations, if not all, have scaling up potential. For one, successful SGP projects are solutions that are relevant to a thousand-fold more communities under similar situations within its country of implementation and also across other countries. In a lot of cases, community-based approaches are able to find ways of more cost-effective utilization of existing resources or utilization of hitherto untapped resources thereby providing a good model for larger projects concerned with efficiency and sustainability. Many large national projects that use top-to-bottom approaches also now finding increasing resistance from grassroots stakeholders (i.e. from indigenous peoples that demand prior-informed consent and their own control of projects). The highly consultative and participatory processes, including the direct access to funds, practiced in SGP projects can provide valuable lessons for larger government and donor programs. Notable too is the global reach of SGP – 128 participating countries – that with good sharing systems can scale up, mainstream, and replicate successful community projects. Scaling up, as well as mainstreaming and replication, however, are processes that require a proactive approach and additional resources especially for communities and CSOs that had just completed their first projects. Research and experience of major private and non-profit funders also show that the upscaling process takes time and involves various stages that require enabling environment from the government, availability of donors and addressing funding gaps. SGP’s main role in the scaling up process is to demonstrate or showcase the successful innovation to a wider set of stakeholders as well as to establish networks/linkages for pooling of effort and resources by various actors needed for scaling up. At the portfolio level, SGP has utilized its National Steering Committees, grantee-partner networks and allied CSO networks to have community innovations and successes recognized and adopted at the national level by policy-makers. The 2008 Independent Evaluation of the GEF SGP found that SGP’s greatest contributions to achieving and sustaining global environmental benefits are in the realm of contributing to country change and reform through the development of local policy instruments, contribution to national policy formulation, and the facilitation of access to broader markets catalyzed by country-specific SGP initiatives. During OP6, SGP will enhance the potential for scaling up through strengthened partnerships at national and global levels. For example, building on progress established during GEF-5, the SGP has an excellent foundation of collaboration with a number of international partners including the International Partnership for the Satoyama Initiative (IPSI), the ICCA Consortium, IUCN Global Programme on Protected Areas (GPAP), the UNESCO World Heritage Centre, UNEP WCMC, CBD Sec LifeWeb, and other relevant networks at the national and regional levels (i.e. International Indigenous Forum on Biodiversity). To facilitate upscaling in GEF-6 SGP will also partner with national and global initiatives currently taking shape such as those of the Green Climate Fund and “Sustainable Energy for All”. These larger initiatives will provide a platform for scaling up SGP work as well as possible co-financing and joint efforts in national and global planning and policy advocacy. SGP will also encourage strong partnerships with the private sector to commercialize successful projects with the aim to shift renewable energy projects from pilot innovations to the mainstream.

2. Stakeholders. Will project design include the participation of relevant stakeholders from civil society organizations (yes  /no) and indigenous peoples (yes /no)? If yes, identify key stakeholders and briefly describe how they will be engaged in project preparation.

# SGP operates through a multi-stakeholder approach engaging a range of stakeholders including NGOs, CBOs, indigenous people, the private sector, government, academia, and donor partners.  During GEF-6, civil society organizations (CSOs) will be both beneficiaries and direct participants in GEF SGP through their inclusion in National Steering Committees (NSCs), where non-governmental members must be in the majority, as well as by taking on the role as National Host Institutions and other key roles related to knowledge sharing and policy advocacy.  Although grants are targeted towards CSOs particularly community-based and non-governmental organizations, a broad range of stakeholders are engaged as active partners in program management and during grant implementation, including inter alia research institutes, local and municipal governments, international NGOs, as well as national and international volunteers.

# With regard to indigenous peoples and marginalized populations, GEF SGP follows a set of principles that advocate for a flexible, time sensitive, and simple project cycle in order to allow these groups to access GEF SGP support. The programme has pioneered numerous user-friendly modalities to work with poor and marginalized groups including alternative proposal formats such as participatory video, Almanario, photo stories, and community theatre, and allowances are made for concept and project submission in local and vernacular languages so long as these concepts and proposals adhere to the basic project elements. GEF SGP also allows for flexible disbursement terms to cope with indigenous peoples’ culture, customs and seasonal movements. SGP makes extra efforts to reach out people and groups that are often marginalized or disadvantaged.  Empowering women and engaging youth have been two important initiatives of SGP.  SGP NSC at the country program level has designated a focal point for gender and youth, respectively to ensure their voices are heard.  Additionally, Through stakeholder workshops, CSOs are able to learn of GEF SGP projects and activities and provide inputs on how to improve on them.

3. Gender Equality and Women’s Empowerment. Are issues on gender equality and women’s empowerment taken into account? (yes  /no).  If yes, briefly describe how it will be mainstreamed into project preparation (e.g. gender analysis), taking into account the differences, needs, roles and priorities of women and men.

As noted in detail under the SGP’s approach towards promoting social inclusion as part of the project framework (page 17), SGP has been pioneering and highly recognized in mainstreaming gender equality and women’s empowerment in every step of the program operation: starting from the development of the country programme strategy to project proposal templates for small grants.  A gender focal point is designated within each SGP National Steering Committee to ensure review of gender considerations in project selection.  Within OP6 a specific component dedicated to promoting social inclusivity will provide direct support for enhancing knowledge, networking and exchange related to promotion of gender mainstreaming and women’s empowerment. SGP is engaging closely with GEF Secretariat, UNDP and a range of GEF Agencies and Convention Secretariats to develop a training platform for increased understanding of gender roles and considerations in environmental management and sustainable development.

# 4. Risks. Indicate risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (table format acceptable).

# There are few new risks that may come into the play as SGP moves into newer disciplines. The possibility of new insurmountable risks is minimal given that the programme has been operating for 25 years and has been constantly learning and adapting during this time.  Potential risks are known, and through the past experience of the GEF SGP, risk mitigation measures are in place for those that have been identified before.  There still is the challenge of working directly with community-based and non-governmental organizations that have a low level of technical and management capacity.  Past performance of the SGP portfolio has shown that 90% of SGP grants achieve outcomes in the satisfactory range. To mitigate risks, especially in the small underperforming portion of the portfolio, the SGP works with all grantees to help develop capacity by identifying appropriate rates of disbursement, linking grantee partners to learn from each other, and working in a flexible manner that responds to the strengths and comparable advantages of grantees. Risks of underperformance due to capacity limitations will also be mitigated by consistent and comprehensive oversight and monitoring of the SGP portfolio in each country by CPMT and the UNDP Coutry Offices.

# The SGP also reduces risk by supporting replication and re-validation of good practices that have proven to deliver on GEF strategic priorities at the community level.  In each country, the National Steering Committee, with representation from civil society leaders, government institutions, and donors provides further support for effective design and implementation of SGP projects.  Additional risks may be anticipated from the gradually changing geographic presence of SGP, where in each operational phase the most mature countries meeting the criteria for upgrading are being upgraded, while in the past two operational phases a significant number of LDCs and SIDs, as well as countries in post conflict situations, have been added.  The potential risks of working in newer countries, countries with post conflict situations, capacity challenges, etc. will be mitigated in OP6 through the greater flexibility in SGP playing grantmaker+ roles to complement and ensure the success of grant projects. By actively promoting CSO-government dialogue platforms, providing dedicated support to gender mainstreaming and indigenous peoples engagement, as well as by developing and utilizing effective global knowledge exchange platforms, SGP will be better able to build the capacity of CSOs and promote community action in many of the newer countries that have joined SGP in OP4 and OP5.

# 5. Coordination. Outline the coordination with other relevant GEF-financed and other initiatives:

# SGP has formed mutually beneficial long-standing relationships with international, national and community-level initiatives and partners, and will continue to seek synergies in the coming operational phase. The program works with relevant stakeholders in its geographic and thematic areas to ensure coordination of donor funding on relevant initiatives.  There are also numerous national and local level initiatives that GEF SGP is in partnership with.  Globally, SGP has partnered and cofinanced together with the Global ICCA Support Initiative, the community-based REDD+ program, the Community Development and Knowledge Management in the Satoyama Initiative (COMDEKS), the EU funded Environmental Governance and NGO Strengthening project, among others.  SGP will also seek linkages with other relevant GEF MSPs and FSPs whenever synergies can be found.  SGP continues to identify opportunities to share successful methodologies and approaches with other GEF FSPs, and will serve as a delivery mechanism for the community components of these MSPs and FSPs.  Although it is not possible to list all existing and potential partnerships in this document, enhancing linkages and cooperation with GEF medium-sized and full-sized projects and other donor partners will continue to be a priority for GEF SGP in the 6th Operational Phase.

6. Consistency with National Priorities:  Is the project consistent with the National strategies and plans or reports and assessements under relevant conventions? (yes  /no ).  If yes, which ones and how:  NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, etc.:

Most national policies and strategies such as NBSAPs, NAPs, NIPs, NAMAs, LEDS and others emphasize the importance of engaging the widest possible circle of stakeholders (including CSOs) in order to achieve their environmental protection objectives. UNDP has a strong record of supporting developing countries in the elaboration of national strategies and plans. As the GEF Agency implementing the SGP as well as having supported many GEF Enabling Activities, UNDP is well placed to ensure greater synergy in the implementation of the SGP in alignment with National strategies and planning frameworks, as well as to effectively leverage the potential of the SGP to contribute community perspectives and CSO engagement.  In each of these national planning frameworks, SGP’s community-based approach targets a critical constituency of small-scale localised actions which represent a critical contribution to the implementation and achievement of these national policies and strategies.

The GEF SGP country programme strategies (CPS) are the over-arching documents guiding the SGP strategic directions, programming and operations. The development and updating of the strategies are based on national policies and action plans, such as NBSAPs, NAPs, NIPs etc. and other national key documents, which are directly linked to GEF multi-focal area strategies and priorities.

SGP operates in countries where specific requests to initiate the programme have been received from the appropriate national authorities, represented by the GEF Operational Focal Point.  By first requesting and subsequently supporting implementation of the SGP, a country demonstrates that the SGP will be a country-driven and owned initiative supporting community-level and civil society environmental projects. SGP has operated in 128 countries in the past immediate phase, reflecting each of these countries’ priorities for community-driven approaches to addressing global environmental issues.

National priorities are reflected through the constitution of the SGP National Steering Committee (or National Focal Group for sub-regional programmes), which guides implementation of the SGP in each respective country.  National Steering Committtee members are leading national government and civil society representatives in the environmental field, who provide strategic guidance and oversight for the programme, and ensure its focus on and coherence with national priorities as they apply to and are relevant for community-level needs and priorities.  For all these countries, start-up missions supported the organization of the new country programmes to develop strategies reflecting national priorities focused on community-level actions, and created the necessary institutional structures.  SGP priorities at the national level are codified in detail in the SGP Country Programme Strategy, which is linked to the country’s GEF resources allocation strategy, which in turn reflects GEF policies and strategic priorities for GEF-6.  Each of these strategies draws on national priorities and strategies, in particular those that focus on civil society and community-based actions.

7.Knowledge Management. Outline the knowledge management approach for the project, including, if any, plans for the project to learn from other relevant projects and initiatives, to assess and document in a user-friendly form, and share these experiences and expertise with relevant stakeholders.

One of the most important results from the innovative community solutions supported by SGP is the wealth of knowledge it has produced over the years at the project, national and global level. To make this knowledge accessible and useful, SGP has developed a Knowledge Management Strategy that presents the tools that the programme use for knowledge exchange at each of these levels with the ultimate aim to inform and influence policy, replicate and upscale good practices, promote a culture of learning and innovation.

At the global level, SGP provides guidance on how to capture and disseminate knowledge and conduct knowledge exchange at the local level so that it can be aggregated at the global level; shares technical publication and provides guidance of each focal and cross cutting areas of work; organizes regional workshops to exchange knowledge and provide training to its staff; and shares good practices emerging from the portfolio at global conferences and events. SGP also establishes partnerships with a variety of partners to upscale best practices in environmental conservation and and works to capture and disseminate the lessons learned and best practices of its massive portfolio in case studies, fact sheets, publications, and new media.  Knowledge platforms including the SGP website and Communities Connect (a platform to share knowledge from civil society organizations around the world that promotes solutions created by communities and civil society organization to sustainable development issues) have been created and will be updated.

At the national level, each country will work directly with the communities in (i) capturing their lessons; (ii) conducting knowledge exchanges; (iii) organizing training workshops; (iv) establishing and nurturing networks of NGO’s and CBO’s; (v) working with the government in achieving national environmental priorities; (vi) and helping to scale up and replicate best practices and lessons learned. Each country programme outlines a knowledge management plan as part of their Country Programme Strategy. Based on these experiences, country programmes will routinely produce knowledge materials in local languages, including project fact sheets, informational brochures and case studies, to disseminate at key national events and conferences.  For example, Knowledge Fairs will be organized to feature the most innovative practices supported by the programme and allow communities to present those and connect with key stakeholders like the academia, other NGOS, the government and other development practitioners for replication, upscaling, and policy influence, as well as technical support and knowledge transfer. These Knowledge Fairs also allow communities to learn from one another and to foster networks of civil society innovators for sustainable development.

At the project level, each project needs to include a knowledge management plan with a corresponding budget that allows the programme to capture their experience as well as to access the training needed to carry out the projects. SGP will be facilitating peer-to-peer learning between local communities and SGP graGEFntees as an effective method to share knowledge, help communities learn from each other and as a tool for replication and up scaling of best practices.

SGP will further enhance access to and opportunities for knowledge exchange at the global level through a Global Reach for Citizen Practice-Based Knowledge programme. Specifically this will be comprised of the following two knowledge platforms as desicribed in the previous sections: (1) the “Digital library of Community Innovations for the Global Environment” will feature tested methods and technologies, many of them original innovations, developed by SGP and other partners and CSOs. The platform will prioritize the documentation and dissemination of practices that have the potential for replication in other countries of the south and that will also facilitate technology uptake and help transfer technical expertise from a community in one country to other communities, CSOs, policymakers and development practitioners; (2) the “South-South Community Innovation Exchange Platform” will aim to promote knowledge exchange between SGP countries to encourage cross country/region wide replication of good practices. This platform will link mentors to emerging practitioners and set aside some funds to select a few strategic projects that can have high potential impact to facilitate knowledge exchanges in specific technologies, regions and landscapes. Currently, the existing South-South exchange platforms in UNDP, World Bank and other organizations do not target CSOs or communities. SGP has started discussions to partner with and complement other South–South initiatives wherever possible.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A. Record of Endorsement of GEF Operational Focal Point (s) on Behalf of the Government(s):  
(Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this SGP OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| H.E Mr. Mostapha Zaher | Director-General a.i | National Environmental Protection Agency, Afghanitstan | 7/31/2017 |
| Mr. Pellumb Abeshi | General Director | Environment, Albania | 12/11/2014 |
| Mr. Artsvik Minasyan | Minister | Nature Protection, Armenia | 10/06/2017 |
| Mr. Philip Weech | Director | Environment and Housing, Bahamas | 10/28/2016 |
| Mr. Guo Wensong | Director | Finance, China | 8/3/2016 |
| Mr. Enrique Moret Hernandez | Director | Science Technology and Environment , Cuba | 2/3/2016 |
| Ms. Ghrmawit Haile Gebrehiwot | Director, Strategic Planning and Resource Mobilization Directorate | Environment and Forest, Ethiopia | 4/14/2015 |
| Ms. Nino Tkhilava | Head of Environmental Policy and International Relations Department | Environmental Protection and Natural Resources, Georgia | 9/22/2017 |
| Dr. Saleh Al-Kharabsheh | Secretary General | Planning and International Cooperation, Jordan | 06/16/2015 |
| Mr. Lonkham Atsanavong | Director General | Department of Environment Quality Promotion, Lao PDR | 8/17/2017 |
| Mr. Issa Fahiri Kone | Specialiste en Foresterie Rurale | Ministère de l'Environnement, d’Assainissement et du Developpement Durable, Mali | 7/25/2017 |
| Mr. Clarence Samuel | Director | Office of the Environmental Planning and Policy Coordination, Marshall Islands | 2/28/2017 |
| Mr. Yaye Seydou | General Director of Planning | Planning, Territorial Management and Community Development, Niger | 3/31/2015 |
| Mr. Amos Ibrahim Tanko | Director | Environment, Nigeria | 08/03/2017 |
| Mr. King Sam | Protected Area Network | Natural Resources, Environment and Tourism, Palau | 6/30/2016 |
| Mr. Gunther Joku | Acting Director | Department of Environment and Conservation, Papua New Guinea | 9/22/2014 |
| Mr. Abdul Bakarr Salim | Assistant Deputy Director | Environment Protection Agency, Sierra Leone | 08/31/2017 |
| Ms. Lavern Queeley | Director | Sustainable Development, St. Kitts and Nevis | 2/10/2017 |
| Ms. Caroline Eugene | Chief Technical Officer | Sustainable Development, Energy, Science and Technology, St. Lucia | 1/29/2016 |
| Dr. Julius Ningu | Director of Environment | Vice President's Office, Tanzania | 4/16/2015 |
| Mr. Akif Ozkaldi | Undersecretary | Forestry and Water Affairs, Turkey | 4/25/2016 |
| Ms. Soseala Saosaoa Tinliau | Director of Environment | Ministry of foreign affairs, trade, tourism, environment and labour, Tuvalu | 08/29/2017 |
| Mr. Patrick Ocailap | Deputy Secretary to the Treasury | Finance, Planning and Economic Development, Uganda | 08/09/2017 |
| Mr. Vladyslav Marushevskyi | Head of International Coordination Division | Ecology and Natural Resources of Ukraine | 09/27/2017 |

B. GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation under GEF-6.

| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu, Executive Coordinator, UNDP-GEF |  | 10/09/2017 | Yoko Watanabe, Global Manager, GEF SGP | (646) 781 4383 | yoko.watanabe@undp.org |

C. Additional GEF Project Agency Certification (Applicable Only to newly accredited GEF Project Agencies)

For newly accredited GEF Project Agencies, please download and fill up the required GEF Project Agency Certification of Ceiling Information Template to be attached as an annex to the PIF.

When completing Table A, refer to the excerpts onGEF 6 Results Frameworks for GETF, LDCF and SCCF and CBIT guidelines.

Financing type can be either investment or technical assistance.

For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal;  above $2 million, PMC could be up to 5% of the subtotal. PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.

PPG requested amount is determined by the size of the GEF Project Financing (PF) as follows: Up to $50k for PF up to$2m (for MSP); up to $100k for PF up to $3m; $150k for PF up to $6m; $200k for PF up to $10m; and $300k for PF above $10m. On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

PPG fee percentage follows the percentage of the Agency fee over the GEF Project Financing amount requested.

Provide those indicator values in this table to the extent applicable to your proposed project.  Progress in programming against these targets for the projects per the Corporate Results Framework in the GEF-6 Programming Directions, will be aggregated and reported during mid-term and at the conclusion of the replenishment period. There is no need to complete this table for climate adaptation projects financed solely through LDCF, SCCF or CBIT.

For biodiversity projects, in addition to explaining the project’s consistency with the biodiversity focal area strategy, objectives and programs, please also describe which Aichi Target(s) the project will directly contribute to achieving.

GEF IEO. OPS5 Final Report: At the Crossroads for Higher Impact (Section 7.5 Engagement of Civil Society Organizations, p. 57). 2014

Survey made in the period August 2014 in preparation for SGP OP6 PIF development

OPS5 technical study (document no. 14) survey on GEF CSO engagement showed that out of the six mechanisms GEF has used to engage CSOs, the SGP was rated the most effective (2.18 out of maximum 3); rankings were given 2.83 by the GEF Secretariat respondents as compared to 2.06 for the CSOs (their highest ranking) with informants referring to the SGP as “important”, "the main door for CSOs” and “the most relevant GEF mechanism”.

The GEF’s Overall Programme Study of GEF 4 (OPS4, 2010) observes that “The GEF provides funding through four basic modalities: full-size projects, medium-size projects, enabling activities, and small grants (through the SGP)” (p.8).  It goes on to recommend, as Recommendation 8 of the study, that: “The SGP should be recognized as a GEF modality that should be available to all recipient countries.” (p. 18)

GEF-5 Focal Area Strategies ‘Objective One: Improve Sustainability of Protected Area Systems’ p.3:http://www.thegef.org/gef/sites/thegef.org/files/documents/document/GEF-5_FOCAL_AREA_STRATEGIES.pdf

For example, in its 12 years of work, COMPACT directly supported over 430 projects (and, through partnerships, indirectly supported other initiatives) at eight World Heritage Sites and/or other globally significant protected areas covering a total area of some 788,000 hectares, providing over US$10-million in small grants, and leveraging a further US$5.5-million in co-financing (cash and in-kind support). In addition, the work contributed significantly to Target 11 of the Aichi framework on shared governance of protected areas.

For example, in China, SGP has supported five projects on international waters by reducing land-based pollution and restoring and protecting coastal habitats. These five projects have involved 19,770 local people and benefited 4,345 people directly.  An example of the work supported by SGP is a project on investigation and control of land-based pollution in the coastal area of Dalian that ended in January 2011. The project engaged over 8,000 volunteers who contributed 22,630 hours and cleaned up 11,590kg waste along the Dalian coast. As a result, 1,906 kilometers of the Dalian coastline are now under regular monitoring and protection by the community and the achievements of this project have been acknowledged by the local government by providing US$50,000 to continue the work started by SGP.

For example, in Dominican Republic, whereelectricity supply is a significant problem, sixteen off-grid community-managed micro hydro systems were established with SGP support. Significant environmental impacts were achieved at country level: more than 24,000 tons of CO2 emissions per year were avoided, more than 10,000 ha of forests important for biodiversity conservation preserved and restored. From the economic perspective, these initiatives saved the import of more than 15,700 barrels of oil equivalent per year, saving 1.6 million USD per year for country’s economy. Additionally, more than 1000 families, schools, microenterprises, rural health, communication and community centers have energy access. Before, each family had to spend 12-30 USD per month to buy kerosene gas, candles and batteries. Now each family pays 3-6 USD per month and has access to 4-9 times more electricity, which represents savings between 100 and 300 USD/year per family. On a policy level, GEF SGP successful experiences in rural electrification informed the process of drafting and approval of law fostering renewable energy leading to inclusion of community projects in the text.

For example, in Nepal, with the support of SGP and other co-sponsors, the Center for Public Health and Environmental Development (CEPHED) launched a campaign to raise public awareness about POPs and establish models to reduce POPs usage and unintentional production.  Approximately 2,000 liters of PCBs contaminated transformer oil has been avoided by replacing the wet welding machines with PCBs free dry welding machines. The project successfully reduced the release of PCDD/Fs from non-burning medical waste treatment in the Kanti children hospital by 1.19 g TEQ /year. This project won the Stockholm PEN Award in April 2011.

These partnerships have been mutually reinforcing. GEF full-sized projects, with their larger funding and direct links to government implementation, have access to greater resources, networks and policy influence than SGP.  On the other hand, SGP’s knowledge and experience working with communities and CSOs at the local level help FSPs work better with these stakeholders. For example, SGP and the UNEP/GEF South China Sea project worked together to ensure the delivery of $1 million in grants (half from SGP and half from the South China Sea project) to communities via 31 projects in support of the implementation of the South China Sea SAP. The FSP provided technical and training support as well as government networking for communities and CSOs while SGP provided its grantmaking mechanism to ensure fast and efficient funds flow to communities as well as oversee the implementation of these community-based projects. As a result 2,079 hectares of seagrass, 2,388 hectares of coral reef and 12,618 hectares of mangrove were put under sustainable management which represents 8%, 4.5% and 0.7% of the SAP targets of the FSP was met.

For example, in its 12 years of work, COMPACT directly supported over 430 projects (and, through partnerships, indirectly supported other initiatives) at eight World Heritage Sites and/or other globally significant protected areas covering a total area of some 788,000 hectares, providing over US$10-million in small grants, and leveraging a further US$5.5-million in co-financing (cash and in-kind support). In addition, the work contributed significantly to Target 11 of the Aichi framework on shared governance of protected areas.

CBD COP11 in Hyderabad, October 2012, reconfirmed the critical role of the ICCA Global Registry in monitoring the contributions of voluntarily conserved areas under decision XI/24 on protected areas of UNEP/CBD/COP/11/35 to: “Strengthen recognition of and support for community-based approaches to conservation and sustainable use of biodiversity in situ, including indigenous and local community conserved areas, other areas within IUCN governance types and initiatives led by indigenous and local communities that fulfill the objectives of Aichi Biodiversity Target 11 and support the voluntary use of the Indigenous and Community Conserved Areas Registry managed by the United Nations Environment Programme World Conservation Monitoring Centre.”

GEF Assembly Document GEF/A.5/07/Rev.01, May 22, 2014

Sustainable Energy for All: Technical Report of Task Force 1, April 2012

GEF Assembley Document GEF/A.5/07/Rev.01, May 22, 2014

Strategic Approach to International Chemicals Management (SAICM) states in paragraph 9.a.

The important role of local impact to progress towards larger system impact is highlighted in the OPS5 Report (see Figure 7.2).

Joint GEF/UNDP Independent Evaluation of SGP, Final Report, 2015, pp. 55.

Harvey Koh, Ashish Karamchandani and Robert Katz. From Blueprint to Scale: The Case for Philanthropy in Impact Investing, April 2012

For regional and/or global projects in which participating countries are identified, OFP endorsement letters from these countries are required even though there may not be a STAR allocation associated with the project.

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, SCCF and CBIT