request for

Project Type:

Type of Trust Fund:

part i: project information

| Project Title: SUSTAINABLE AGRICULTURE AND CLIMATE CHANGE MITIGATION PROJECT |  |  |  |
| --- | --- | --- | --- |
| Country(ies): | Uzbekistan | GEF Project ID: | 4642 |
| GEF Agency(ies): |  | GEF Agency Project ID: | P127486 |
| Other Executing Partner(s): |  | Submission Date: | 2012-12-21 |
| GEF Focal Area (s): |  | Project Duration(Months) | 48 |
| Name of Parent Program (if applicable): - For SFM/REDD+ |  | Agency Fee ($): | 1,269,900 |

- Focal Area Strategy framework

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | Trust Fund | Grant Amount ($) | ### Cofinancing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | Outcome 1.1 - Technologies successfully demonstrated, deployed, and transferred | Output 1.1 - Innovative low-carbon technologies demonstrated and deployed on the ground |  | 1,000,000 | 1,000,000 |
|  | Outcome 2.2: Sustainable financing and delivery mechanisms established and operational | Output 2.3: Energy savings achieved |  | 2,900,000 | 16,500,000 |
|  | Outcome 3.2 - Investment in renewable energy | Output 3.2 - Renewable energy capacity installed |  | 3,558,780 | 30,080,000 |
|  |  | Output 3.3 - Electricity and heat produced from renewable source |  | 3,557,782 | 30,080,000 |
|  | Outcome 1.2 - Improved agricultural management . | Output 1.2 - Types of Innovative SL/WM practices introduced at field level Output 1.5 - Information on SLM technologies and good practice guidelines disseminated |  | 1,090,000 | 27,800,000 |
|  | Others |  |  |  |  |
| Subtotal |  |  |  | 12,106,562 | 105,460,000 |
| Project management cost |  |  |  | 592,438 | 2500000 |
| Total project costs |  |  |  | 12,699,000 | 107,960,000 |

- Project Framework

| ### Project Objective: (i) promote the introduction of renewable energy and energy efficiency technologies of relevance to agri-businesses and farms; and (ii) strengthen capacity for improving degraded irrigated land and water conservation. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Grant Amount ($) | ### Confirmed Cofinancing ### ($) |
| 1. Investments for sustainable technologies |  | Low-carbon technologies successfully demonstrated and transferred and GHG emissions avoided in rural areas Renewable energy technologies begin to be adopted in rural areas throughout the country | a) Demonstrations of off-grid renewable energy technologies in rural areas, including bio-gas digestors, small solar and biomass, and energy efficient irrigation pumps supported through workshops under Comp 3 below) ($1M) b) Matching grants to implement renewable energy and energy efficiency technologies in agribusinesses and on farms ($8M) |  | 9,000,000 | 76,660,000 |
| 2. Irrigated land degradation mitigation/. |  | Improved management of agricultural systems and water resources is achieved through the adoption of technologies and good practices for irrigated land Degraded irrigated lands in the baseline project raions are improved; more efficient water use practices adopted; agricultural productivity increased | a) Technologies and management approaches for controlling and reversing irrigated land degradation introduced in 7 raions; number of hectares improved ($1M) b) Farmer Field School approach delivers knowledge and skills to farmers and local communities to promote sustainable land management practices ($0.09M) |  | 1,090,000 | 26,610,000 |
| 3. Project technical support and advisory services. |  | Renewable energy, energy efficiency and land degradation mitigation technologies and practices adopted; legal framework enables introduction of renewal energy technologies; renewable energy technology and sustainable land management support businesses are established and functioning | a) Advisory services for analysis and development of the legal and regulatory framework to support broader adoption of renewable energy technologies (initially focusing on grid access and expanding as resources permit); b) workshops for information dissemination for the technologies that will be demonstrated and to publicize the RESP-2 credit line; c) energy audits for agribusinesses; d) capacity building for GHG measurement of project activities and sustainable agricultural practices (focusing on irrigated land); e) advisory services and twinning arrangements for development of renewable energy technology and sustainable land management support businesses f) Consulting services to advise RRA and banking sector how project activities can best be provided to transition to sustainability |  | 2,016,562 | 2,190,000 |
| Subtotal |  |  |  |  | 12,106,562 | 105,460,000 |
| Project management Cost |  |  |  |  | 592,438 | 2,500,000 |
| Total project costs |  |  |  |  | 12699000 | 107960000 |

- sources of confirmed Cofinancing for the project by source and by name ($)

| Sources of Co-financing | Name of Co-financier (source) | Type of Cofinancing | Cofinancing Amount ($) |
| --- | --- | --- | --- |
|  | World Bank IDA |  | 107,960,000 |
| Total Co-financing |  |  | 107,960,000 |

- GEF/LDCF/SCCF/NPIF Resources Requested by agency, Focal Area  and country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
|  |  |  | Uzbekistan | 11,609,000 | 1,160,900 | 12,769,900 |
|  |  |  | Uzbekistan | 1,090,000 | 109,000 | 1,199,000 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 12,699,000 | 1,269,900 | 13,968,900 |

- Consultants working for technical assistance components:

| ### Component | ### Estimated Person Weeks | ### Grant Amount ($) | ### Cofinancing ($) | ### Project Total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* |  | 1,472,300 | 24,921,000 | 26,393,300 |
| ### International consultants* | 493.00 | 1,634,268 | 3,879,000 | 5,513,268 |
| ### Total |  | 3,106,568 | 28,800,000 | 31,906,568 |

*  Details to be provided in Annex C.

- Project management cost

| ### Cost Items | ### Total Estimated Person Weeks/Months | ### Grant Amount ($) | ### Co-financing ($) | ### Project Total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | 1,248.00 | 245,400 | 1,157,335 | 1,402,735 |
| ### International consultants* | 6.00 |  | 100,000 | 100,000 |
| ### Office facilities, equipment, vehicles and communications* |  | 321,038 | 1,006,415 | 1,327,453 |
| ### Travel* |  | 26,000 | 236,250 | 262,250 |
| ### Others** |  |  |  | 0 |
|  | Specify "Others" (2) |  |  | 0 |
| Total |  | 592,438 | 2,500,000 | 3,092,438 |

* Details to be provided in Annex C.                    ** For others, to be clearly specified by overwriting fields *(1) and *(2).

- Does the project include a “non-grant” instrument?

(If non-grant instruments are used, provide in Annex E an indicative calendar of expected reflows to your Agency 
       and to the GEF/LDCF/SCCF/NPIF Trust Fund).

- describe the budgeted m &e plan:

The Rural Restructuring Agency (RRA), which is the same Project Implementation Unit (PIU) that is implementing the parent RESP-2, would provide daily management, administration and coordination of the project, including procurement, financial management, monitoring and reporting to the Bank and Line Ministries. A project Monitoring and Evaluation (M&E) system would be adapted to function within the existing M&E system managed by the RRA to monitor the existing RESP-2. This project M&E system would employ an adaptive management framework characterized by regular monitoring and evaluation, semi-annual reports on implementation progress, a comprehensive Mid-Term Review, and a final assessment (discussed below in more detail). Implementation of the M&E system would be the responsibility of the RRA, which would prepare semi-annual reports on implementation progress. These reports would include progress reports based on the Project Operational Manual’s timetable for the various project activities, the Procurement Plan and schedule, and the agreed Annual Operation Plans. Overall, the M&E system would track project impact, compliance of agro-businesses with the sub-project agreements, and performance in attaining results. This M&E system would have four modules: (i) a Management Information System to track results and financial indicators and provide feedback for decision making; (ii) investment sub-project agreement compliance; (iii) site-specific monitoring and assessment of GHG reduction, with baseline for all investment sub-projects and a sampling of 20 percent of sub-projects at both midterm and final points in the project; and (iv) standard annual auditing and supervision missions twice a year to review the technical, fiduciary, and safeguards aspects of the project. Project indicators and expected outputs of the M&E System are included in the Project Operation Manual and would be used to assess the performance of the various project components. A separate set of indicators would be used to monitor GEF-financed project activities and its impact on GHG emissions. In addition to the management budget, there are funds set aside to undertake field surveys under (iii) as part of a baseline, mid-term and final project review. For each of these surveys, $12,000 has been set aside, bringing the total M&E budget for these monitoring surveys to $36,000. The project unallocated funds and RESP II IDA resources will be used in the case of need more funding for the M&E purposes.

part ii:  project JustiFication

- Description of the consistency of the project with:

A.1.1.  The GEF focal area/LDCF/SCCF strategies/NPIF Initiative:

The project promotes effective GHG emissions control and sustainable land use and is consistent with two main focal areas of GEF, Climate Change Mitigation and Land Degradation. The project is in line with the Climate Change Mitigation focal area strategy and will contribute to Strategic Objective 2 “promote market transformation for energy efficiency in industry” and CCM-3 “promote investment in renewable energy technologies,” with emphasis on agri-businesses and rural communities. By doing so, it will also demonstrate new, little known technologies in the Uzbek agricultural sector. While the energy sector is responsible for greatest volume of GHG emissions (except methane), extensive support to implementing large scale solar to decrease reliance on gas-fired power plants is currently being undertaken by the Government in cooperation with ADB. The proposed project will directly respond to the strategic goals of the GEF-5 strategy in the Climate Change Mitigation focal area, namely promoting the use of renewable energy for the provision of rural energy services, improving energy efficiency in the agricultural (irrigation pumping) industry, and supporting new low-GHG emitting energy technologies. The project is consistent with the GEF-5 CCM-1 objective in that it would use south-south and north-south cooperation as well as institutional and technical capacity building and information dissemination to create an enabling environment for technology transfer, specifically for renewable energy (biogas, solar) and energy efficiency (energy efficient irrigation pumps) technologies. The project addresses priority needs identified by the Government and in consultation with key donors, and puts in place legal, policy, technological and business development measures to mainstream renewable energy in Uzbekistan’s energy sector by focusing on the introduction of relevant technologies and capacity building in rural areas. Therefore, the Project is well aligned with the Climate Change Focal Area. The project also responds to the GEF’s Objective 1 in the Land Degradation focal area to “maintain or improve flows of agro-ecosystem services to sustain livelihoods of local communities.” Rural communities in Uzbekistan will be supported to adopt, transfer and replicate sustainable agriculture and land management practices aimed at restoring and improving irrigated land while increasing economic opportunities for the rural population and improving environmental conditions. Finally, the project will carry out cross cutting activities to strengthen the capacity of the Uzbekistan legal and institutional system to develop and implement reforms to respond to challenges of climate change and land degradation in the agricultural sector.

A.2.   National strategies and plans or reports and assessments under relevant conventions, if  applicable, i.e.  NAPAS, NAPs, NBSAPs, national communications,  TNAs, NIPs, PRSPs, NPFE, etc.:

The Project is in full accordance with key national strategies that were articulated in the Second National Communication on Climate Change (November 2010), which was prepared in accordance with the United Nations Convention on Climate Change. The First National Communication of the Republic of Uzbekistan was prepared and submitted to the Fifth Conference of Parties to the Convention in Bonn in 1999. The Second Communication highlights the problems associated with climate change as a national priority, and notes particular challenges in implementing GHG mitigation measures and meeting international obligations under UNFCCC. Given the importance of the agriculture sector overall in Uzbekistan and the country’s vulnerability to climate change, the Second Communication also emphasizes land degradation in agriculture, stating that “ .the country faces a number of problems [in agriculture] due to lack of water resources and land degradation. Over 50% of land resources are used for agricultural purposes. Irrigated area of Uzbekistan is 4.2 million hectares of land with low productivity and high salinity rates. Wind and water erosions are widespread. Arable lands located in the lower reaches of the rivers are especially saline…” Water scarcity is expected to be further exacerbated by a warming climate. Uzbekistan’s Technology Needs Assessment (TNA) was presented to the COP in 2001. For the agricultural sector, it highlights several important sources of GHG emissions. The two most important are inefficient agricultural pumping and the need to process manure and crop wastes to better reduce methane emissions. In fact, the one activity highlighted as a priority is Use of agricultural biomass and wastes for energy generation. This proposal is fully consistent with the findings of the Uzbekistan Technology Needs Assessment. The Republic of Uzbekistan ratified both the UN Framework Communication on Climate Change and the Kyoto Protocol in 1993. The country continues to carry out wide-scale awareness raising activities on climate change to promote mitigation, contribute to the reduction of climate change risks, and build resilience to the projected impacts of climate change in the country. With respect to land degradation, the project also supports the priority actions identified in the National Action Program to Combat Desertification (NAPCD, 2002) and the objectives of the Central Asia Countries Initiative for Land Management (CACILM). The CACILM Multicountry Partnership Framework (CMPF) is one of six GEF country pilot partnerships (CPPs) on sustainable land management at different stages of implementation. CACILM is a multi-country and multi-donor, long-term program in the spirit of UNCCD aimed at restoring, maintaining and enhancing productive functions of land in the five countries of CA. In each participating country, National Programming Framework (NPF-2006) on Sustainable Land Management (SLM) forms its strategic basis. The overall goal of the NPF in Uzbekistan is to combat land degradation through the strengthening and mainstreaming of sustainable land management approaches among all land management stakeholders. Attaining this goal will result in stabilized/ improved ecological integrity and better rural living standards.

- Project Overview:
B.1. Describe the baseline project and the problem that it seeks to  address:

Uzbekistan is the second largest country in Central Asia by land mass, and the largest in terms of population. The country has a total land area of 447,800 km2, mostly flat to rolling sandy desert with flat, intensely irrigated river valleys along the courses of the two major rivers, the Syr Darya and the Amu Darya. The largest desert in Central Asia, the Kyzylkum, covers the greater part of the lowlands and plains in the west and south of Uzbekistan. Uzbekistan is a dry country, comprised of mountains (20%) and arid/semi-arid areas (70%) and experiences high solar radiation. This, combined with its landlocked situation and topographic relief, results in a severe continental climate with large diurnal and seasonal variations in temperature. Average precipitation in the desert is less than 200 mm per year. It reaches about 400 mm in the foothills and can go above 800 mm at altitudes between 1,000m and 4,000m. About 90% of the land area consists of mountains, desert and semi-desert, the rest being fertile valleys along major rivers. The population of Uzbekistan is estimated at 28 million and the annual growth rate is 2.3% which is one of the highest in Central Asia. More than half (about 60%) of the population of Uzbekistan is considered rural. The agricultural sector accounts for about 33% of gross national product (GNP), about 38% of employment, and about 40% of export income. Total agricultural land occupies 28.5 million hectares (or 63% of the total land area) including 23.4 million hectares (or 52%) that can be considered poor or low-productive pastureland, and 4.2 million hectares of arable land (approx. 11%). Due to its arid climate arable agricultural output is almost entirely dependent on irrigation. The total irrigated area is 4.2 million hectares, of which 4.1 million hectares is arable land with almost 3.4 million hectares cultivated with annual crops (grain, barley-corn, wheat, rice, corn, cotton, potato, vegetables). Cotton and grain are the most important crops in Uzbekistan; significant products include fruits (apples, apricots, peaches and berries), vegetables (cucumbers, tomatoes and potatoes), milk, silk and livestock. The sown area for cotton is 1.3 million ha, grain crops 1.2 million ha, potatoes and vegetables 50,000 ha, fodder 180,000 ha, and gourds on 20,000 ha. Agriculture also has a direct impact on and relationship with many other areas of the economy generating 70 percent of domestic trade, servicing 90 percent of domestic demand for agricultural products and processing of agricultural output accounting for 35-40 percent of all industrial output (7.7-7.8 percent of GDP). The policies of GOU in relation to agriculture have undergone major changes in the past years. The organization of farming was fundamentally reformed, with land passing from co-operative usage (kolkhozes, then shirkats) to a new class of private farmers. This was completed in 2007, with an average land endowment per farm of 26.2 hectares and approximately 1.8 million workers employed on the lands. In January 2007 there were 189,200 active private farms, as compared with 87,500 in 2003. The newly privatised farms account for over 32 percent of total gross agricultural output, including 86 percent of raw cotton and 73 percent of wheat production. The impact of the reforms has created a new class of private farmer, no longer subject to direct government management, but equally not supported by direct government service and input supply. Due to the competitive nature of land allocation, many of the farmers have detailed knowledge of the agronomic practices required for farming, but lack the management skills required to operate their farms as private business. In addition, the reform of the financing system means that farmers now have to seek financing from the commercial banking sector (especially for non-cotton crops), a practice for which they have little experience. The fundamental reform of the structure of farming has also created a new challenge in relation to irrigation and drainage (I&D). There is now a specific division of responsibility, with inter-farm and upstream infrastructure and works being the responsibility of the government, whilst the on-farm I&D is now the responsibility of the newly privatised farmers. Much of the I&D infrastructure is over 30 years old, and has suffered from a lack of investment and maintenance (funding currently estimated at 40-50 percent of required levels) in the past 15 years. Estimated yield losses due to lack of timely water supply and increasing salinization are high at almost US$ 1 billion annually. The government has noted these specific problems in the Welfare Improvement Strategy and has recently passed a Decree creating a fund of almost US$ 50 million for investment, mainly in inter-farm drainage system rehabilitation. Of equal importance is the establishment of Water Users’ Associations (WUAs) for managing on-farm I&D operations and maintenance. Whilst initial steps have been taken in this area, success to date in creating viable, sustainable WUAs has been elusive. The effect of the reforms is having a noticeable impact in the financial sector. Loans to agriculture in the banking sector amounted to 3 – 5 percent annually during 2002-2005. In 2006, the share of agricultural loans increased to about 14.2 percent of the total banking sector portfolio (largely due to government programs being channelled through the banking sector). In 2006 agricultural lending stood at 10 percent of agricultural GDP. The exposure and activity of individual banks differs greatly (from 3 up to 50 percent of total portfolios). In the Credit Union (CU) sector, lending for agriculture ranges between 15 percent and 30 percent of total portfolios. Availability of financial services for rural areas remains an acute issue, as access is more limited than in urban areas, whilst rural demand is increasing dramatically (partly as a factor of the privatization of farmers). Provision of adequate financial services to the general agri-business sector remains constrained by several factors such as lack of collateral; low capacity of banks to assess agricultural risk; low capacity of Recipients to prepare business plans; and lack of long term funding sources. Addressing these shortcomings remains a major challenge in promoting rural growth. In view of the importance of agriculture and its potential for adding to overall economic growth and raising rural incomes in the coming period, the government is keen to develop the sector and has raised its importance on the economic agenda. A number of government-led and also donor financed projects are being undertaken to address the major challenges created by the recent reforms. Baseline Project. The Uzbekistan Government requested Bank’s support to address the above problems. As a result, the 2nd Rural Enterprise Support Project (RESP-2) has been developed, consisting of the following components: Component 1. Rural Finance, to (i) enhance access to commercial financial services by the newly independent farmers and small/ medium size rural enterprises, and (ii) reduce the risks associated with lending to the agriculture sector by providing assistance to the potential recipients on business planning and improving the sector-specific lending skills of the staff of the commercial lenders through training. Component 2. Irrigation and Drainage, to improve water management of irrigated areas in these seven districts, through investments in: (i) the rehabilitation of critical inter-farm and on-farm I&D infrastructure; (ii) strengthening WUAs and the institutional capacity to train and support WUAs to rehabilitate, operate and maintain on-farm I&D systems; (iii) investments in demonstration plots in the district for applied modern irrigation techniques. Component 3. Rural Training and Advisory Services, to (i) provide training and advisory services to newly independent farmers in various farm management skills (e.g. legal, accounting, business, technical aspects including agronomy, water management, pesticide handling, IPM etc); and (ii) increase availability of technical information and advisory services. Component 4. Project Implementation, for overall management, monitoring and evaluation. Baseline Project Financing and Benefits. The total financing is US$115 million, comprising US$107,960 million credit from the International Development Association (IDA), US$6.58 million from the Government contribution and US$0.460 million from the beneficiaries. The baseline project objective is to increase the productivity and financial and environmental sustainability of agriculture and the profitability of agribusiness in the project area. This will be achieved through the provision of financial and capacity building support to farmers and agribusinesses in seven regions of the Republic of Uzbekistan (covering around 65 percent of the total population of the country), and improved irrigation service delivery through rehabilitation of I&D infrastructure and strengthening of WUAs in seven districts within following seven regions: Andijan (Ulugnor district), Bukhara (Alat district), Kashkadarya (Mirishkor district), Samarkand (Pastdargom district), Syrdarya (Bayavut), Tashkent (Buka district), Fergana (Yazyavan district). Key baseline project outcome and output indicators are as follow: Outcome indicators - Farmers in project regions will have increased their overall productivity and income - Farmers and agribusiness access to information about and demonstrations of environmentally sustainable practices improved; 10% of farmers in the project area who benefit from RTBAS activities will have begun to adopt these practices by end of project. - Farmers and agribusiness access to financial services improved: growth in overall agricultural portfolio of the commercial banks at least 10 percent per year during the project period - Microfinance institution outreach improved: the aggregate agricultural lending by microfinance institutions increased 10 percent during the project period - Increased irrigated areas with adequate water supply and drainage in the project districts. - Increased amount of maintenance work undertaken by WUAs in the project districts. Output indicators - At least 700 loans/leases provided under the credit component - At least 100 micro-loans (up to US$ 10,000) provided under the project - At least 200 loan officers and branch managers trained - At least 4 PFIs participate in the project, of which at least one is new, i.e., did not participate in the first RESP - At least 600 km of irrigation and drainage networks will be rehabilitated. - At least 75 WUAs will have developed and budgeted operation and maintenance plans - Basin administration authorities will have increased capacity to provide advice to WUAs. - At least 50,000 independent farmers will have received training in a number of critical farm management skills.

B. 2. incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:

The GEF grant would make possible the introduction of renewable energy and energy efficiency technologies and more sustainable irrigated land use practices, which could receive very only limited resources within the baseline RESP-2 project. The GEF grant would be of particular significance to Uzbekistan: while the baseline project supports improved rural access to credit, capacity building, and rehabilitation of I&D systems, it does not emphasize or provide dedicated resources to introduce renewable energy technologies in agribusinesses and on farms, nor approaches for improved flow of agro-ecosystem services to sustain rural communities. These communities, large private farmers and small farmers, especially those in remote regions subject to unreliable power and gas supply, would benefit greatly from off-grid energy from renewable sources. At the same time, the project would begin to introduce renewable energy technologies in rural areas throughout the country, thus supporting a key Government development objective. The rural communities and agribusinesses depend on irrigated land and livestock for their livelihoods, creating both inputs for renewable energy (manure, biomass) and demand for energy and sustainably managed irrigated land. While Uzbekistan has good supplies of natural gas, the Government is keen to develop renewable energy sources both to free up for export gas currently sold at low domestic prices, and to fulfill their obligations under UNFCCC. The proposed GEF project concept was endorsed by the Government Inter-Agency Working Group Meeting on 30 June 2011, as having great value for sustainable economic development, especially in rural areas. The current unsustainable exploitation of soil and water resources would be addressed through a combination of investments for the prevention and mitigation of irrigated land degradation. Increase of evaporation due to global warming will lead to water loss in the irrigation zones, while irrigation demand is expected to increase in average by 5% by 2030, 7-10% by 2050, and 12-16% by 2080. The expected decrease of river water resources will lead to worsening of the water scarcity situation, which will be especially acute during low-flow years. Livestock is an important and growing source of methane emissions. The number of cattle, sheep and goats, and poultry has increased by 35%, 29% and 81% respectively from 1996 to 2010. The increase in livestock has led to the growth of methane emission by 33.1% and of nitrous oxide emissions by 26.4%. Improved water resources management, rehabilitation of degraded irrigated land and reduction of GHG emissions from agricultural sources are thus a high priority for the Government, as reflected in the Second National Communication on Climate Change and the National Programming Framework under CACILM. Detailed analysis of the cost effectiveness and incremental environmental benefits in terms of greenhouse gas emissions avoided in provided in Section B.6 below. The implementation of these incremental activities would generate significant global environment benefits while supporting local and national, social and economic development through promotion of environmentally sound, climate-friendly technologies to achieve significant GHG reductions (tons of CO2 equivalent); reversing the current trend in land degradation and promoting water conservation in agriculture; supporting creation of more productive and sustainable agri-businesses; and introduction of climate change adaptation measures to address Uzbekistan’s increasingly dire water shortages. The main areas supported by the GEF grant would be the following: promoting the use of renewable energy for the provision of rural energy services and supporting new low-GHG emitting energy technologies; introducing legal, policy and technological measures to mainstream renewable energy in Uzbekistan by developing renewable energy legislation, technologies and capacity building in rural areas; and supporting rural communities to adopt sustainable agriculture and land management practices aimed at restoring and improving irrigated land while increasing economic opportunities for the rural population. Finally, the project will carry out activities to strengthen the capacity of the Uzbekistan legal and institutional system to develop and implement reforms to respond to challenges of climate change and land degradation in the agricultural sector. While there is keen interest in adopting renewable energy and improved land management approaches, Uzbekistan has little experience with the technologies and practices involved. Good interagency coordination on climate change and energy policy is expected through the active engagement of the Ministry of Economy Interdepartmental Council, which serves as the national authority for Kyoto Protocol implementation, and the Center for Hydrometeorology under the Cabinet of Ministers, responsible for UNFCCC implementation. The GEF grant would support development of national level legislation and institutions which would provide overall guidance on the introduction and use of renewable energy technologies. This would include: technical assistance for the legislative review and reform; capacity building to strengthen the Eco-Energy Center (under the State Committee for Nature Protection), Ministry of Agriculture and other key government institutions, and the private sector service providers; dissemination of best renewable energy and land degradation mitigation practices and results to facilitate replication and sustainability; and knowledge programs and exchange programs to facilitate acquiring best international expertise in the area. These activities would complement the Rural Finance, I&D, Capacity Building and Project Management Components of the baseline project as follows: 1) Investments for sustainable technologies. Activities under this component would aim at introducing renewable energy and energy efficiency technologies in small and medium size (SME) agribusinesses and on small and large farms. The GEF grant would support innovative technologies that could have a significant impact in the long-run in reducing GHG emissions and developing capacity for adaptation to climate change. This could also include technologies that are available but have not yet been tested and or widely adopted in Uzbekistan. One such example would be the bio-gas digestors, which would use poultry and livestock manure to produce gas and electricity for farm households and agribusinesses. Other renewable energy technologies could include solar (photovoltaics and water heaters), biomass (using cotton stalks and/or sorghum), wind and micro-hydroelectric installations. With respect to energy for irrigation within the agricultural sector, the focus will be on increasing the market for more efficiency on-farm irrigation pumps. The GEF grant would support initial demonstrations of the technologies, and then provide matching grant funds to scale up their introduction. It is envisioned that the grants would initially cover 80% of the costs for demonstration activities decreasing to 60% and 40% as the up-take grows, the market matures and the project approaches closure. The beneficiaries could apply to the credit line under Component 1of the baseline project for their portion of the co-financing. This would improve the financial sustainability of the sub-projects financed under the credit line, and provide needed portfolio diversification under RESP-2. 2) Irrigated land degradation mitigation. Activities under this component would aim at introducing technologies and management approaches for controlling and reversing irrigated land degradation. This could include introduction, testing and demonstration of the integrated low-cost, low-risk water and land management technologies, such as drip irrigation, salinity mitigation of marginal land, water re-use, soil quality enhancement, pumping for groundwater extraction, alternative cropping, and other techniques or practices to increase water use efficiency and agricultural productivity. This component will improve knowledge, skills and know-how of farmers and local communities and promote the transfer of demonstrated technologies and SLM practices through the Farmer Field School (FFS) approach. These activities would be targeted to the rayons participating in the Irrigation and Drainage Component of the baseline project, which are receiving funds and technical assistance to repair and upgrade irrigation infrastructure. 3) Project technical support and advisory services. Activities under this component would support key capacity development and analytical services needed to introduce and scale up adoption of renewable energy, energy efficiency and land degradation mitigation technologies and practices. These are expected to include workshops and information dissemination for the technologies that will be demonstrated and to publicize the RESP-2 credit line, energy audits for agribusinesses, capacity building for GHG accounting linked to project activities and sustainable agricultural practices (focusing on irrigated land), and advisory services and twinning arrangements for development of renewable energy technology and sustainable land management support businesses. This component would also help to introduce systems for sending timely weather data by mobile phone text messages or voice mails to farmers to enable better planning (e.g., when to apply fertilizers, when to harvest crops) and response to extreme weather events. The GEF grant would also support advisory services for analysis and development of the legal and regulatory framework to support broader adoption of renewable energy technologies, focusing particularly on the issue of access to the grid for renewable energy generators. Technical assistance to help ease the transition from the project’s subsidy-based system to a sustainable, post-project system will be provided. These activities would complement the Rural Training and Advisory Services Component of the RESP-2 baseline project, and strengthen environmental oversight and impact of RESP-2. The GEF grant is of major importance for the Government of Uzbekistan. In the absence of the proposed GEF Grant, the Government of Uzbekistan would have limited funding and access to best international practice to test and implement new technologies for reduction of carbon emissions and to mitigate degraded irrigated land. Without the GEF Grant, the Government would also lack the needed incremental support to demonstrate, disseminate and promote the appropriate technologies that increase sustainable agricultural production and reduce degradation of natural resources. The GEF Grant would also contribute significantly to the improvement of the country’s legal, institutional and regulatory environment with respect to climate change and land degradation, as well as provide the resources for provision of advisory services to rural communities. As the nation’s second largest GHG emitting sector, agriculture has an important role to play in the mitigation of greenhouse gas emissions in Uzbekistan, with many of the practices that have benefits for both productivity improvement and adaptation also having synergistic mitigation benefits (i.e. “win-win-win”).

B.3. Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF). As a background information, read Mainstreaming Gender at the GEF.":

At the local level, the baseline project together with the proposed GEF grant are expected to bring tangible benefits to farmers and small and medium sized agribusinesses in rural communities through improved access to bio-gas for heating, cooking and electricity, and through reduced energy requirements for irrigation pumping, increased productivity, provision of renewable energy technologies, and sustainability of irrigated agricultural land. This would be evidenced by: (i) improved livestock and poultry waste management and the number of households and SMEs adopting renewable energy technologies and decreasing their reliance on the national gas and electricity grids; (ii) increased efficiency of irrigated land management, as measured by increased agricultural productivity and diversification of produce, and improved soil and water quality; and (iii) increased number of technical service providers to support the introduction and maintenance of renewable energy and sustainable irrigate land management technologies. The project will benefit women in rural areas. While the project is not directly targeting women, its implementation mechanisms ensure women’s equitable access to resources and equitable representation in decision making. This suggests that women and women’s groups are likely to benefit from the project. Furthermore, a number of measures towards highlighting and intensifying women’s role and involvement in social and economic life of rural communities will be undertaken under the project. This will include alternative opportunities for women’s entrepreneurship and employment through the baseline project credit line, which supports village-level agri-business and farmer groups to develop new business opportunities, improve marketing, and introduce and demonstrate new renewable energy and irrigate land management technologies that could benefit communities..

B.4  Indicate risks, including climate change risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks to  be further developed during the project design:

The key risks that may affect the project objective and proposed mitigation measures are described below. Climate change. According to Uzbekistan’s Second National Communication on Climate Change (2010), intensive warming is observed on the whole territory of Uzbekistan. Variability in climate is expected to generate important socioeconomic and environmental consequences, especially for water resources. Average annual temperature has already increased by 0.29°С since 1951. Significant increase in repetition of high temperatures has been observed during the last decade. With further of acute water scarcity (assessment for extremely warm and dry years), flows in the Syrdarya and Amudarya Rivers Basins might decrease by 25-50%. The activities envisaged under this GEF grant would contribute to mitigating and adapting for these water scarcity, land degradation and increased GHG emission risks. Legal and institutional framework. Uzbekistan’s institutional capacity and technical expertise in land degradation mitigation, renewable energy technologies and climate change adaptation are weak. The Second National Consultation notes that development and implementation of mitigation and adaptation measures are the major priority issues in the area of Climate Change. Overall challenges existing in this area include lack of organization, technical and financial resources, qualified personnel and insufficient legal base. To mitigate this risk, the project will support policy dialogue and technical assistance to develop the legal and institutional framework. The project would also address the lack of technical capacity to establish, operate and maintain innovative sustainable renewable energy and land degradation mitigation technologies. Acceptance and sustainability of sustainable technology investments. Visible benefits of rural investments, in particular those concerning alternative energy technologies and rehabilitation measures for degraded lands, may take longer than expected, thus impacting on the local communities’ and SMEs’ acceptance and continued use of the new technologies and land management approaches. Most of the country is adequately served by the national electricity and natural gas supply grids at modest cost, although service can be intermittent, especially for remote rural communities. In order to mitigate this risk, the GEF project would support initial demonstration of innovative technologies and approaches, complimented by a strong information dissemination and capacity building program. The risk would also be mitigated by focusing on introducing renewable energy technologies in communities poorly served by the natural gas and/or electric grid, as interest and demand should be stronger there. Adaptation of new low carbon technologies to Uzbekistan’s specific climate conditions. The new technologies, even if proven successful elsewhere, might not be suitable to Uzbekistan’s conditions. To mitigate this risk, South-South cooperation will be promoted, in addition to technical assistance and studies to test, demonstrate and transfer these technologies..

B.5. Identify key stakeholders involved in the project including the private sector, civil society organizations, local and indigenous communities, and their respective roles, as applicable:

The key stakeholders and beneficiaries of the project will be the Ministry of Agriculture and its provincial and district departments, UzHydromet, the Eco-Energy Center (under the State Committee for Nature Protection), Uzgip Institute, other government institutions, SMEs, new private sector service providers, small and large scale farmers, local governments and rural communities would benefit from participation in capacity building activities. The Rural Restructuring Agency (RRA), which is same Project Implementation Unit (PIU) that is implementing the baseline RESP-2, will provide daily management, administration and coordination of the project, including procurement, financial management, monitoring and reporting to NSEC CACILM, as well as technical and other oversight in accordance with GEF and World Bank rules and procedures. A range of civil society organizations, donor and government agencies are expected to participate in project networking and dissemination activities. Farmers, Householders, Agricultural and Agribusiness Enterprises will benefit will benefit from access to grant funding for introduction of RE/EE technologies.. B.6. Explain how cost-effectiveness is reflected in the project design: The project envisions supporting investment loans and subsidies for farm-based renewable energy and energy-efficient installations: biogas plants; solar water heaters; solar photovoltaics; and energy efficient irrigation pumps. All of these investments can be attractive to rural farmers to increase their productivity and income, but the benefits are often difficult to measure accurately in the case of a nascent market where the applications have not yet been demonstrated. The market, financing, and economics of each of these installations and of the project structure as a whole are explained in the following section to the extent that existing data can be gathered or adopted from other contexts. Biogas Plants Livestock ownership in Uzbekistan has been growing in the past 15 years, providing up to an estimated 40 percent of agricultural product. Animal husbandry in Uzbekistan traditionally has been dominated by agricultural families and not by the large agricultural enterprises, which in the past prevailed in the production of crops. More than 50 percent of cattle were owned by agricultural households in Soviet times. After 1995, total cattle in Uzbekistan grew from 5 to 9.5 million, and this growth took place mainly in household plots and exceeded the reduction rate of agricultural enterprises because of privatization in the animal husbandry sector. Farm communities play a marginal role in animal husbandry: cattle in farm communities have grown with time but it still does not exceed 5 percent of the total cattle in the country. This indicator strongly differs from the share of farm communities in land use – this figure has reached 65 percent of arable lands and almost 30 percent of agricultural lands in 2006. The total share of private sector in animal husbandry (individual (dehkan) farms and farm communities together) has reached 98 percent in cows, 96 percent in cattle, and 80 percent in sheep and goats, whereas most cattle are concentrated in household plots and not in farm communities. While dehkan farms dominate in the animal husbandry sector of Uzbekistan, an average dehkan community has only 1.4 cattle and 0.8 cows against 42 cattle and 13 cows in livestock farm communities. Thus, most cattle in Uzbekistan belong to very small household units: 4.5 million households own more than 6 million cattle including 2.7 million cows—more than 90 percent of the livestock population in Uzbekistan. For this reason, the project plans to promote initially biogas plants in three standard sizes: small, with tanks of roughly 6m3; medium, with tanks holding up to 60 m3; and large, with tanks as large as 2400m3. This is not to say that custom-sized plants cannot be supported under the project, but rather that for early, rapid growth in terms of financing and installations, it makes sense to promote standard-sized units that may be available from many different suppliers. The smaller plants are targeted at dehkan farm households to supply gas for cooking and heating, and limited electricity. The smaller plants may draw upon designs from China or Nepal. The medium-sized plants would be fewer in number and would be targeted at medium-size farm communities and agro-industry. The large-scale plants are oriented toward agro-industrial facilities. For the medium and large sized plants in the demonstration program, they would have to be procured via international competitive bidding (ICB). Based upon the assessment undertaken at the preliminary stage, few such large, modern facilities have been built in Uzbekistan. Table 1 below summarizes the financial characteristics of each of the biogas plants proposed for promotion under the project. For all of these plants, the financial internal rate of return exceeds 12 percent, with the smallest being the least profitable at 17 percent and the two larger ones being estimated at 18 percent and 21 percent, respectively. It is worth noting that the greatest value produced by these plants under current economic conditions is that of the fertilizer, comprising over 50 percent of the potential revenues or savings from these installations. The value of the solid ($27/tonne) and liquid fertilizer ($13.4/tonne) is taken from farm-gate prices currently being obtained by farms with operating biogas producers. The assumption that farmers installing biogas plants can obtain adequate compensation for fertilizer production from biogas either through market sales or own application (and either reduced expenditures on fertilizer or increased yields) is critical to the success of the undertaking. Until regulations requiring the electric utility to take and pay for electricity from independent renewable generators, the compensation for electricity from these plants will be the smaller and possibly even more uncertain revenue component of the biogas projects. Hence, proponents of this project need to strategically utilize the resources available under Component 3 to advance the improvement of the renewable energy policy and regulatory framework. Table 1: Financial Analysis of Proposed Models of Biogas Plants Item; Pilot Plant 1; Pilot Plant 2; Pilot Plant 3. Animal waste processed per day (t/day) Size of Bioreactor Tank (m3); 0.25 6; 2.5 60; 30 2400. Number of Livestock Units; 3; 60; 700. Total Investment Cost; $2,508; $55,000; $805,000. Annual Savings/Revenue; $525; $11,505; $115,050. Internal Rate of Return (FIRR); 17%; 18%; 21%. Net Present Value (NPV) in Financial Terms (i=12%); $816; $23,007; $507,003. Simple Payback Period; 5.65 years; 5.27 years; 4.5 years. Greenhouse Gas Emission Reductions (including both methane conversion and substitution in electricity generation); 438; 16,422; 321,339. Investments in all of these plants would appear to be profitable and attractive as individual farmers’ investments. The participating financial institutions (PFIs) would require assistance in evaluating these plants, as they are a new form of investment, and financing packages would need to be structured around their unique characteristics. Work with local supply companies and farmers would need to be undertaken to stimulate both the demand and supply side of the market for this technology. The most likely adjustments to the financial analysis to correct for market imperfections or faulty assumptions would take place in three areas. First, because there is the risk that not all farmers would be able to monetize the value of the fertilizer, there is a need to see what a reduced fertilizer value would do to the attractiveness of the investment. A higher price for the biofertilizer would serve to increase the return on the plants. The critical test applied to the scenario applications is to reduce the value of the fertilizer by half to demonstrate the value of the project if it is less marketable or productive than anticipated. A second necessary economic adjustment would be to see what might happen if the willingness to pay for electricity were set at a higher level. The current tariff is US$0.05 per kWh, and so this figure was used in the analysis, but this does not represent the true export or border price of the natural gas being exported to Europe. If this gas were used instead to fire the local grid, the value of the electricity would rise to a higher level. In a similar manner, if a premium were placed on renewable-generated electricity, the value of electricity would also be higher. For this scenario, a value of US$0.08 per kWh was used to test the robustness of the economic returns. . For households currently without access to electricity, the willingness to pay is no doubt much higher, but no good estimates have yet been undertaken to estimate this value. The third risk element has to do with the cost of the plants. In each case, the estimates above are based upon estimates made given knowledge of conditions in Tashkent. No transportation to the rural areas has been included in the cost. There is also the possibility that these costs would in actuality run much higher than estimated. Therefore, there is a need to evaluate economic performance with a 50 percent cost over-run in capital costs. These elements of risk to the financial viability of the biogas investments are summarized in Table 2 below. With respect to the risk of fertilizer prices or responses from own-farm use, the smallest of the plants appears to be most susceptible to this risk. If the fertilizer value is 50 percent or less than 50 percent of the farm-gate price estimated in this feasibility work, then the returns for all three pilot farms drops below the FIRR hurdle rate of 12 percent. With respect to a higher estimate of willingness to pay for electricity, if this begins to approximate a world market price of about US$0.08 instead of the tariff cost of US$0.05, the attractiveness of all three pilot biogas investments increases. With respect to the construction cost overrun, the smallest of the pilot plants falls to just slightly below economic attractiveness, with the internal rate of return falling slightly below 12 percent and the NPV becoming negative. The case of the medium-sized plant is similar, with cost over-runs leading to an 11% rate of return and a slightly negative FIRR. However, the largest pilot model retains its financial attractiveness under these conditions. Table 2: Financial Risk Scenarios Pilot Farm 1 (6m3); Pilot Farm 2 (60 m3); Pilot Farm 3 (2400 m3). Fertilizer prices lower than estimate ($13.5/ton for solid and $6.7/ton for liquid); FIRR= 9% NPV@12% = $(494) Payback = 8.5 years; FIRR =12% NPV@12% = $1,194 Payback = 7.64 yr; FIRR = 11% NPV@12% = $73,678 Payback = 8.22. Willingness to pay for electricity ($0.08 instead of $0.05 per kWh); FIRR= 20% NPV @ 12%= $1,336 Payback = 4.89 years; FIRR = 23% NPV@12% = $42,500 Payback = 4.21 yr; FIRR = 17% NPV@12% = $250,896 Payback =4.26 yrs. Construction Costs Over-run by 50%; FIRR = 12% NPV @ 12% = $(65) Payback = 7.60 years; FIRR = 11% NPV@12% = $4,493 Payback = 7.9 yrs; FIRR = 13% NPV@12% = $104,533 Payback = 6.87 yrs. Based upon this analysis, clearly the small plants demonstrate the greatest vulnerability to possible alternative economic assumptions. As smallholders always face tighter margins and greater vulnerability to fluctuations of a natural or economic nature, this is not surprising. For the project to ensure profitable outcomes at the individual investment and programmatic level, efforts need to be made to ensure that the biofertilizer market develops, the electric grid operators are encouraged to pay renewable generators a reasonable rate for their inputs to the grid, and that construction (and transport costs) are carefully controlled. Nature and Structure of GEF Subsidy for Biogas Plants The GEF contribution to the project would be used to remove barriers, including financing barriers, to the widespread adoption of biogas and other sustainable energy options in rural Uzbekistan. Experience from other GEF-sponsored projects has shown that the value in the incremental financing provided by GEF is in providing pilot, demo and softer-termed financing to enable bankers and farmers to experiment and learn. In the case of these proposed biogas investments, the GEF incremental contribution would be used as a larger portion of the subsidy for the early adopters and the fraction of the total investment provided by the subsidy be reduced over time as familiarity with the technology grows, and the cost of the investment declines as the market scales up. But the incremental cost contribution is justified on the basis of the limited experience with these technologies, the marginal returns that the technologies may face, and the large uncertainties prevalent in this market. The administration of the subsidy is envisioned as being applied in three stages. In the first stage, the small and medium demonstration projects will be supported with a grant element of up to 80% of the cost. They will be shared-cost, market-based demonstrations installed in farms that have demonstrated interest and satisfactory design qualifications and have the credit-worthiness (or capital on hand) to be able to finance the remaining costs. As past demonstrations have shown, full-cost demonstrations (where the entire value of the investment is subsidized) tend to fail largely because the owner or recipient has no stake in the plant. Therefore, the beneficiary of the grant element for the small and medium-sized biogas plants will receive a grant equal to 80 percent plant’s costs, declining to 60% and 40% of the plants costs as the project progresses (see Table 3). The beneficiary will either finance or provide from its cash reserves the remaining 20 percent of the costs, increasing to 40 and 60 percent of the costs, respectively, during the latter stages. For the largest size biogas plant, the grant element will be handled differently, at least during this first stage. The objective for the large plant during this first stage is to introduce international, best-practice technology into the country, not to test the business model. Therefore, this first plant—a demonstration plant—will be procured through international competitive bid. The grant element will be limited not to 80% of the cost, but will rather be capped at $500,000 maximum (62% of estimated plant costs). The winning proposal will be selected and the plant installed via normal goods and civil works procurement. Subsequent installations of the large plants will be eligible for either the 60% or 40% subsidy, as appropriate, and will be selected via normal business practice with the rural banks undertaking normal due diligence processes. Thus, the second and third stages for the large plants will test the financial intermediary mode with a declining subsidy. As with other elements of the project, the Steering Committee will have the responsibility to review and modify the subsidy and procurement arrangements for all technologies sponsored under the project. Following these initial demonstration facilities, the proposal would be to support early adopters (investors in years 1 and 2 of the project) of the technology with a 60 percent grant element and 40 percent loan or equity contribution. If the banks or farmers are willing to finance a higher share of the investment, they may do so. As the project progress into its final two years , it is proposed to reduce the grant element to 40 percent of the total cost of the investment, with 60 percent of the investment being covered by a loan-equity arrangement. This “phasing-down” of the grant element is designed to increase the share of loan or equity in the financing and to prepare participants in the market for the unsubsidized future expected at the end of the project period. These proposed terms—which would have to be adopted and adjusted by the Project Steering Committee—are summarized in Table 3. The Steering Committee should also be provided with sales and uptake information so that if there is one type of plant whose distribution is lagging or one whose uptake is moving faster than expected, they can make a rationale decision about shifting resources from one-size category to another. Table 3: Stages of Project and Financing Mixture Stage; Grant Element; Loan/Equity. Step 1: Demonstration and Pilot Phase; 80%; 20%. Step 2: Early Adopters; 60%; 40%. Step 3: Market Maturation; 40%; 60%. Given the above stages and the need to ensure strong ownership on the part of beneficiaries, it is proposed that based upon the costs in the pre-feasibility studies, the following would be the proposed level of grant, loan, and equity for the various stages of the project (Table 4). These figures can be used to estimate the likely numbers of installations of each kind of biogas plant that can be supported under the project. Table 4: Breakdown of Grant, Loan and Equity Funds over Project Stages Plant 1; Plant 2; Plant 3. Stage 1: Demo Stage--Total Cost; $2,500; $55,000; $805,000. Grant (80%); $2,000; $44,000; $500,000 (note: capped at 62% of costs). Loan/Equity (20%); $500; $11,000; $305,000. Stage 2: Years 1 and 2-Early Adopters-- Total Cost; $2,500; $55,000; $805,000. Grant (60%); $1,500; $33,000; $483,000. Loan/Equity (40%); $1,000; $22,000; $322,000. Stage 3: Years 3 and 4 Market Maturation-- Total Cost; $2,500; $55,000; $805,000. Grant (40%); $1,000; $22,000; $322,000. Loan/Equity (60%); $1,500; $33,000; $483,000. For the demonstration stage, it is anticipated that only one of the largest biogas plants would be built as it would require nearly 50 percent of the US$1 million set aside for demonstrations. Given its size, this plant would have to be obtained through international competitive bidding (ICB). Two of the medium-sized plants would be built during the demonstration period, requiring $88,000 of the demonstration budget support. The 20 smaller units to be demonstrated would require US$40,000 of the demonstration budget. If these are the final biogas installations piloted under the project, that would correspond to US$628,000 out of the US$1 million set aside for demonstrations. The number of investment-stage installations and the budget set aside for them will depend entirely upon the uptake or expressions of interest from the market. As dekhan farmers would constitute the target beneficiaries for the smallest plant, a marketing or outreach program would have to be designed for them. For the medium and large-size plants, a more selective, targeted outreach program would have to be implemented in close collaboration with the RRA and the participating banks. The Project Steering Committee would have the authority to set and alter the level of the grant and loan requirements, subject to the Bank’s no objection, steering the project from stage to stage, as deemed appropriate. As specified above, it would also have the authority to shift resources from one size of biogas plant or from one technology where there is no technical demand to another. A “back-of-the-envelope” estimate of the number of installations expected under the project might be as many as 775 small installations; 90 medium-sized installations; and 4 larger installations. If these numbers are targeted for the investment phase of the project using the grant/equity/loan element presented above, the total cost to the project would come to US$10 million, of which approximately US$4.6 million would be paid out in grants. Table 5 breaks down the arbitrary targets for investment installations so that plants built during years 1 and 2 receive a 60 percent grant and those built during years 3 and 4 receive a 40 percent grant. The assumption is that the market and the demand are growing as the market moves from supporting only early adopters to approaching Market Maturation. These figures show that these goals are more than within reach in the budget of the project, and would result in significant GHG savings. The total savings from these investment stage installations comes to about 2.0 million tonnes of CO2 equivalent. The total investment cost to the project of these 1,200 installations, not counting the pilot/demo facilities, comes to US$5,047,000. Table 5: Costs and GHG Results of Sample Biogas Investment Program Plant 1 6m3; Plant 2 60 m3; Plant 3 2400 m3. Stage 2 Target Installations; 125; 3; 2. Stage 2 Subsidy; $1,500; $33,000; $483,000. Stage 2 Cost of Subsidy to Project; $187,500; $1,155,000; $966,000. Stage 2 GHG Avoidance (t CO2eq); 55,000; 575,000; 642,678. Stage 3 Target Installations; 650; 55; 2. Stage 3 Subsidy; $1000; $22,000; $322,000. Stage 3 Cost Of Subsidy to Project; $650,000; $1,210,000; $644,000. Stage 3 GHG Avoidance (t CO2eq); 285,000; 903,000; 642,678. Total Cost to Project; $837,500; $2,365,000; $1,610,000. Total GHG Emission Avoidance; 339,000; 1,478,000; 1,285,000. Solar Photovoltaic Water Pumps for Remote Livestock Posts With the recent rise of livestock ownership and farming across Uzbekistan, there is an increased need for livestock farmers to be able to provide clean drinking water to their herds in remote areas. Such an activity will assist in maintaining the health of the herds and thereby increasing both the quality and quantity of the product. The quantities of water required to be pumped for such applications remains limited, at approximately 50 tonnes (or m3) per day, which is considered insufficient to draw-down local groundwater. The systems being promoted for this activity would require approximately 1.1 kWp of solar capacity; would be able to pump water of approximately 50 m of head; and would reduce about 15 tonnes of CO2eq over their lifetime (assuming a diesel pump-set equivalent baseline). Several local companies are able to supply suitable water pumping systems made up largely of imported components. However, none of these companies yet operate at a significant scale. In order to “jump-start” this market, the demonstration phase will include 4 of these PV-pumping water stations to be demonstrated in the oblasts participating in this project. Each system is estimated to cost approximately US$20,000 and will receive an 80% subsidy for the demonstration phase. As with the other demonstration technologies, the investment installations will receive a 60% grant and a 40% grant during the “early adoption” and “market maturation” phases, in keeping with the support for other technologies under the project. As with other technologies new to Uzbekistan, it is not clear exactly how many such systems can be sold and installed during the life of the project. For the sake of project costing and assessment, it has been estimate that 15 such systems will be installed during years 1 and 2 of the project, and 60 will be sold during years 3 and 4. Altogether, the project is anticipating support to 79 PV pumping systems for providing water to remote livestock posts. The baseline assumes that in the absence of these PV-pumps, water would be pumped through small-scale diesel pump-sets. These investments are estimated to result in 1185 tonnes of CO2eq reduction per pump over their lifetime. Solar Water Heaters and Collectors for On-Farm Applications For this project, the primary objective of promoting solar water heaters is in the context of enhancing agricultural production through improving productivity on dairy or poultry farms or through applying solar collectors to greenhouses. Utilizing warm water, especially in winter months, helps increase the productivity and health of livestock and is a potential key to raising on-farm productivity. Greenhouses operated on small farms can help increase the production of those farms by enabling them to grow out-of-season vegetables for private sale. Several local companies produce solar collectors for water heating, but they are currently targeted at primarily the domestic market. In rural areas, they are frequently sold to private clinics in rural areas. Part of the promotional role under Component 3 will involve working with potential farmers and industry actors to tailor solar water heaters to the needs of farming consumers. For the analysis used for this project, the assumption has been made that the solar collector for the agricultural market will produce 5 t (or m3) of hot water per day from approximately 20 m2 of collector surface. This hot water will be stored in a 1000 liter (1m3) tank until ready for use. The cost of the system delivered and installed in rural areas has been estimated at about $20,000 each. For the demonstration phase, it is proposed that 5 such systems be installed, and that they benefit from the same 80% grant element as the other demonstration technologies. Again, during the “early adopter” and “market maturation” phases, the eligible grant element will be reduced to 60% and 40% respectively, or to the level decided by the Steering Committee. For the investment phases, it is estimated that 15 solar collectors will be sold and installed during the first two years of project operation, and that 45 collectors will be installed during years 3 and 4. Altogether, the entire project is estimated to support the installation of approximately 65 solar water heaters. The assumption is that under the baseline, some form of fossil-fuel or electricity would be used to heat these greenhouses, so that these activities will reduce future GHG emissions. However, as such systems are not yet in operation in Uzbekistan, their potential to actually reduce GHG’s will be explored during the demonstration phase of the project. Energy Efficient Pump Sets The financial internal rate of return of installing an energy efficient pump is estimated at 19 percent, with a simple payback period of 5.03 years and a net present value of US$8,969 in financial terms. Accordingly, investing in energy efficient replacement of worn-out pumps appears to be profitable and attractive from the individual farmers’ perspective. Table 6: Financial Analysis of Illustrative Energy Efficient Improvement of Irrigation Pumps Current situation; Energy efficient pump. Pumping type; SNP-500/10; А30ГЦ—0.3/7. Pumping height (m); 5.31; 5.31. Irrigated land area (ha); 380; 380. Pump capacity (m3/s); 0.5; 0.3. Pump efficiency; 67%; 80%. Pumped water per year (thousand m3); 9112; 9112. Electricity consumption per year (kWh); 314,639; 228,555. Electricity costs per year (US$) at unit cost US$ 0.05/kWh; 15,731.95; 11,427.75. Energy savings per year (kWh); N/A; 86,084. Value of electricity savings US$; N/A; 4304. Capital costs (excl. O&M) US$; N/A; 21658. FIRR (at 12%); N/A; 19%. NPV at 12% in US$; N/A; 8969. Simple payback; N/A; 5.03. Total tCO2 avoided (20 year period); N/A; 988. Similar to RE technologies, the proposed approach for supporting energy efficiency improvements of irrigation pumps is to provide 80 percent of the investment costs during demonstration stages, 60 percent of the investments costs during the early years, and 40 percent of the costs in the final years (years 3 and 4). The values of these contributions are summarized in Table 7. Table 7: Project Financing of Grant and Loan/Equity for Energy Efficient Pumps Energy Efficient Pump. Stage 1: demonstration. Total costs; 30,000. Grant (80%); 24,000. Loan/Equity (20%); 6,000. Stage 2 (years 1 and 2): early adopters. Total costs; 30,000. Grant (60%); 18,000. Loan/Equity (40%); 12,000. Stage 3 (years 3 and 4): market maturation. Total costs; 30,000. Grant (40%); 12,000. Loan/Equity (60%); 18,000.

B.7. Outline the coordination with other related initiatives:

The project is coordinated with initiatives supported by the OECD, UNDP, FAO, GIZ, ADB, the Central Asia Country Initiative for Land Management (CACILM), and the World Bank-financed Central Asia Hydrometeorology Modernization Project. Formal co-financing by partners is not anticipated. Extensive coordination with other partners engaged in renewable energy, energy efficiency and land degradation mitigation began during preparation of the project and would continue during implementation. OECD is supporting preparation and consultation on a new draft law on renewable energy. UNDP has initiated the “Supporting Uzbekistan in transition to a low-emission development path” (LED) project to support the evolution of policies for improved technologies to introduce energy efficiency measures among public and private users, and assist in harnessing potential future financing flows and clean technology transfer opportunities. UNDP in cooperation with CACILM Secretariat is also preparing a PIF for a new GEF project, “Reducing pressures on natural resources from competing land use in non-irrigated arid mountain, semi-desert and desert landscapes of Uzbekistan,” which would complement the irrigated land degradation mitigation activities to be carried out under the proposed Sustainable Agriculture and Climate Change Mitigation Project. FAO is preparing a new global GEF project, “Land Degradation Assessment and Monitoring for Sustainable Land Management Decision Support and Scaling Up of Best Practices,” in which Uzbekistan will participate. The FAO project will provide important complementary technical assistance and support for monitoring UNCCD implementation at the national level, access to sustainable land management data bases, and regional and global cooperation mechanisms that will benefit Uzbekistan. The German International Society (formerly GTZ) in Uzbekistan has supported several pilot projects in energy efficiency and renewable energy, good agricultural practices, greenhouse production, integrated and biological pest management, and agribusiness value chain promotion in the Aral Sea region. The GTZ pilots demonstrated the strong demand for these renewable energy technologies and sustainable agricultural practices, but also brought to the foreground the limited knowledge of the technology among farmers and also the limited availability of this equipment in the market. The pilots offer valuation lessons for the proposed project, and may be eligible to be scaled up or replicated in other regions of the country. Introduction of a service to send timely weather forecasts to mobile phone subscribers would be supported by the new Central Asia Hydrometeorology Modernization Project, which will strengthen hydrometeorology services in the region. ADB is working actively with the Government and UZBEKENERGO to introduce large-scale solar power and carry out solar mapping country-wide. The ADB’s focus on large-scale solar is quite distinct from that of the WB GEF project, which in contrast would target on-site use by small and medium-size rural farms and agribusinesses. A donor’s forum was convened during preparation of the proposed GEF project to draw on these experiences and to ensure good coordination of these inter-related initiatives; the donor’s forum would continue to operate during implementation of the GEF project

C. GEF Agency information: C.1 Confirm the co-financing amount the GEF agency brings to the project: The International Development Association (IDA) has provided a credit for the baseline RESP-2 project in the amount of US$67.96 million, which will also be co-financed by the Government with an amount of US$6.58 million and by the beneficiaries with an amount of US$0.460 million. This brings the total co-financing that the GEF agency is bringing to the overall project to US$75 million. Additional financing in the amount of US$40 million has been approved in FY13 to supplement the credit line and capacity building components of the baseline project..

C.2  How does the project fit into the GEF agency’s program (reflected in documents such as UNDAF, CAS, etc.)  and staff capacity in the country to follow up project implementation:

The proposed GEF project is consistent with the outline of the new Country Partnership Strategy (CPS) recently developed by the World Bank and Uzbekistan for FY12-15.  The overall goal of the CPS is be to support efficiency, competitiveness, diversification and social equity policies, with continued attention to the agriculture sector.  A key focus of the Bank’s partnership strategy in agriculture and rural development is to help the Government in its efforts to address the issues of national land resource degradation. The project will contribute to the CPS by addressing climate change adaptation and mitigation and the environmental challenge of land degradation to ensure sustainable agriculture development and reduce poverty.  Finally, the 2nd Rural Enterprise Support Project (RESP-2), which the GEF grant would co-finance, was included in the Country Partnership Strategy for the Republic of Uzbekistan prepared for the fiscal years of 2008-2011.

The GEF project would be partially blended with, and will co-finance, the Second Rural Enterprise Support Project (RESP-2) to provide financial and technical support in achieving the milestones of the Country Partnership Strategy, namely:

- supporting the further development of private sector farming;

- strengthening infrastructure and services required by private farmers;

- increasing and encouraging commercial banking sector lending to agriculture;

- addressing land quality and degradation problems associated with irrigation and drainage.

The World Bank TTL for RESP-2, is based in the Country Office in Tashkent, and will be responsible for oversight of the proposed GEF project. Procurement and financial management staff are also available to support the project from the Tashkent office. The Bank team will include specialists in credit line finance, agriculture, irrigation and drainage and environment (including climate change and renewable energy technologies). The team will also draw on the Bank’s extensive global experience in introduction of innovative renewable and energy efficiency technologies and in land degradation mitigation.

part iii:  institutional coordination and support

- institutional arrangement:

See below.

- project implementation arrangement:

The Rural Restructuring Agency (RRA), which is the same Project Implementation Unit (PIU) that is implementing the parent RESP-2, would provide daily management, administration and coordination of the project, including procurement, financial management, monitoring and reporting to National Secretariat of the Central Asian Countries Initiative for Land Management (NSEC CACILM), as well as technical and other oversight in accordance with GEF and World Bank rules and procedures. A range of civil society organizations, donor and government agencies are expected to participate in project networking and dissemination activities.

Part IV: Explain the alignment of project design with the original PIF

The final project design is overall very well aligned with the original PIF. Components, activities and budget are the same. The project objective (PO) is re-phrased from PIF PO: current PO: (i) promote the introduction of renewable energy and energy efficiency technologies of relevance to agri-businesses and farms; and (ii) strengthen capacity for improving degraded irrigated land and water conservation. PIF PO: Promote the use of renewable energy for the provision of rural energy services and improve flows of agro-ecosystem services to sustain livelihoods of local communities in Uzbekistan The one substantive change from the PIF stage came about when the project team was discussing the energy needs of on-farm, irrigation pumping. As most larger-scale irrigation pumps are owned and operated by the Government, promoting their replacement with newer, more efficient pumpsets did not make sense under the business model adopted under this project. On the other hand, the smaller, on-farm pump-sets are the responsibility of the individual farmers that own and operate them and therefore could be reached through the rural, farmer finance model being utilized to provide credits for renewable energy for farmers. Hence, these small-scale, irrigation pumps have been identified as filling an important need in rural Uzbekistan and have been included in the goal and objectives of the project. Farmer demand will determine what fraction of the final financing under the project goes to the renewable energy options or the energy-efficient pump-sets.

PART V: Approval/endorsement by gef operational focal point(s) and gef agency(ies)

- Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): ): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Dr. Sergey Myagkov | Deputy Director of NIGMI of UzHydromet | Hydrometeorological Research Institute | 07/29/2011 |

B.  GEF agency(ies) certification

This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for CEO endorsement/approval of project.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Karin Shepardson GEF Executive Coordinator The World Bank |  | December 21, 2012 | Angela Armstrong, GEF Regional Coordinator Dilshod Khidirov Task Team Leader | (202) 458-0975 +5771-255 | aarmstrong@worldbank.org dkhidirov@worldbank.org |

ANNEX A:  PROJECT RESULTS FRAMEWORK

| Global Environmental Objectives |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| . |  |  |  |  |  |  |  |  |  |  |  |
| PDO Statement |  |  |  |  |  |  |  |  |  |  |  |
| The Global Environmental Objectives of the proposed Project are to (i) promote the introduction of select renewable energy and energy efficiency technologies of relevance to agri-businesses and farms; and (ii) strengthen capacity for improving degraded irrigated land and water conservation. |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |
| Global Environmental Objective Indicators |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Cumulative Target Values |  |  |  |  |  | Data Source/ | Responsibility for |
| Indicator Name | Core | Unit of Measure | Baseline | YR1 | YR2 | YR3 | End Target |  | Frequency | Methodology | Data Collection |
| Number of hectares of irrigated land where degradation has been reversed |  | Hectare(Ha) | 0 (incremental area) | 0 | 0 | 450 | 900 |  | Quarterly | Project Monitoring | RRA |
| Renewable Energy technology demonstrations in the project areas |  | Number | 0 | 5 | 15 | 25 | 55 |  | Quarterly | Project Monitoring | RRA |
| Support formulation of the regulatory framework to assist integration of renewable energy into the rural energy system |  | Text | Existing draft RE policy and regulation documents |  | Draft regulatory framework revised and consulted | Draft regulatory framework revised and consulted | Draft regulatory framework revised and consulted |  | At end of input | Project Monitoring | RRA |
| GHG emissions avoided by the project (in Tons CO2 equivalent) |  | Metric ton | 0 | 0 | 200,000 tons CO2eq over lifetime of investment | 1,500,000 tons CO2eq avoided over lifetime of investment | 3.5 million tons CO2eq avoided over lifetime of investment |  | Estimated at mid-term and final review | Project reports especially investment records | RRA |
| . |  |  |  |  |  |  |  |  |  |  |  |
| Intermediate Results Indicators |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Cumulative Target Values |  |  |  |  |  | Data Source/ | Responsibility for |
| Indicator Name | Core | Unit of Measure | Baseline | YR1 | YR2 | YR3 | End Target |  | Frequency | Methodology | Data Collection |
| Investment in renewable energy in the agri-business sector |  | Number | 0 | 60 | 800 | 1400 | 2370 |  | Quarterly | Project Monitoring | RRA |
| Number of workshops for farmers on relevant practices for irrigation/land conservation/EE (men and women) |  | Number | 0 | 0 | 50 | 100 | 150 |  | Quarterly | Project Monitoring | RRA |
| Number of workshops for equipment and service providers on legal issues, regulations, contract law, guarantees, health and safety etc |  | Number | 0 | 0 | 35 | 70 | 90 |  | Quarterly | Project Monitoring | RRA |
| Number of workshops held to inform/disseminate selected RE technologies and publicize the RESP-2 credit line |  | Number | 0 | 50 | 120 | 190 | 256 |  | Quarterly | Project Monitoring | RRA |
| . |  |  |  |  |  |  |  |  |  |  |  |

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

Based on this PIF screening, STAP’s advisory response to the GEF Secretariat and GEF Agency(ies): Minor revision required.

STAP believes the World Bank proposal "Sustainable Agriculture and Climate Change Mitigation Project" (SACCMP) in Uzbekistan is scientifically and technically viable. The problem and baseline are well defined, and the project components are clear. STAP believes, however, the proposal could be strengthened in several ways. Its recommendations are listed below.

1. The linkage between the project Components, especially 1 and 2, is obscure and may have adverse socio-economic impacts at the local level.  It is unclear, for example, whether the enhancement of financial service provision will be primarily taken up for the rehabilitation of I&D. What will be the distributive effects of this better financial access; will only local elites be able to take advantage; will this increase gender differentiation?  In MFA projects in general because of their complexity and difficulty to manage, STAP would prefer to see a tighter focus on a core problem, bringing multiple global environmental benefits through a variety of routes such as reduced GHG emissions, C-sequestration and protected ecosystem service benefits. So, the project proponents are urged to re-examine the basket of activities, identify the complementarities and linkages, and more clearly specify the multiple GEBs with targets.

Team response:  As a multi-focal area project, SACCMP seeks to fulfil development objectives in both climate change and land degradation, designed to complement the UZ RESP-2 project. Linkages between Component 1 and Component 2 are primarily in concentration of the activities in the same general project areas, which contributes to efficiency in implementation by using the services of the same oblast level RRA office, as well as more focused interventions for the eligible SME and  farmers.  The SACCMP PDOs are to (i) promote the introduction of renewable energy and energy efficiency technologies of relevance to agri-businesses and farms; and (ii) strengthen capacity for improving degraded irrigated land and water conservation.  The bulk of the funds are from the CC focal area for technology demonstrations and investments to reduce GHG emissions. The renewable energy component of the project in particular is expected to have a positive impact on female farm family members, who would benefit from the availability of biogas for cooking and heating. All family members would potentially benefit from greater farm productivity from availability of improved fertilizer and from expanded profitable agribusinesses (e.g., dairies, greenhouse produce) that could be supported as part of renewable energy investments.  All training and outreach activities will include women business owners and farmers as well as general audiences, and the project M & E system will capture the impacts on women.  To date, RESP 2 has recorded 218 jobs created for women from the financed investments and 15% of those attending the RTAS training courses have been women.

Resources from RESP-2, the GEF project, and Swiss Development Corporation (SDC) (parallel grant financing) would be pooled to support improved management of agricultural systems and water resources through the introduction of technologies and good practices for irrigated land. Activities under this component would aim at introducing technologies and management approaches for controlling and reversing irrigated land degradation.  This includes the introduction, testing and demonstration of integrated low-cost, low-risk water and land management technologies, such as drip irrigation, salinity mitigation of marginal land, water re-use, soil quality enhancement, pumping for groundwater extraction, alternative cropping, and other techniques and practices to increase water use efficiency and agricultural productivity.  This component would improve knowledge, skills and know-how of farmers (including women farmers) and local communities and promote the transfer of demonstrated technologies and SLM practices through the Farmer Field School (FFS) approach.  These activities would be targeted to the raions participating in the Irrigation and Drainage Component of the parent project, which are receiving funds and technical assistance to repair and upgrade irrigation infrastructure.

GEB targets are identified in the results indicators:

- GHG emissions avoided by the project.

- Number of hectares of irrigated land where degradation has been mitigated.

- Support the formulation of the regulatory framework to assist integration of renewable energy into the rural energy system.

- Renewable Energy technologies successfully demonstrated

2. STAP appreciates that agri-business and the market access more generally is a driver for rural development and improved livelihoods. However, the link between such rural enterprises and GHG emissions needs to be made

Team response:  The second largest source of GHG emissions in Uzbekistan is agriculture, which accounted for 8.2 percent of GHG in 2005. The majority of GHG emissions from agriculture (not related to fuel combustion) is due to fermentation and agricultural soils. The agricultural sector is also a major consumer of electricity, using 24 percent of final electricity consumption. This is as much as the residential sector consumes; 70 percent of the electricity consumption by the agricultural sector is used for irrigation pumping.  The project would promote the market for low-carbon technologies (both renewable energy and energy efficient) in the agricultural sector and is consistent with the GEF Climate Change (CC) Mitigation focal area objectives.  It would also contribute to the CC focal area Strategic Objective 3 “promote investment in renewable energy technologies,” with emphasis on agri-businesses and rural communities.  It would also be consistent with GEF’s Climate Change Mitigation objective 2 (CCM-2) “promote market transformation for energy efficiency in industry and the building sector”. The proposed project would directly respond to the strategic goals of the GEF-5 strategy in the Climate Change Mitigation focal area, namely, promoting the use of renewable energy and enhanced energy efficiency in the provision of rural energy services.  As such, it supports the adoption of new, low-GHG emitting energy technologies. This component addresses priority needs identified by the Government through supporting measures to mainstream renewable energy in Uzbekistan. It will support the introduction of relevant renewable and energy efficient technologies and undertaking related capacity building in rural areas.

3. Make the outputs more explicit. For example, it would be good to specify further how pilot demonstrations of renewable energy technologies the project will develop (component 1), or how many information dissemination workshops the project will organize (component 3).

Team response:  These outputs are now clearly defined for all components in the PAD.

4. STAP has a number of concerns over broad approaches/targets of the project as well as choice of technologies. There appears to be no intended financial cost-benefit analysis, which will be crucial in understanding the rationality for local people of taking up the elements of the project. For example,

a.	The drivers of degradation of irrigated crop lands. Identification of drivers of degradation would assist in identifying the interventions.

b.	Ecosystem services to be targeted under the LD FA need specifying

c.	Scientific rationale for selecting RETs for intervention (such as   Biogas, Solar and Biomass)

d.	Why only off-grid technologies are considered and why not grid connected RETs.

e.	How is climate resilience built into the project?

Team response:  These elements are now clearly defined for all components in the PAD.

5. STAP acknowledges the World Bank's intentions to provide more accurate estimates of the expected CO2  emission reduction for each renewable energy technology selected by the project beneficiaries. STAP would further recommend for the World Bank to specify what methodology (ies) will be used to estimate and monitor the CO2 reduction generated by each technology. This will assist the project detail explicitly the global environmental benefits generated through renewable energy interventions. The information could be provided at the time of CEO endorsement.

Team response:  The estimates of the expected CO2  emission reduction for the primary renewable energy technology being deployed (biogas) and for irrigation pumping efficiency have been carefully estimated and are included in the package.  Methodologies have been identified to estimate and monitor the CO2 reduction generated by each technology and the project overall.  The methodologies used to estimate and monitor the CO2 reduction generated by each technology in the project are described in the PAD.

6. Currently, the expected global environmental benefits generated through sustainable land management are described broadly as for example: "mitigation of irrigated land degradation" and "promoting water conservation in agriculture". STAP encourages a more explicit definition of the expected global environmental benefits generated through sustainable land management interventions.

Team response:  These expected global environmental benefits generated through sustainable land management interventions are now clearly defined for the land degradation mitigation component in the PAD.

7. One underlining assumption in the proposal is that the project will be able to reverse land degradation caused by irrigation. However, the proposal also should include the difficulties, associated with reversing salinity due to biophysical factors, and the potential risks of not restoring soil matter.

Team response:  The technical and other risks associated with mitigating land degradation have been taken into consideration and are now clearly defined for the land degradation mitigation component in the PAD.

8. On knowledge management and uptake, STAP recommends for the World Bank to specify how its experience on irrigation-induced salinity in the region is expected to contribute/strengthen the project's effectiveness.

Team response:  The project takes into account lessons learned from other WB projects and those supported by other organizations, and reflects these lessons in the project design.

9. In the incremental reasoning, the proposal raises "pumping for groundwater extraction" as a potential measure for controlling and reversing irrigated land degradation. It is not clear to what extent the project intends to use groundwater extraction measures, and whether they will couple with groundwater recharge interventions. Perhaps the World Bank could clarify these issues further.

Team response:  New use groundwater extraction investments will not be supported by the GEF project.

10. The proposal raises the climate change risks that will likely affect Uzbekistan,  mainly intense warming across the country. It also states that the proposed activities will contribute to mitigating and adapting for water scarcity. However, the proposal does not appear to build- in water conservation measures, or adaptive capacity to deal with water scarcity. Given the projected climate variability in the region (1 to 2.50 Celsius as projected by ADAPT) along with the current trend in rising temperatures noted in the proposal (average annual temperatures increasing by 0.290 Celsius since 1951), STAP recommends for the World Bank to specify more clearly in the project framework, incremental reasoning, and climate change risks what water conservation technologies and adaptive capacity measures (including institutional capacity needs and information needs for addressing climate risks and resilience enhancement measures) the project will seek to address in its efforts to mitigate and adapt to climate change.

Team response:  The project addresses water conservation measures and improving adaptive capacity to deal with water scarcity under Comp 2 and Comp 3.

| GEFSEC Comments at CEO Endorsement (27NOV2012) | Team Response |
| --- | --- |
| Comment No. 8: Please briefly describe in Part II A.1.1 the consistency of the project with the CCM-1 objective. | Done |
| Comment No. 9: Please address the consistency of the project with Uzbekistan Technology Needs Assessment. CCM/FJ - Dec 10, 2012: Thank you for the response provided. Please include the response in Part II A.2. of the CEO endorsement request. | The Uzbekistan TNA was presented to the COP in 2001. For the agricultural sector, it highlights several important sources of GHG emissions. The two most important are inefficient agricultural pumping and the need to process manure and crop wastes to better reduce methane emissions. In fact, the one activity highlighted as a priority is Use of agricultural biomass and wastes for energy generation. This proposal is fully consistent with the findings of the Uzbekistan Technology Needs Assessment. 12/15/2012 Done. See second para in Section II.A.2. |
| Comment No. 11: a) Please clarify or modify the assumptions considered for biogas plants benefits. While it is true that biogas sludge can be used as fertilizer, it seems unlikely that manure would not be used in agricultural fields in the absence of biogas plants, especially for the smaller ones. In such case, the main economic benefit of biogas plants (biofertilizer) could be questioned. b) Please clarify the baseline scenario (in the absence of GEF funded project) for PV water pumps and solar water heaters. Are fossil-fuel based water pumps or water heater currently used by farmers or would the project introduce the use of water pump for livestock and water heaters for on-farm applications? In the latter case, please address the potential impact | a) Currently animal wastes (manure and poultry droppings) are applied as organic fertilizers to the fields without any processing. However, these fertilizers litter the soil with weed seeds, they may facilitate spreading infectious diseases, and contribute to methane gas release to the atmosphere. Efficiency of these fertilizers is about 10-15%. Whereas after processing in the biogas facility the organic fertilizer significantly improves its qualities, the processing results in production of bio-fertilizer, which is free from weed seeds and pathogenic microbes, and which is 5-6 times more effective than traditional organic fertilizers. The processed fertilizer contains large amount of biologically active substances and microelements. Nutrition elements are transformed into forms more accessible for plants. It results in better balancing and higher degree of humification of organic substance. The organic substance serves as powerful energetic material for ground microorganisms, therefore after applying the processed fertilizer to the soil nitrogen fixing and other microbiological processes takes place. Application of bio-fertilizers increases crop yield by 15-20%. Our observations confirm that there is an additional value created for processed biogas slurry fertilizer that does not exist for unprocessed manure. The willingness to pay is higher and processed slurry fertilizer has a market value beyond the immediate vicinity of the farm where it is produced. Part of this value is in the ease of transport and part in the increased fertilizer value, as highlighted above. However, we chose not to include yet another set of assumptions for sensitivity analysis as any increase in the baseline value of the manure would serve to decrease project profitability, thereby increasing incremental cost. We consider it unnecessary to modify the economic assumption deployed in this instance. b) In the baseline scenario, PV water pumps and solar water heaters are rarely found in Uzbekistan. Existing pumps use fossil fuels or manual operation, and water heaters (if present) use fossil fuels. The project would replace fossil fuels for pumping and heating with solar systems, and would not increase water extraction or use to create groundwater issues. |
| Comment No. 12: a) Please address Q14 b) b) Please consider revising the level of subsidy for large biogas plants at stage 2 since it appears very similar to stage 1 level while it is expected to be significantly lower. 12/10 b) The comment is not addressed. The rationale for a similar subsidy level for large biogas plants at stage1 and 2 is not clear. One expects to have a progressive decrease of subsidy level from stage 1 to stage 2 b) Please state clearly in the CEO endorsement request that PV water pumps and solar water heaters will only be used in the project as replacement of existing fossil fuels based pumps or water heaters. (iii) if no economic viable option is identified for small scale biogas, consider the option of not going further with stage 2 and 3 for small scale plants and reallocating funds to other activities. . c) Please indicate the difference in investment between existing irrigation pumps and energy efficient ones. | a) Please see Q14 b) below. b) The task team and counterparts considered different subsidy levels for the different stages, and decided that the selected levels would be most effective under Uzbek conditions. 12/15 response The subsidy for the first large biogas plant has been capped at $500,000 for financial equity reasons. As there is only one large biogas plant being demonstrated, it will be dealt with as an International Competitive Bid (ICB) procurement. It is included more as a technology demonstration than a market-based, business-model demonstration. Those large plants envisioned during Stage 2 will really be the test of the business-model (financial intermediary loans complemented by subsidies). A new paragraph has been added on pages 16 and 17 of CEO memo. Wrt the PV water pumps and Solar H20 pumps, the text has been rewritten to clearly explain that the baseline assumption is that in the absence of this project, the energy for pumping of GH heating would likely be supplied from fossil fuels. See pp. 19 & 20. In response to this request, the Memo has been clearly rewritten to authorize the Steering Committee to allocate resources away from underperforming activities to those which are performing well. See paragraph preceding Table 3 in CEO memo and page 18. c) Cost data are not availing for existing irrigation pumps, which are very old, and impossible to replace exactly. All pumps now on the market would offer increased energy efficiency. The model used for the analysis is the most efficient model locally available. Please refer to PAD para 69 and Table 6 for additional detail. |
| Comment No. 14: a) Please delete outcome 3.3 in table A part I. CCM-3 has only 2 outcomes as per the GEF5 template (http://www.thegef.org/gef/node/3624). Output 3.3 should be kept (output of outcome 3.2). b) Please strengthen the sustainability of Component 1 by adding or modifying activities. Currently, the project intends to support renewable and energy efficient technologies through a gradually decreasing subsidy level (starting at 80% and going down to no less than 40% of considered investment). However, the project does not include activities to ensure that a sustainable delivery and financing mechanism may follow and thus ensure further diffusion of the technologies once the GEF grant is used up. The PAD mentions page 17 a transition to a non-subsidy market regime but the project does not propose a mechanism to ensure this transition. c) Please specify what kind of legal and regulatory framework the project intends to provide support to under Component 3 (the associated row in the PAD's result framework may then also need revision). Please clarify the scope of the considered support and its consistency with the project scope (PAD page 18 seems to consider a much larger scope than the scope of Component 1). Please also clarify the barriers currently faced in this domain and how the project may overcome these barriers. d) Please specify and justify with what country South-South cooperation will be promoted to mitigate the risk of choosing technologies poorly adapted to Uzbekistan's conditions. e) Please clarify the activities that the project would include and that would aim at developing the needed new business models mentioned in PAD page 20. f) Please clarify the link between activities under component 3 and the rest of the project. Several output do not seem directly related to Component 1 and 2 objectives. g) Please clarify the activities under output d) of Component 3, their scope and objectives. One wonders in particular whether this would be a CCM-5 objective (LULUCF emissions' monitoring). 12/10/2012 Comments b) Thank you for the information provided. Please add to the project additional activities aimed at supporting the government in designing and putting in place a sustainable subsidy scheme in case the value of the demonstrated technologies cannot be sufficiently demonstrated by the end of the project. c) The scope of support for legal and regulatory framework under Component 3 appears much larger than the scope of the project. A more focused approach in component 3 could enable to support a detailed implementation of a general legal and regulatory framework on renewable energy. e) The response provided is very general. It does not address what new business models the project is trying to develop and how project activities would specifically support the development of such models. In particular, it is not clear how the project will identify and set in place the necessary arbitration between supply companies, consumers, and financiers. g) Please clarify whether "carbon accounting" under output d) of Component 3 refers only to estimating the GHG impact of project activities or if the objective is to take part in setting up a national monitoring system of GHG emissions in the agricultural sector. In the latter case, this would relate to CCM-5 objective. | a) Done. b) The baseline project and its additional finance provide funding to rural borrowers for investments, including in RE/EE. The baseline project is introducing rural finance, which is growing in acceptance in the Uzbek banking community, and which is expected to continue to grow after the baseline project and GEF project are completed. During last phase of implementation of the GEF project, the costs of these technologies is expected to fall and the value of the technologies will be sufficiently demonstrated so that no subsidy should be needed. If there is one needed, government has agreed to consider some form of subsidy continuation if deemed absolutely necessary. c) There are the following barriers that impede development and implementation of renewable energy sources that will be addressed by the project: -- No established legal and regulatory foundation for renewable energy adoption or connection to the electrical grid; -- Absence of privileges and preferences for producers and consumers of renewable sources of energy; -- Weak development of production of renewable sources of energy; and -- High prices of renewable energy sources along with low prices for the energy resources. The project would support advisory services for: -- The Strategy for development of the renewable energetic in the country -- Adoption of a special law on implementation of the Strategy which should ensure interaction between various legal and physical persons, involved into this area, -- Development of state and technical standards, appropriate normative documents on production and usage of means and equipment for renewable energy, --Development of specific mechanisms to stimulate development of renewable sources of energy in the country, including customs and tax privileges, preferential credits for equipment producers, and for legal and physical persons who are implementing projects in this area -- Development of mechanisms for attraction of funds of international financial institutions and funds to implement the strategy for development of renewable energy sources -- Development of the “National Programme on usage of renewable energy sources” d) Mexico and China, based on experience with other good, current World Bank projects with similar objectives. e) Training, advisory services, mentoring/twinning arrangements and study tours. f) Component 3 provides capacity building and advisory services in support of Components 1 and 2 and the overall project objectives. g) Capacity building through formal training and on-farm workshops and field schools. 12/15/2012 response b) There is uncommitted budget available for this task. It has been described in the CEO memo, see para 3) on page 11 and will be included in the project. c) The focus of this activity is really on finding a way to ensure that RE generators under the project can sell their excess power to the grid. How exactly this will be achieved is uncertain and will be further investigated during the project. Clearly, the entire element of power-sector reform is too broad for this project to take on. See also p 11 and also PAD Annex 2. e) The business model being tested is really that of rural financial institutions providing subsidized loans to rural farmers for purchase or RE equipment. With time, if demand is sufficient and the RE technologies prove profitable enough, it should develop into a new line of business for the banks and for farmers. g) No, carbon accounting under Component 3 really only relates to measuring the results of project activities. See Table B and page 11 where this has been made clear. Also PAD, page 49. |
| Comment no. 15: a) Please describe the assumptions and methodology used for the various emission reductions estimates provided for assessment. Please also provide an estimate of the total emission reductions that may be expected thanks to the project, along with the assumptions used to calculate it. b) Please clarify the potential impact on CH4 and N2O emissions of the improved agricultural practices under component 2. 12/10/2012 Comments - The comment is not addressed. The PAD provides figures of emission reductions estimates for each technology separately but does not describe the assumptions and methodology used for these estimates. Also, the PAD does not provide an estimate of the total sum of emission reductions that may be expected thanks to the project, and does not provide the assumptions used to calculate it. b) The comment is not addressed. Component 2 activities aim at promoting technologies and practices to mitigate irrigated land degradation. They include changes in irrigation and fertilization practices that can influence N2O (and maybe CH4) emissions from agricultural fields. c) Please address Q11 b). | a) Please refer to PAD Appraisal Summary and Table 5 (p.29) for details and methodologies. 12/15/2012 All GHG assumptions are included in the final page of the Tracking tool. The PAD includes an estimate of the total tonnage targeted under the project, at about 3.5 Mt CO2eq. It is found in the ORAF and is consistent with the estimate in the CCM tracking tool. b) Utilization of renewable energy sources including biogas facilities reduces methane CH4 releases. In reviewing the experience from the irrigation enhancement in irrigation programs in Uzbekistan over the past decade, the reforms being introduced (drip irrigation, land leveling, deep ripping, etc.) have increased the productivity of the agricultural land and helped reduce water utilization. There may be some slight reduced in methane as leveled fields no longer allow water to pool unevenly as it is able to be absorbed uniformly across the field. With respect to fertilizer application (the source of N2O emissions), these activities have been shown to be fertilizer neutral, that is, there is little or no evidence of changing patterns of fertilizer use post project. The Uzbekistan TNA was presented to the COP in 2001. For the agricultural sector, it highlights several important sources of GHG emissions. The two most important are inefficient agricultural pumping and the need to process manure and crop wastes to better reduce methane emissions. In fact, the one activity highlighted as a priority is Use of agricultural biomass and wastes for energy generation. This proposal is fully consistent with the findings of the Uzbekistan Technology Needs Assessment. . c) please see 11 b above |
| Comment No. 17: Please clarify the role to be played in the project implementation by the key stakeholders and beneficiaries mentioned Part II B.5. 12/10/2012 Comments Thank you for the clarification. Please include the response in Part II B.5. | Ministry of Agriculture hosts the RRA and is responsible for implementation. UzHydromet, the Eco-Energy Center (under the State Committee for Nature Protection), Uzgip Institute, other government institutions would benefit from participation in capacity building activities. Rural SMEs, new private sector service providers and small and large scale farmers will benefit from access to grant funding for introduction of RE/EE technologies. 12/15/2012 Response Done. See page 13. |
| Comment No. 18: While the provided document indicates that a single water pump is unlikely to draw-down groundwater resources, please clarify the impact of the development of numerous water pumps used by several farmers taping in the same groundwater resources. | Pumps would operate on existing wells without increasing water consumption. |
| Comment No. 19: Please briefly explain the lessons learned from existing GTZ pilots mentioned in PART II B.7. 12/10/2012 Comments Thank you for the clarification. Please clarify how the project will address the acknowledged weak market access to equipment. | The GTZ pilots demonstrated the strong demand for these technologies and sustainable agricultural practices, together with inadequate capacity and limited availability of this equipment in the market. Done, see p 21. 12/15/2012 Response. It is not clear what was meant by “weak market access to equipment” so the phrase was eliminated. The real issue is that the RE industry in Uzbekistan exists and has reasonable technical capacity, but without the latent demand being released (the goal of this project), there is little incentive to market the equipment, to improve upon it, and to find economies of scale. This is inherent in the activities proposed. |
| Comment No. 20: Please clearly specify, in Table F project management cost, the nature of the cost item "Others". | No budget is allocated for “Others.” |
| Comment No. 27: Tracking tools comments. 12/11/2012 Comments GEF expects that LD GEBs will be measured during project implementation and reported trough the tracking tool by mid-term review and end of project. 12/10/2012 d) The comment is not addressed. The project will demonstrate 4 technologies (biogas plants, solar photovoltaic water pumps, solar water heaters and collectors, and energy efficient pump sets). The tracking tool only indicates 2 (row 39). Please revise the number of innovative technologies demonstrated or deployed. i) The comment is not addressed yet. Please fill in rows 95 and 107 with the expected impact of photovoltaic water pumps. Please fill in rows 96 and 108 with the expected impact of solar water heaters. Please make sure the CO2 impact of these two elements is taken into account in row 112. Once Q15 is cleared, further review will check the consistency between the figures provided to address Q15 and the figures presented in the tracking tool | The CC tracking tool has been revised. 12/15/2012 Response LD Tracking Tool has been updated to better reflect project context and impacts. In addition, it is agreed that LD GEBs will be measured during project implementation and reported at mid-term and project completion through the Tracking Tool. 12/15/2012 The tracking tool has been revised to allow for 3 technologies under CCM1 (biogas, EE pumps, PV pump-sets), but the fourth cannot be included as there is no space or flexibility. Therefore, a note has been added mentioning solar greenhouses, which are the most experimental of the technologies, and considered the riskiest. However, adjustments were made to the wording of Indicator 2 in the Results Matrix to measure “# of Technology Demonstrations” to be distinct from this indicator in the GEF tracking tool. There are 55 demonstrations targeted under the project, but only 4 technologies targeted. - Row 95 and 107 are filled in. Numbers for 96 and 108 cannot yet be estimated, as mentioned in the assumptions page. The PV number is included in the RE total in row 112. Figures are consistent. The LD tracking tool does not estimate GEBs because the specific sites and types of degraded land mitigation approaches will be identified during implementation. The criteria for the sites and selection of mitigation technologies will be defined in the PIP. |
| Comment No. 28: Please provide a budget for the proposed M&E plan. 12/10/2012 The comment is not sufficiently addressed. Please indicate in part I.H. of the CEO endorsement request: the total M&E budget, and the response provided to Q28 | M&E costs include the M&E consultant; other M&E costs are covered by the RRA office operating expenses. 12/15/2012 Para’s in Part I. H have been adjusted to reflect the current situation. Also, uncommitted funds are available for further monitoring needs. |
| Comment No. 29: a) The response provided to STAP recommendation 1 does not address the issue of the linkage between the project Components 1 and 2. b) STAP recommendation 5 is not addressed. Please specify the methodology (ies) used to estimate and monitor the CO2 reduction generated by each technology in the project. | The STAP responses have been revised and highlighted above. 12/15/2012 Methods and assumptions are listed in the fourth page of the tracking tool. |
| Comment No. 33: Please address the above comments Q8, Q9, Q10, Q11, Q12, Q14, Q15, Q17, Q18, Q19, Q20, Q27, Q28, and Q29. | These are addressed above. |

ANNEX C:  CONSULTANTS TO BE HIRED FOR THE PROJECT USING GEF/LDCF/SCCF/NPIF RESOURCES

| Position Titles | $/ Person Week* | Estimated Person Weeks** | Tasks To Be Performed |
| --- | --- | --- | --- |
| For Project Management |  |  |  |
| Local |  |  |  |
| (a) (i) Renewable Energy Technical Specialist: (ii) Credit Line/Grant Specialist (iii)M&E Specialist (iv) Procurement Officer (v) Translator | 196.6346 | 1,248 | Detailed term of references will be developed by the Rural Restructuring Agency and submitted to the Bank for review. |
| Equipment, Goods and Audit Surveys | 127,050 |  |  |
| General office costs (papers, photocoping etc), Communication, and other miscellaneous cost | 193,988 |  |  |
| Travel cost | 26,000 |  |  |
| International |  |  |  |
|  |  |  | . |
| Justification for travel, if any: |  |  |  |
| For Technical Assistance |  |  |  |
| Local |  |  |  |
| Training, Information Centres and Media assistence | 1,472,300 | 346 workshops | (i)Training in Legal Issues and Regulations to Equipment Operators and Service Providers; and (ii) Farmers Workshops in RE and Environmental Matters |
| International |  |  |  |
| International Specialist - to Assist with Supporting RE Regulations | 3,000 | 52 | Detailed term of reference will be developed by the Rural Restructuring Agency and submitted to the Bank for review. |
| International Specialist - Capacity Building to UzHydromet | 3,000 | 17 | Detailed term of reference will be developed by the Rural Restructuring Agency and submitted to the Bank for review. |
| International Economist - Assessing Feasibility of Demonstration Units and Training Local ToT and other staff | 3,000 | 86 | Detailed term of reference will be developed by the Rural Restructuring Agency and submitted to the Bank for review. |
| International consultant firm for demonstrating and promoting sustainable land management practices | 3,500 | 310.0766 | Detailed term of reference will be developed by the Rural Restructuring Agency and submitted to the Bank for review. |
| Study tour and provision of assistence to update solar/wind maps | 3,000 | 28 | Study tour to the developed countries to see and learn RE activities |
| Justification for travel, if any: Travel and per diems for training PIU staff in RE - $40,000 |  |  |  |

*  Provide dollar rate per person week.    **  Total person weeks  needed to carry out the tasks.

Annex d:  status of implementation of project preparation activities and the use of funds

A.  explain if the ppg objective has been achieved through the ppg activities undertaken.

n/A

B.  describe findings that might affect the project design or any concerns on project  
         implementation, if any:

n/A

C.  provide detailed funding amount of the ppg activities and their implementation status in the 
        table below:

| Project Preparation Activities Approved | Implementation Status | GEF/LDCF/SCCF/NPIF Amount ($) |  |  |  | Cofinancing ($) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Amount Approved | Amount Spent Todate | Amount Committed | Uncommitted Amount* |  |
| Total |  | 0 | 0 | 0 | 0 | 0 |

*  Any uncommitted amounts should be returned to the GEF Trust Fund.  This is not a physical transfer of money, but achieved  through 
             reporting and netting out from disbursement request to Trustee.  Please indicate expected date of refund transaction to Trustee.

It is important to consult the GEF Preparation Guidelines when completing this template

Project ID number will be assigned by GEFSEC.

Refer to the Focal Area/LDCF/SCCF Results Framework when filling up the table in item A.

GEF will finance management cost that is solely linked to GEF financing of the project. PMC should be charged proportionately   
   to focal areas based on focal area project grant amount.

Same as footnote #4.

Source: Sustainable Development of Livestock Sector in Uzbekistan: Status and Recommendations, Analytical Review, UNDP, #1, 2008.

This pump type is locally produced by SUVMASH JSC Company located in Tashkent, who is the only large pump manufacturer in Central Asia.

Compared to capital costs of the illustrative example (i.e., US$21,658), this cost estimate (i.e., US$30,000) includes O&M and leeway for potential cost increases associated with different pump types.